FLAGSHIP PROGRAMME

CSIR Water Sustainability Flagship

Integrated Solution

Implementation Plan

2013/14

Document Version: V1.0

Authors

This document was prepared by:

Dr H Pienaar (NRE); HPienaar@csir.co.za; 012 841 3957

Dr M Claassen (NRE); MClaasse@csir.co.za; 012 841 2385

Dr Chris Rust (BE)’ Crust@csir.co.za; 012 841 2927

Ms K Van Breukelen (CAS); KvBreukelen; 012 841 4128

Mr L Barwell (NRE); LBarwell@csir.co.za; 0218882576

Version History

| Date | Document Version | Document Revision History | Document Author/Reviser |
| --- | --- | --- | --- |
| April .. 2013 | 1.0 | Initial draft | M Claassen, C Rust, K v Breukelen |
| April 2013 | 2.0 | Reviewed with Coordinator and revised | L Barwell, M Claassen, C Rust, K v Breukelen |
| April , 2013 | 3.0 | Reviewed and revised following meeting with Project Sponsor | L Barwell, M Claassen, C Rust, K v Breukelen |

Approvals

| Date | Document Version | Approver Name and Title | Approver Signature |
| --- | --- | --- | --- |
| April , 2013 | 3.0 | Project Sponsor and Director | H Pienaar |

# Summary

| ## Financial year reporting |  |  |  |
| --- | --- | --- | --- |
| ## Participating Operational units/centres |  |  |  |
| ## External partners institutions/collaborators |  |  |  |
| ## Project leader/manager |  |  |  |
| ## Contact details |  |  |  |
|  |  | TRL range | Target |
| Publications/Reports | CSIR reports |  |  |
|  | Policy documents/frameworks/guidelines |  |  |
|  | Policy documents/frameworks/guidelines adopted by client |  |  |
| Technology Development | Hardware |  |  |
|  | Software |  |  |
|  | Processes |  |  |
|  | Products |  |  |
| Implemented/Operationalised in client environment | Hardware |  |  |
|  | Software |  |  |
|  | Processes |  |  |
|  | Products |  |  |
| Commercialisation | Number of licences |  |  |
|  | Royalties |  |  |
|  | Start-ups |  |  |
| Partnerships | Engaged (number) |  |  |
|  | Secured MoA/U/Contracts |  |  |
|  | Technology transfer agreements |  |  |
| Funding | Internal funding (R) |  |  |
|  | External funding pending (R) |  |  |
|  | External funding secured (R) |  |  |

Available information indicate that large areas in South Africa experience ‘water stress’ and this situation is likely to continue in future. There are escalating demands for water from a growing population and expanding economy.

The disparity in service delivery provides many challenges associated with the requirement to address this and water is needed to ensure food security and energy security. There is a worsening of water quality in many rivers with a deterioration of reservoirs and ecosystems and especially rural communities face growing risks of water shortages and the health impacts of contamination.

Given the situation, problems and associated implications described above, the CSIR’s Water Sustainability Flagship (WSF) as indicated above, provides a mechanism to focus the organization’s capabilities and invite collaboration from strategic partners in contributing to solving the country’s water challenges. This provides an opportunity to give effect to the outputs from the CSIR’s R&D activities done under for example the Research Impact Areas (RIAs).

As depicted above, two parallel intervention processes are being followed, namely (1) a short-term approach focused on the water quality and efficiency components at Waste Water Treatment Works where the results should be realised within 1 to 2 years, and (2) the bigger picture where water quantity, quality and treatment efficiency at water basin scale are addressed and results realised within 3 to 5 years.

Since the intention of the CSIR Flagship initiative is to develop and implement current CSIR Technology Demonstrators (TRL 5 and above) to at least pilot scale (TRL 7 and above), a process was followed to identify suitable TRL 5+ products within CSIR that aligned with and addressed the needs within the identified Intervention Areas.

The essence (or overall objective) of the WSF is “to contribute to the equitable, efficient and sustainable use of water to ensure that South Africa attains its national and economic growth and development aspirations.” The expectation is that, through the WSF, products of research and technological/knowledge development produced by the CSIR will be further developed for implementation within a relatively short time frame and that these will have a positive/noticeable impact on the economy and society.

The failure of waste water treatment works at municipal level is being taken seriously by the relevant authorities. The DWA recently announced that the cost of addressing the problem is in the order of R500Billion. Taking a 1% (R50billion) as the market potential for the CSIR packaged solution, the risk of delays in packaging the technologies for role out is significant.

As reflected in the Logic Model adapted from RAND (www.rand.org) in the figure below, the anticipated output of the WSF is therefore to move beyond simply providing evidence in support of decision-making to a suite of practical and sustainable tools and technologies to assist practitioners and decision makers in the water sector.

Here the objective statement and underpinning strategic programme outcomes are used as the starting points. These reflect the WSF Focus Areas as discussed above.

To realise the desired impact some change has to be induced in the way the targeted stakeholder groupings address their mandated responsibilities. For the WSF these are defined as Intermediate Outcomes reflected in the second column from the right.

The key aspects of the WSF is seen to be the fact that the D & I activities are packaged as an integrated solution aimed at national and even regional replication. The innovation therefore lies in:

An integrated , multi-disciplinary solution, piloted in an Urban and Peri-urban environment that includes a predictive ability to provide current and future scenario-based insight into the quantity and composition of the effluent stream entering the waste water treatment system.

The focus on increasing the longevity of aging WWT plants by rehabilitating and upgrading the Anaerobic Digester component that leads to compliance of the solid waste stream, an energy cost reduction via biogas production and the value add (and associated job creation) of producing safe compost for sale and use in community gardens.

An efficient low cost integrated near real-time 1st level water quality monitoring system that allows for timely compliance evaluation and response at key nodes within the whole system to influence the Green Drop status of targeted municipalities.

As detailed below the WSF is a collaborative project that brings together researchers from across the CSIR and the private sector.

The detailed cashflow from the WSF fund for the 2nd year (2013/14) of the integrated project is detailed in the document and summarised in the table below. The PG and ‘Other’ funding is provided in the document

|  | April’13 | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan ’14 | Feb | Mrch | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IA1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IA2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IA3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Coord |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cont Pool1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |

Note 1: The Contingency Pool is a shared reserve to be managed by the Project Coordination Team to cover unforeseen expenses

A stage-gate assessment approach is proposed with Table 5.5 forming the basis for regular progress assessments

Assumptions affecting cost and schedule

Co-funding obtained for the capital expenses associated with the construction of the full scale AD in I

Programme implementation status as reported in April 2013

Overall it can be seen that the programme is on track to achieve the set objectives and impact within the set timeframe as summarised in the implementation plan.

The delay in implementing IA2 has occurred due to the procedural challenges experienced with securing co-funding for equipment from the DST. Application for funding from the DBSA Green Fund has progressed past the first stage and a decision is pending.

The intention and approach of the WSF has received positive feedback from a broad spectrum of stakeholders at all levels of society and governance and the focus is therefore correct.

Internal to CSIR a highlight is the degree of inter-disciplinary work that has been achieved as researchers share and learn from their colleagues in other research units. It is foreseen that a high level of transdisciplinarity will be achieved as implementation proceeds and results become available.

A constraint was the lack of funding available to maintaining momentum of the across-unit collaboration achieved during the planning stages of the WSF. The cross-pollinating and experiential learning environment created by regular sharing of results and workshopping of implementation challenges should form an important component of Flagship programmes. The intension is to actively pursue this approach in the next stages of the WSF.

Although the solution is packaged in three logical interlinked Intervention Areas, a summary of the progress of each of the Intervention Areas is provided below. Summaries of the progress of the programme schedule and the programme performance are also provided in the 2012/13 Annual Report.

Intervention Area 1: Planning and Governance in relation to Waste Water Treatment Works

As stated above, the identified problem statement for this intervention area is defined as:

Inadequate strategic, integrated and cooperative governance and planning for water sustainability constrains equitable access as well as sustainable and inclusive development.

In essence the brief is therefore to achieve water quantity, quality & efficiency at basin level, specifically relating to wastewater treatment works (WWTWs).

Current planning decision support systems developed to TRL 6-7 by the CSIR are available and enables the analysis of spatial and temporal development trends at a metropolitan as well as regional scale for the whole of South Africa.  The platform facilitates a shared understanding of development patterns and trends and the forces that shape them, by providing the evidence required to inform rigorous and robust debate amongst the various agencies of the state.

In addressing the underlying issues the existing CSIR technologies are being adapted for waste water applications both in the Metropolitan and Peri-Urban areas.

- The use of the urban simulation platform in the metropolitan regions addresses all three of these identified shortcomings by:

- Generating future settlement patterns for the larger metropolitan region of Gauteng including Ekurhuleni, Johannesburg and Tshwane, based on provincial and local spatial planning and policy scenarios.

- Modelling growth in informal settlement patterns including new and informal settlement expansion and backyard shack formation.

- Modelling future settlement patterns as a market response to a range of spatial planning scenarios as contained in the Gauteng Spatial Development Framework, the Ekurhuleni Growth and Development Strategy and Metropolitan Spatial Development Frameworks.

The results of the simulation process form the basis for the development of high level estimates of bulk waste water effluent discharge (yield) in each of ERWAT”s drainage area with a view to inform ERWAT’s waste water infrastructure investment planning. The evidence produced by the platform will assist ERWAT to optimise the capacity and efficiency of existing waste water treatment plants and to strategically direct infrastructure expansion to achieve greater efficiencies in the urban system over the medium to long term.

The Geo-Spatial Analysis Platform (GAP) is being used to spatially profile development in the Sekhukune Case Study Area. Spatial information (derived from the GAP Platform) is packaged in a spatial viewer with a view to facilitate a shared understanding of spatial development patterns and trends that shape the Sekhukune area and may impact on waste water generation and its downstream impact on the region.

Existing knowledge and technologies are being integrated into a spatial (GIS) based risk platform to assess, prioritise and mitigate the impact of WWTWs on ecosystem and human health. Decision support systems include the Assessment of Considerations for Water Use Allocations (ACWUA), which utilizes a Bayesian engine to evaluate decisions based on multiple criteria, particularly where information related to the decision is incomplete (uncertain). The ECO2 (Ecology to Economy) model provides a robust framework for the analysis of development opportunities, taking the availability of resources into account. This framework provides a good platform to facilitate discussions in a multi-party environment.

The structured decision support approaches are supported by the Water Sector Institutional Landscape (WSIL) scenario analysis, which maps key drivers of change and facilitates the evaluation options and decisions under different future conditions. The National Freshwater Ecosystem Priority Areas (NFEPA) framework uses systematic conservation planning to provide strategic spatial priorities for conserving South Africa’s freshwater biodiversity, within the context of equitable social and economic development, whereas Solar Water Disinfection (SODIS), the Phosphate Sensitivity Index, and SWAT hydrological model can also contribute to achieving a balance between development (and consequent WWTWs) and protection (of human health and the environment).

The project is operating within the budget of the current financial year, but additional funding will be required to further enhance the urban simulation platform during the next financial year.

With the exception of first round simulation results project deliverables are on schedule, but peer review of the platform and the verification of spatial planning scenarios and the evaluation of the urban simulation results will only happen during the latter part of April 2013, to accommodate the business cycle of the Metro.

There are no high priority risks (i.e. risks that could prevent the project from delivering on the objectives).  Minor risks (that impact mostly on the timing of the project) include:

- the non-availability  and poor quality data

- the unavailability of contingency funds to deal with unexpected issues or capitalise on opportunities

- the availability of officials to participate in living laboratory sessions due to the demands of the municipal business cycle, the schedules of officials and the fact that many officials function in an acting capacity and are not assigned to positions on a full time basis.

There are no specific issues associated with the IA1 component of the overall initiative.

Intervention Area 2: Solid waste/sludge treatment & management

The associated problem statement is:

Failing sewage treatment works impact on people’s health and water resources.

The main objective of IA2 is the implementation of a two stage anaerobic digester at the Hartbeestfontein waste water treatment plant of ERWAT using patented CSIR technology (TRL 5).

The stabilised sludge that will result from the digestion process will be used in a community benefit program that include the production of fertiliser from the sludge and the establishment of community gardens and community cooperatives to run those.

To date the following tasks have been completed:

- MoA with ERWAT signed

- Partnership with Barloworld Power established

- Co-operation with UP regarding sludge beneficiation established

- Co-operation with Ekurhuleni metropolitan municipality established

- Detailed planning of the activities to be carried out at the Hartbeestfontein site in collaboration with ERWAT and Barloworld Power

- Testing of sludge from ERWAT’s Hartbeestfontein wastewater treatment plant in the CSIR pilot plant

- Extensive interactions with the Department of Science and Technology (DST) on the requested funding of the project with ERWAT

- Development of the socio-economic baseline study on Thembisa and Sekhukhune

- Literature study on aerobic digestion.

- Develop and submit co-funding proposals to the DBSA Green Fund.

The project has been delayed due to the delay in funding approval from the DST. Activities related to the ordering and installation of equipment was therefore not conducted.

Intervention Area 3: (Near) real-time monitoring system for Waste Water Treatment Works

The problem statement being addressed is:

Failing sewage treatment works impact on people’s health and water resources.

The implementation of the near real-time monitoring, evaluation and response system via Water Sustainability Flagship (WSF) forms part of the Consulting and Analytical Services (CAS) Business Plan for the Remote “Real-time” Water Quality Monitoring Platform. CAS has partnered with Natural Resources and Environment (NRE) and Material Science and Manufacturing (MSM) units to produce the Water Quality Monitoring System (WQMS) at a TRL 6. This CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop certification.

Green Drop certification is a program specifically aimed at Waste Water Treatment Works (WWTW), it aims to ensure that WWTW continuously improve their operations so as not to impact negatively on the water bodies into which they discharge their end product. The Green Drop certification programme forms part of incentive-based regulation implemented by the Department of Water Affairs to identify and develop core competencies required in wastewater management. Compliance with the Green Drop certification programme will ensure that all Water Service Authorities are gradually and sustainably able to improve the level of wastewater management.

A decision was taken to focus initially on assisting with Green Drop issues, however the CSIR technology and its application covers the whole RDI value chain, namely Green Drop certificate support; Blue Drop certificate support; River Health Monitoring; Industry Effluent discharge; and “Green Scorpion” Screening support. The CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop Certification.

The project as planned has achieved the majority of goals set and is on schedule for completing all tasks as amended through the project.  A small contingency budget was awarded to cover costs of additional resources required to complete one task.  A high priority issue that remains is that of the algorithm development.  The methodology as proposed when planning the project proved not feasible.  The appropriate task was thus modified to accommodate a peer review of that methodology and water quality indicator relationships in order to make the decision as to whether to continue with this aspect of the WQMS commercial offering.  The results of this investigation have not discarded the option of algorithm development, however it is not clear as to how accurate these will prove in extended field trials and this must be noted when planning the next year’s investment.

Several changes were made to tasks during execution, these included the reduction of the number of installations (14 to 7) as requested by the Sekhukhune District Municipality as the responsible entity for the pilot WWTWs; the parallel increase in number and depth of assessment of WWTWs (15 instead of 14) and the development of a hand-held WQMS not foreseen when planning the project.  Software and Information and Communication Technology (ICT) hardware required more resources than planned for and this was covered by diverting funds from CAS’ field-related tasks.

# Project Charter

## Background

Water challenges in South Africa are well known and documented (e.g. DEAT, 2006; 2030 Water Resources Group, 2009; CSIR, 2010; DWA, 2011). The most significant challenges include increasing water scarcity, poor and ageing infrastructure, skills and capacity shortages in the water sector, increasing pollution, failure to meet environmental flow requirements, poor enforcement of regulations and potential impacts of a changing climate.

Given that water is a crucial, cross-sectoral input for all development and growth, its availability (and quality) will be a limiting factor across the country. Many initiatives to address these challenges have been taken up in the different sectors, though these have been fragmented and isolated often resulting in ineffective solutions at the national level. These include (1) The Department of Water Affairs (DWA) Water for Growth and Development (WfGD) Framework (January 2009) and (2) the (draft) DWA National Water Resources Strategy (NWRS II) (DWA, 2011)

The WfGD represents DWA’s strategic turnaround approach in managing the country’s water more effectively and efficiently in order to enhance economic and development goals as well as to respond to concerns raised regarding the state of water in the country over the past two years. These concerns include that South Africa will experience severe water shortages by 2025; Gauteng will run out of water in 2013; the state of South Africa’s water resources infrastructure (i.e. dams) is in a poor condition; South Africa’s rivers are severely polluted; and that municipal infrastructure (in particular waste water treatment plants) are failing, the latter having an added effect on the state of the rivers. A further concern highlighted is the lack of skills and capacity at various technical and managerial levels within the water sector. The WfGD Framework is responsive to the needs of various economic sectors and points to the relationship between water availability and the forms of economic activity that are dependent on available water supply of varying levels of quantity and quality depending on the technologies being used.

The (draft) National Water Resources Strategy (NWRS II) (DWA, 2011), identifies four challenges in the water perspective for South Africa, namely (1) Water underpins the socio-economic development of SA, (2) water resources in SA are limited and under stress, (3) SA’s future depends on timely resource planning, and (4) SA strives to be a responsible neighbour and global player. It lists three main water concerns which are associated with three of the challenges. These are:  (A) decreasing water security; (B) deterioration of ecosystems; and (C) deterioration of water & wastewater infrastructure.

In September 2008 the Minister of Water Affairs introduced a regulatory approach that has gained significant momentum as an Incentive-based Regulation. Two programmes, the Blue Drop Certification Programme for Drinking Water Quality Management Regulation and the Green Drop Certification Programme for Wastewater Quality Management Regulation define the concept.

The Green Drop process measures and compares the results of the performance of Water Service Authorities and their providers, and subsequently rewards (or penalises) the municipality upon evidence of their excellence (or failures) according to the minimum standards or requirements as defined. Awareness of this performance is obtained by pressure through the customers, the media, political classes and NGOs. The strategy revolves around the identification of mediocre performing municipalities who consequently correct the identified shortcomings, as well as the introduction of competitiveness amongst the municipalities and using benchmarking in a market where competition is difficult to implement.

Water Quality

A key conclusion from the Green Drop Certification Programme showed that many of South Africa’s waste water collection and treatment systems are failing. This impacts directly onto the water quality in the water resource system.

Waste water treatment occurs via one or more natural systems (i.e. wetlands, natural side-channel vegetation, sand or soil filters and in-stream reedbed systems), the so-called ecosystem services. Man-made waste water treatment works take on many forms with the conventional municipal works typically consisting of a combination of components including anaerobic digester technology.

The 2011 Green Drop Report (DWA, 2011) shows that the Green Drop Certification programme of 2010/11 verified the status of wastewater service delivery by hundred and fifty-six (156) municipalities that provide services via an infrastructure network comprising of 821 wastewater collector and treatment systems. Statistics taken from the DWA, (2011) report are summarised in the figure below and show that a significant number of the waste water collector and treatment systems did not reach the compliance threshold of above 50%. The Free State, Northern Cape and Limpopo Provinces have the largest challenges.

Green Drop Status: Water and waste treatment during 2010 – 2011

http://www.ewisa.co.za/misc/BLUE_GREENDROPREPORT/GreenDrop2011.htm

The Cumulative Risk Rating (CRR) included in the report provides a risk analysis that focuses on the wastewater treatment function specifically. It provides insight into the treatment component of the total municipal waste water management value chain. This component is one of the high risk components within the production chain and allows the municipality to identify and prioritise the critical risk areas within its wastewater treatment process and to take corrective measures to abate these. The results for 2011 show that the biggest deviation from the maximum value (CRRmax) that the deviation can reach occurs in the Free State, Limpopo and Eastern Cape Provinces with deviation values of 83%, 79% and 78% respectively. The deviation limits that define a critical state are in the range (90-100%).

## Statement of the problem/opportunity

The available information therefore indicates that large areas in South Africa experience ‘water stress’ and this situation is likely to continue in future. There are escalating demands for water from a growing population and expanding economy.

The disparity in service delivery provides many challenges associated with the requirement to address this and water is needed to ensure food security and energy security. There is a worsening of water quality in many rivers with a deterioration of reservoirs and ecosystems and especially rural communities face growing risks of water shortages and the health impacts of contamination.

Water quality problems in the Olifants River Basin

As indicated by the Green Drop Report (DWA 2011) and in particular the Cumulative Risk Rating (CRR) assessment, the failure of many urban, peri-urban and rural waste water treatment plants poses a real health threat to downstream populations as well as the functioning of natural resource systems. The figure below depicts the main components of the system and their logical linkages within which the waste water treatment plant forms the central point.

The schematic below is a simplified version of the wider system depicted above within which the problem occurs.

As shown in the figure above, the systems analysis reflects three logical clusters of interlinked ‘Intervention Areas’, each with an associated focusing problem statement defined below:

Planning and Governance in relation to Waste Water Treatment Works

Associated problem statement:

Inadequate strategic, integrated and cooperative governance and planning for water sustainability constrains equitable access as well as sustainable and inclusive development.

Solid waste/sludge treatment & management

Associated problem statement:

Failing sewage treatment works impact on people’s health and water resources.

(Near) real-time monitoring system for Waste Water Treatment Works

Associated problem statement:

The lack of (near) real-time system performance information hampers effective and efficient response

## Goal

Given the situation, problems and associated implications described above, the CSIR’s Water Sustainability Flagship (WSF) provides a mechanism to focus the organization’s capabilities and invite collaboration from strategic partners in contributing to solving the country’s water challenges. This provides an opportunity to give effect to the outputs from the CSIR’s R&D activities done under for example the Research Impact Areas (RIAs).

The essence (or overall objective) of the WSF is “to contribute to the equitable, efficient and sustainable use of water to ensure that South Africa attains its national and economic growth and development aspirations.”

The expectation is that, through the WSF, products of research and technological/knowledge development produced by the CSIR will be further developed for implementation within a relatively short time frame and that these will have a positive/noticeable impact on the economy and society.

## Objectives

As reflected in the Logic Model adapted from RAND (www.rand.org) in the figure below, the anticipated output of the WSF is therefore to move beyond simply providing evidence in support of decision-making to a suite of practical and sustainable tools and technologies to assist practitioners and decision makers in the water sector.

Here the objective statement and underpinning strategic programme outcomes are used as the starting points. These reflect the WSF Focus Areas as discussed above.

To realise the desired impact some change has to be induced in the way the targeted stakeholder groupings address their mandated responsibilities. For the WSF these are defined as Intermediate Outcomes reflected in the second column from the right.

The Outputs of the Development and Implementation (D & I) activities carried out under the WSF are depicted in the central two columns demarcated by the dotted line in the Logic Model diagramme above. Technologies (or ‘tools’) developed by the CSIR that are at a Technology Readiness Level (TRL) above 5 form the basis for the ‘quick win’ D&I activities over the first 12 to 18 month period. As indicated, these activities can only be achieved through effective and efficient collaboration across the capabilities in CSIR and within its external network.

Although the final end users (or target population) are the ‘People of South Africa’, the various levels of government are mandated to act on behalf of their constituents and to ensure a healthy and safe environment and are therefore seen as the Intermediate Customers.

To this end the South African Government has agreed on 12 outcomes as a key focus of service delivery work up to 2014. Each outcome has a limited number of measureable outputs with targets. For example, the Delivery Agreement for Outcome 10: Environmental Assets and Natural Resources that are valued protected and continually enhanced (www.environment.gov.za) has as Output 1 ‘Enhanced quality and quantity of water resources’ with sub-outputs of (1) water demand management, (2) water resource protection, and (3) regulation of water quality.

Aligned to assist the above, the expected results of the WSF are therefore to (1) facilitate changes in knowledge, attitude and behaviour of planners, water users (and effluent dischargers), and authorities in terms of the implementation of the required practices, procedures and policies that influence water quality, and (2) the adoption of relevant technologies by owners, funders, managers and operators of waste water treatment works in municipalities.

Two parallel intervention processes are being followed, namely (1) a short-term approach focused on the water quality and efficiency components at Waste Water Treatment Works where the results should be realised within 1 to 2 years, and (2) the bigger picture where water quantity, quality and treatment efficiency at water basin scale are addressed and results realised within 3 to 5 years.

Since the intention of the CSIR Flagship initiative is to develop and implement current CSIR Technology Demonstrators (TRL 5 and above) to at least pilot scale (TRL 7 and above), a process was followed to identify suitable TRL 5+ products within CSIR that aligned with and addressed the needs within the identified Intervention Areas.

The essence of the intervention plan is depicted in the summary figure below.

# Work breakdown structure

As described above, the key aspects of WSF is seen to be the fact that the D & I activities are packaged as an integrated solution aimed at national and even regional replication. The innovation therefore lies in:

An integrated , multi-disciplinary solution, piloted in an Urban and Peri-urban environment that includes a predictive ability to provide current and future scenario-based insight into the quantity and composition of the effluent stream entering the waste water treatment system.

The focus on increasing the longevity of aging WWT plants by rehabilitating and upgrading the Anaerobic Digester component that leads to compliance of the solid waste stream, an energy cost reduction via biogas production and the value add (and associated job creation) of producing safe compost for sale and use in community gardens.

An efficient low cost integrated near real-time 1st level water quality monitoring system that allows for timely compliance evaluation and response at key nodes within the whole system to influence the Green Drop status of targeted municipalities.

The following criteria were defined for selecting the pilot sites where the technology demonstration would be focused:

- Integrated solution (co-location)

- Local community-level need or high-risk water problem

- Representative of national scale problem

- Co-funding available from local sources

- Ease of access to the pilot area by CSIR teams

- Current CSIR initiatives underway (co-locate)

  - Good relationship with key stakeholders

  - Current externally funded complementary projects

The application of the selection criteria resulted in the definition of a single integrated experiment piloted in two complementary locations, namely:

- The ERWAT managed Hartbeestfontein WWTW located within an Urban setting in the upper Crocodile River catchment. The intervention would be focused on ‘Fit-for-use / purpose’ infrastructure improvement with a secondary aim for community job creation and household level impact via waste beneficiation and a community garden.

- The Sekhukhune District Municipality which is located in a Peri-Urban setting in the Upper Olifants River catchment where the focus will be on Green Drop status improvement.

The pilot sites are shown in the figures below.

The Hartbeesfontein Waste Water Treatment Works is located in an Urban environment upstream of the Rietvlei Dam

The Hartbeesftfontein WWTW

## Work packages/project phases

As discussed above, the first part of the WSF is focused on short-term (1 to 2 years) focused intervention followed by a medium term (3 to 5 Year) period where the packaged integrated solution will be expanded to catchment scale and more components of the system (e.g. the water quantity aspects) will be addressed.

Components (or Work Packages) of the integrated solution

A number of CSIR technology demonstrators that are aligned with the proposed integrated solution were identified. Three core technologies, all at TRL 5 or above were chosen as the core to the three interventions. These are briefly described below with the technical detail, along with the activities associated with the development and implementation of each are described in Appendices A, B and C of the full document (GWDMS#216950-Pta Gen).

The implementation of the technologies requires collaboration amongst researchers from BE, NRE, CAS, MSM, MDS and Meraka.

The overall objective of the integrative solution is to achieve water quantity, quality & efficiency at basin level, specifically related to wastewater treatment works (WWTWs).

Intervention Area 1: Planning and Governance

The Urban Growth Simulation Platform (UrbanSim) models spatially explicit patterns of urban growth over a 20-30 year period. Calibrating and adapting the modelling platform to facilitate the understanding and assessment of the impact of spatial planning and development on wastewater flows inflows to WWTW lies at the core of this intervention area. Existing knowledge and technologies will be integrated into a spatial (GIS) based risk platform to assess, prioritise and mitigate the impact of WWTWs on ecosystem and human health. This framework provides a good platform to facilitate discussions in a multi-party environment and facilitates a shared understanding of development patterns and trends and the forces that shape them, by providing the evidence required to inform rigorous and robust debate amongst the various agencies of the state.

The integrated solution will establish a platform to deliver different solutions at different levels, i.e. geographically (Plant, municipality, province, national), scales (small and large plants), governance (municipal, (inter)departmental, provincial, national), and temporal (short, medium and long term).

Intervention Area 2:  Revitalising Waste Water Treatment Works

The CSIR has developed a new anaerobic digester (AD) technology package that improves the performance of anaerobic digestion considerably compared with existing processes and equipment used at WWT plants.  The process is novel and consists of a two-stage, fully automated anaerobic digester that includes control of the critical parameters to optimize the process.  In addition, it reduces the retention time of the sewage in the system by almost half, thus increasing the capacity of such a system significantly.

The CSIR, in collaboration with ERWAT (the WWT service provider to Ekurhuleni municipality), will pilot this innovative technology package at full scale at one of ERWAT’s WWTWs upstream of the Rietvlei Dam near Tswane.

Intervention Area 3: Real-time water quality monitoring, assessment and response

The Green Drop certification programme in South Africa forms part of incentive-based regulation implemented by the Department of Water Affairs to identify and develop core competencies required in wastewater management. Compliance with the Green Drop certification programme will ensure that all Water Service Authorities are gradually and sustainably able to improve the level of wastewater management.

The Green Drop Certification program is specifically aimed at Waste Water Treatment Works (WWTW) and aims to ensure that WWTW continuously improve their operations so as not to impact negatively on the water bodies into which they discharge their end product.  In order for WWTWs to achieve Green Drop status, water quality monitoring is a key requirement.

The CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop certification.

The detailed technical plan and associated Task Detail sheets for Year 1 (2012/13) are shown in Appendix D of the full project document (GWDMS#216950 Pta Gen) and those for Year 2 (2013/14) in Appendix E of the same document. The work packages, resource allocations, milestones, deliverables, payment schedules and technical risk assessment for each of the Intervention Areas are all shown in the Task Detail Sheets for each of the work packages (or Intervention Areas).

A summary of the each of the Work packages (Intervention Areas) is provided in the tables below.

Regular progress reviews will be held at specific stage-gates using the progress reports and information shown in the table presented in the following sections where Go, Redirect or Stop decisions will be made.

The project measurables for the WSF are shown as Quarterly stage-gate deliverables for the WSF, PG funded and Other co-funded projects in Table 1 along with their associated value.

Table 1: Stage Gate analysis for the WSF

| Task | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IA1 PLANNING & GOVERNANCE (COORDINATED BY NRE) | Activity | Deliverable | Budget | Activity | Deliverable | Budget | Activity | Deliverable | Budget | Activity | Deliverable | Budget |
| WSF project: Planning and governance | • Assess case area conditions • Develop detailed research plan • Review key literature on pilot areas | Inception report | 825 | • Develop governance framework • Collect and analyse available pilot site information and data • Continue engagement with key stakeholders • Assess available technologies for potential interventions • Develop model for human settlements | Report on case areas, evaluation of technology options and stakeholders | 2150 | • Evaluate objectives • Compare options and scenarios (informed by model) | Report on development trajectories and options | 2236 | • Develop and populating of risk matrix • Finalise models • Assess intervention options and prioritise • Communicating findings (peer review and local stakeholders) | Report on preferred intervention options • Feedback reports of stakeholder engagement; • Feedback from Peer rieviews | 1289 |
| NRE: Aquabase, wetland index and water sustainability | Project scoping and planning | Detailed project plan | 355 | Analysis of available data and literature, data collection and stakeholder consultation | Report on data and literature synthesis, data collection and stakeholder consultation | 532 | Set up conceptual models for the study areas | Report on conceptual models | 532 | Develop models and ecological production functions | Report on the models and ecological production functions | 532 |
| BE: Living lab application | Project scoping and planning | Detailed project plan | 182 | Desk Top Review of Urban Form Literature, Policies and Plans, Analysis of Simulation Results | Synthesis report on urban form literature, policies and plan and the results of the simulations | 273 | Develop a policy brief of the key findings in respect of alternative development scenarios | Policy brief available | 273 | Send out publications for peer review | Peer reviewed publications | 273 |
| BIO: Water sustainability | Review of available literature | Report on literature review | 273 | Assessment of detection methods | Report on detection methods | 409 | Modify detection methods for the WSF | Report on recommended modified detection methods | 409 | Evaluation of detection methods | Report on evaluation of detection methods | 409 |
| NRE: Coaltech sustainability and wetlands | Project scoping and planning | Detailed project plan | 655 | Stakeholder engagement and analysis of the cause-effect relationships in the study areas | Report on stakeholder engagement and cause-effect relationships | 982 | Evaluate and prioritise possible intervention options | Report on evaluation of possible intervention options | 982 | Implementation of selected options (continue into 2013/14) | Progress report on implementation of selected options | 982 |
| BE: IPDM and GITMC | Project scoping and planning | Detailed project plan | 182 | Set up of customized model and validate for study areas. | Customized and validated model. | 273 | Determine the geographic scope | Progress report on geographic scope. | 273 | Evaluation of scenarios | Report on scenario evaluations | 273 |
| IA2 INFRASTRUCTURE INTERVENTION | Activity | Deliverable |  | Activity | Deliverable |  | Activity | Deliverable |  | Activity | Deliverable |  |
| WSF Project: Infrastructure intervention, AD, community programme, electricity manufacturing | Site preparation and high level planning. | Signed MoA with ERWAT. Sign off by ERWAT on site location and nature of community programme. | 465 | Detailed planning | Detailed project plan based on first quarter activity for example site selection. | 1620 | Professional engineering design and procurement of equipment, construction initiated | Final design, equipment delivered on site, first stage of construction completed | 3240 | Community programme initiated, baseline study complete, construction completion, system setup and commissioning | A working anaerobic digester system. Operational progress report. | 975 |
| BE: Baseline study for impact assessment | N.A. | N.A. |  | Baseline study initiated | Progress report of baseline study | 900 | Continuation with baseline study | Baseline study completed |  | Report writing | Final PG report |  |
| BE: Development of conceptual design of enhanced aerobic solution | N.A. | N.A. | 200 | Literature survey | Report on proposed approach for developing aerobic solutions. |  | Conceptual design of solution. | Conceptual design. | 900 | Report writing | Final PG report |  |
| BE: DST project on AD: |  |  |  |  |  |  |  |  |  |  |  |  |
| Degritting of existing AD | N.A. |  | 0 | AD degritted |  | 320 | Complete |  |  |  |  |  |
| Purchase of equipment for upgrade | N.A. |  | 0 | Equipment purchased |  | 7507 |  |  |  |  |  |  |
| Operation of plant and evaluation | N.A. |  | 0 | None |  | 0 | Operation and evaluation ongoing |  | 600 |  |  |  |
| ERWAT maintenance and community programme | N.A. |  | 0 | Community programme initiated |  | 400 | Community programme ongoing |  | 600 |  |  |  |
| IA3 REAL TIME MONITORING AND RESPONSE (COORDINATED BY CAS) |  |  |  |  |  |  |  |  |  |  |  |  |
| WSF Project: Real time monitoring system developemnt and installation | Preparation and equipment manufacturing, site inspections initiated. Integration of wide area alert system into existing platform. | 14 units ready for installation; functional wide area alert system | 2079 | Installations and water footprints complete; develop specifications for integrated open platform | Report on 14 site inspections, 14 installations and water footprint data; Open platform specifications document | 3812 | Development of Version 1 of next generation unit; continued monitoring of installations; Development of core modules of the IT infrastructure | Prototype of next generation unit (upgraded); monthly reports of water quality data; Progress report on module development; | 3082 | Continued monitoring of installations; development of next generation unit; Test and validate core models; Planning for phase-over to open standards and source information system | Final report on 14 installations; next generation manufacturing specification; Tested and validated core modules. Phase-over plan for IT system. | 3102 |
| MSM: Project Management & field sampling (PG MSM) | Groundwork and lit survey | Report on literature survey | 150 | Field data collection | Report on field data | 300 | Organic probe prototype development | Organic probe prototype | 300 | Data collection and specification development for organic measurement | Specification for organic probe and measurement | 150 |
| MER: Project Management (PG MERAKA) | Project management |  | 0 | Project management |  | 80 | Project management |  | 80 |  |  | 0 |
| CAS: Systems, algorithms and rules | Site inspections | Report on site inspections | 1273 | Conceptual design completed | Conceptual design | 1909 | Evaluations | Report on findings from evaluations | 1909 | Market testing and validation | Final market ready design complete | 1909 |

| Work package |  | Intervention Area 1: Planning and Governance |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project leader/manager |  | Dr M Claassen (NRE) and Maria-Joe Coetzee (BE) |  |  |  |
| Start date – End date (duration in months) |  | April 2012 to March 2018 |  |  |  |
| Budget |  |  |  |  |  |
| - Overview of the work package: The Urban Growth Simulation Platform (UrbanSim) models spatially explicit patterns of urban growth over a 20-30 year period. Calibrating and adapting the modelling platform to facilitate the understanding and assessment of the impact of spatial planning and development on wastewater flows inflows to WWTW lies at the core of this intervention area. Existing knowledge and technologies will be integrated into a spatial (GIS) based risk platform to assess, prioritise and mitigate the impact of WWTWs on ecosystem and human health. This framework provides a good platform to facilitate discussions in a multi-party environment and facilitates a shared understanding of development patterns and trends and the forces that shape them, by providing the evidence required to inform rigorous and robust debate amongst the various agencies of the state. The integrated solution will establish a platform to deliver different solutions at different levels, i.e. geographically (Plant, municipality, province, national), scales (small and large plants), governance (municipal, (inter)departmental, provincial, national), and temporal (short, medium and long term). - Description of the activities: - Structure the planned activities into tasks and subtasks and explain them with sufficient detail. The details must also be sufficient to justify the level of effort (man hours) you indicate in Appendix C. - Number the tasks to facilitate reading. - Be specific regarding important information necessary to understand the tasks. - Include tasks related to IP management and Technology Transfer - Outputs/deliverables of this work package: - List the outputs(technical and business) of the tasks produced under this work package. - Examples of business outputs/deliverables: Prior art search results and assessment of IP position and freedom to operate, patent applications filed or granted; Market, industry, competitor analyses; Techno-economic feasibility; Route to market; Business model etc. |  |  |  |  |  |
| - Human resources |  |  |  |  |  |
| Activity | Resources by activity |  | Unit cost (rate per hour) | Units (hrs) | Total HR cost (R) |

| Work package |  | Intervention Area 2: Revitalising Waste Water Treatment Works |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project leader/manager |  | Dr. Chris Rust, Wim Jonker Klunne and Shuntelle Gow |  |  |  |
| Start date – End date (duration in months) |  | April 2012 to March 2018 |  |  |  |
| Budget |  |  |  |  |  |
| - Overview of the work package: The CSIR has developed a new anaerobic digester (AD) technology package that improves the performance of anaerobic digestion considerably compared with existing processes and equipment used at WWT plants. The process is novel and consists of a two-stage, fully automated anaerobic digester that includes control of the critical parameters to optimize the process. In addition, it reduces the retention time of the sewage in the system by almost half, thus increasing the capacity of such a system significantly. The aim of the IA is to up scale the CSIR anaerobic digestion technology to full scale, creation of jobs through sludge beneficiation and the generation of electricity for use at the treatment plant. One of the digesters at the Hartbeestfontein WWTP will be upgraded and the associated generation of electricity for use on site. The stabilised sludge from the digestion process will be used as an input into a community development programme around fertiliser production and community gardens, benefiting the Tembisa settlement adjacent to the plant - Description of the activities: - Structure the planned activities into tasks and subtasks and explain them with sufficient detail. The details must also be sufficient to justify the level of effort (man hours) you indicate in Appendix C. - Number the tasks to facilitate reading. - Be specific regarding important information necessary to understand the tasks. - Include tasks related to IP management and Technology Transfer - Outputs/deliverables of this work package: - List the outputs(technical and business) of the tasks produced under this work package. - Examples of business outputs/deliverables: Prior art search results and assessment of IP position and freedom to operate, patent applications filed or granted; Market, industry, competitor analyses; Techno-economic feasibility; Route to market; Business model etc. |  |  |  |  |  |
| - Human resources |  |  |  |  |  |
| Activity | Resources by activity |  | Unit cost (rate per hour) | Units (hrs) | Total HR cost (R) |

| Work package |  | Intervention Area 3: Real-time water quality monitoring, assessment and response |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project leader/manager |  | Karen van Breukelen (CAS); Peter Bosscha (MSM); Dr Anwar Vahed (MERAKA) |  |  |  |
| Start date – End date (duration in months) |  | April 2012 to March 2018 |  |  |  |
| Budget |  |  |  |  |  |
| - Overview of the work package: The Green Drop certification programme in South Africa forms part of incentive-based regulation implemented by the Department of Water Affairs to identify and develop core competencies required in wastewater management. Compliance with the Green Drop certification programme will ensure that all Water Service Authorities are gradually and sustainably able to improve the level of wastewater management. The Green Drop Certification program is specifically aimed at Waste Water Treatment Works (WWTW) and aims to ensure that WWTW continuously improve their operations so as not to impact negatively on the water bodies into which they discharge their end product. In order for WWTWs to achieve Green Drop status, water quality monitoring is a key requirement. The CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop certification. - Description of the activities: - Structure the planned activities into tasks and subtasks and explain them with sufficient detail. The details must also be sufficient to justify the level of effort (man hours) you indicate in Appendix C. - Number the tasks to facilitate reading. - Be specific regarding important information necessary to understand the tasks. - Include tasks related to IP management and Technology Transfer - Outputs/deliverables of this work package: - List the outputs(technical and business) of the tasks produced under this work package. - Examples of business outputs/deliverables: Prior art search results and assessment of IP position and freedom to operate, patent applications filed or granted; Market, industry, competitor analyses; Techno-economic feasibility; Route to market; Business model etc. |  |  |  |  |  |
| - Human resources |  |  |  |  |  |
| Activity | Resources by activity |  | Unit cost (rate per hour) | Units (hrs) | Total HR cost (R) |

# Stage gate planning

High level strategic points are identified for decision-making during the project lifetime to confirm continued business justification of the project. The table below provides an example of how to present milestones, deliverables and the completion status of a project using the stage gate approach. Refer to Appendix B (do not submit Appendix B with project plan, it only included as a guide).Please ensure that all activities, technical and business, are included.

|  | Milestones |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package 1 | Development | Deliverable(s) | Testing | Deliverable(s) | Trial | - Deliverable(s) | Launch | Gate 4 Deliverable(s) |
|  | Activity 1 |  | Activity 1 |  | Activity 1 |  | Activity 1 |  |
|  | Activity 2 |  | Activity 2 |  | Activity 2 |  | Activity 2 |  |
|  | Activity 3 |  | Activity 3 |  | Activity 3 |  | Activity 3 |  |
| Work package 2 | Development | Deliverable(s) | Testing | Deliverable(s) | Trial | Deliverable(s) | Launch |  |

|_____________ 25% _______________ 50% ______________ 75% ____________ 100%_|

Copy and paste Work package and stage headings as necessary, for the specific project.

## Decision criteria for Go/No go

Define/list the evaluation criteria for each work package to be used in making a go/no go decision. The minimum technical AND business requirements of the project to be met at each specific stage must be considered.

Examples of potential show-stoppers: Limited market size, little interest from potential customers/end-users, highly successful competing products, scale-up issues, raw materials very expensive or difficult to source,

# Project schedule

The project schedule included in the project plan can either be a GANTT or PERT chart. It should include milestones, task dependencies, task duration, work product delivery date, quality milestones (reviews/audits/inspections), management milestones and action items (with deadlines and responsibilities).

## Project critical path

Provide a diagram illustrating the critical path of the project. The critical path describes the sequence of tasks that would enable the project to be completed in the shortest possible time. It is based on the idea that some tasks must be completed before others can begin. A critical path diagram is a useful tool for scheduling the dependencies and controlling a project. In order to identify the critical path the length of time that each task will take must be calculated.

# Project budget

Table 5.1: Summary for WSF

| Income | Budget (R 000) | Comment |
| --- | --- | --- |
| Total income |  |  |
| PG (Flagship) |  |  |
| PG (Core) |  |  |
| External income |  |  |
| Expense type | Budget (R 000) | Comment |
| Total Expenses |  |  |
| i.e. Manpower |  |  |
| Equipment |  |  |
| Running costs (specify) |  |  |
| Running costs (specify) |  |  |
| Net Margin |  |  |

The cashflow and funding split amongst units per Intervention area are shown in the Table 5.2 below.

Table 5.2: WSF cashflow and funding split amongst Units per Intervention Area

| WSF IA | UNIT | Q1 | Q2 | Q3 | Q4 | SUB-TOT | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IA1 | NRE |  |  |  |  |  |  |
|  | BE |  |  |  |  |  |  |
| IA2 | BE |  |  |  |  |  |  |
| IA3 | MSM |  |  |  |  |  |  |
|  | CAS |  |  |  |  |  |  |
|  | MERAKA |  |  |  |  |  |  |
| COORDINATION1 | NRE |  |  |  |  |  |  |
| CONTINGENCY2 | TBC |  |  |  |  |  |  |
| TOT |  |  |  |  |  |  |  |

Note 1: Coordination activities include regular review sessions and included the costs of organizing and facilitating interaction with stakeholders and the reference panel.

Note 2: The contingency pool is centrally controlled and funding releases will be agreed to through consensus during stage-gate review sessions. This implies that Units will share in the pool as the need arises.

The distribution of WSF funding to the various participating Units for each quarter in Year 2 is shown in the Table 5.3 below

Table 5.3: WSF Funding split amongst Units

| UNIT | Q1 | Q2 | Q3 | Q4 | TOTAL |
| --- | --- | --- | --- | --- | --- |
| NRE |  |  |  |  |  |
| BE |  |  |  |  |  |
| MSM |  |  |  |  |  |
| CAS |  |  |  |  |  |
| MERAKA |  |  |  |  |  |
| CONTINGENCY1 |  |  |  |  |  |
| TOTAL |  |  |  |  |  |

Note 1: The contingency pool is centrally controlled and funding releases will be agreed to through consensus during stage-gate review sessions. This implies that Units will share in the pool as the need arises.

The cashflow associated with the expenditure for funds from the WSF, the PG portion and the ‘Other’ co-funding for the 2nd year is summarised in the Table 5.4 below. The detailed breakdown of tasks and associated budget are provided in Appendices A, B, C and D with a summary provided in Appendix E of the full document.

Table 5.4: Cashflow for the WSF and associated co-funding sources (R x 1000)

| Description | 2013/14 |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTALS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 |  | Q2 |  |  |  |  | Q3 |  |  | Q4 |  |  |  |  |  |  |
|  | May | Jun | Jul | Aug |  | Sep |  | Oct | Nov | Dec |  | Jan | Feb | Mar | WSF | PG | OTHER |
| WSF: 2013/14 CASHFLOW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WSF cashflow sub-totals associated with Quarterly stage-gate deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PG: 2013/14 CASHFLOW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| OTHER: 2013/14 CASHFLOW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

The detailed cashflow from the WSF fund for the first year of the integrated project is shown in Appendix E and in Table 5.5 below. Task Detail Sheets are provided in the full document for each of the project tasks (those funded under the WSF, PG and from external sources) for the IAs.

Table 5.5: Cashflow for the WSF and associated co-funding sources (R x 1000)

|  | Task/Activity | 2013/14 |  |  |  |  |  |  |  |  |  |  |  | TOTALS | TOTALS | TOTALS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |  | WSF | PG | OTHER |
| 1 | IA 1 PLANNING & GOVERNANCE (COORDINATED BY NRE) |  |  |  |  |  |  |  |  |  |  |  |  | 6 500 | 4 450 | 4 600 |
| 1.1 | Systems model: Cause-effect relationships | 350 | 350 | 350 | 350 | 350 | 350 | 336 |  |  |  |  |  | 2 436 |  |  |
| 1.2 | Establish integrated simulation platform setup and calibration |  |  | 200 | 300 | 400 | 400 | 400 | 200 | 400 | 386 |  |  | 2 686 |  |  |
| 1.3 | Consolidate and select intervention options |  |  |  |  |  | 100 | 200 | 100 | 200 | 115 |  |  | 715 |  |  |
| 1.4 | Project Management & reporting | 75 | 50 | 75 | 50 | 75 | 50 | 75 | 25 | 50 | 63 | 75 |  | 663 |  |  |
| 1.5 | NRE: Aquabase, wetland index and water sustainability | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 |  |  | 1 950 |  |
| 1.6 | BE: Living lab application | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 |  |  | 1 000 |  |
| 1.7 | BIO: Water sustainability | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 |  |  | 1 500 |  |
| 1.8 | NRE: Coaltech sustainability and wetlands | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 |  |  |  | 3 600 |
| 1.9 | BE: IPDM and urban dynamics laboratory | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 |  |  |  | 1 000 |

| 2 | IA2 INFRASTRUCTURE INTERVENTION (COORDINATED BY BE) |  |  |  |  |  |  |  |  |  |  |  |  | 6 300 | 2 000 | 9 427 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Preparation of site at Olifantsfontein | 90 |  |  |  |  |  |  |  |  |  |  |  | 90 |  |  |
| 2.2 | Detailed planning | 100 | 100 | 100 |  |  |  |  |  |  |  |  |  | 300 |  |  |
| 2.3 | Preparation for and execution of community programme |  |  |  |  | 100 | 100 | 200 | 200 | 200 | 200 |  |  | 1 000 |  |  |
| 2.4 | Procurement of equipment |  | 50 | 30 | 25 | 25 | 50 |  |  |  |  |  |  | 180 |  |  |
| 2.5 | Installation of new equipment (mixing, heat exchange, piping, CHP generator, etc) |  |  |  | 100 | 100 | 50 | 50 | 100 |  |  |  |  | 400 |  |  |
| 2.6 | Design and construction of the second tank and gas storage |  |  |  |  | 690 | 600 | 600 | 690 |  |  |  |  | 2 580 |  |  |
| 2.7 | Installation of gas polishers / scrubbers to remove unwanted content from the biogas |  |  |  |  |  | 200 | 100 | 50 |  |  |  |  | 350 |  |  |
| 2.8 | Monitor and evaluate results (Baseline) |  | 100 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 |  | 700 |  |  |
| 2.9 | BE: Baseline study for impact assessment |  | 300 | 300 | 300 |  |  |  |  |  |  |  |  |  | 900 |  |
| 2.10 | BE: Development of conceptual design of enhanced aerobic solution |  | 200 | 200 | 200 | 200 | 200 | 100 |  |  |  |  |  |  | 1 100 |  |
| 2.11 | BE: DST project on AD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.11.1 | Degritting of existing AD |  |  |  | 320 |  |  |  |  |  |  |  |  |  |  | 320 |
| 2.11.2 | Purchase of equipment for upgrade |  |  |  |  |  |  | 7 507 |  |  |  |  |  |  |  | 7 507 |
| 2.11.3 | Operation of plant and evaluation |  |  |  |  |  |  |  |  | 200 | 200 | 200 | Ongoing |  |  | 600 |
| 2.12 | ERWAT maintenance and community programme |  |  |  |  |  |  | 200 | 200 | 200 | 200 | 200 |  |  |  | 1 000 |
| 2.13 | Project Management & reporting | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 150 |  | 700 |  |  |

| 3 | IA3 REAL TIME MONITORING AND RESPONSE (CAS) |  |  |  |  |  |  |  |  |  |  |  |  | 12 075 | 1 160 | 7 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Pilot Sites Units Yr 1 | 125 | 250 | 200 | 200 | 100 | 100 | 100 | 100 | 60 | 60 | 60 |  | 1 355 |  |  |
| 3.2 | Integrate dissemination (alerting notification) subsystem bases on WAAS (MERAKA) | 20 | 10 | 10 | 10 | 10 | 10 |  |  |  |  |  |  | 70 |  |  |
| 3.3 | Design end-to-end integrated platform (MERAKA) |  |  |  | 30 | 30 | 30 |  |  |  |  |  |  | 90 |  |  |
| 3.4 | Configuration of Pilot Units Yr 1 |  | 25 |  | 25 |  | 25 |  | 25 |  |  |  |  | 100 |  |  |
| 3.5 | Governance - Site Inspections | 100 | 100 | 100 | 100 | 90 |  |  |  |  |  |  |  | 490 |  |  |
| 3.6 | Governance - Laboratory Testing |  | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 42 |  | 442 |  |  |
| 3.7 | Governance - WWTW Assessments |  | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 |  | 3 540 |  |  |
| 3.8 | Modelling & Algorithms |  | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  |  |  | 600 |  |  |
| 3.9 | Hardware & Software |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 800 |  |  |
| 3.10 | Implement near real time monitoring and simulation environment core infrastructure (MERAKA) |  |  |  |  |  |  | 100 | 100 | 90 |  |  |  | 290 |  |  |
| 3.11 | Implement integrated platform (MERAKA) |  |  |  |  |  |  |  |  | 70 | 150 | 150 |  | 370 |  |  |
| 3.12 | Next Generation | 150 | 250 | 250 | 250 | 250 | 300 | 300 | 400 | 450 | 400 | 228 |  | 3 228 |  |  |
| 3.13 | Project Management (WSF) | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 150 |  | 700 |  |  |
| 3.14 | MSM: Project Management & field sampling (PG MSM) | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 |  |  | 1 000 |  |
| 3.15 | MER: Project Management (PG MERAKA) |  |  | 20 | 30 | 30 | 30 | 30 | 20 |  |  |  |  |  | 160 |  |
| 3.16 | CAS: Systems, algorithms and rules | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 |  |  |  | 7 000 |

| 4 | WSF PROGRAMME COORDINATION BY NRE |  |  |  |  |  |  |  |  |  |  |  |  | 5125 | 0 | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Planning, Quality Control and Reporting | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 240 |  | 2240 | 0 | 0 |
| 4.2 | Risk management (Contingency pool) | 700 |  |  | 700 |  |  | 700 |  |  | 785 |  |  | 2885 | 0 | 0 |
|  | FUNDING TOTALS |  |  |  |  |  |  |  |  |  |  |  |  | 30 000 | 7 610 | 21 027 |

# Assumptions and Constraints

List the project assumptions and constraints in the table below. An assumption is a circumstance or event outside the project that can affect its success and that the authors of this plan believe will happen. Constraints are restrictions or boundaries placed upon the project that limit the choices of the project team. The assumptions and constraints for this project are listed in the table below.

| Assumptions | Constraints |
| --- | --- |

Stakeholders/partners/collaborators

This section provides information on project stakeholders, or people with an interest in or influence over project work and results. The table below lists stakeholders/partners/collaborators and indicates how they will be impacted and engaged by the project.

| Stakeholder/Partner/Collaborator | Impact | Engagement |
| --- | --- | --- |

# Risks

This section provides a description, the estimated probabilities and impacts of risks (high, medium, low) identified while writing the project plan. This section also includes recommended responses to risks.

The integrated solution is aimed at pre-competitive development and implementation of CSIR technology packages at TRL 5. Thus the solutions have been proven at laboratory scale. The risk therefore does exist in the scaling up the lab scale technologies to ‘real-life’ pilot scale. It is for this reason that both Urban and Peri-Urban settings were chosen for the pilots and where active collaboration with the user community is key.

A key component to mitigate this risk is the decision to implement scientifically designed experiments to ensure that the results are statistically defendable, whether positive or negative. This will directly inform the stage-gate project progress reviews.

| Risk description | Risk likelihood H/M/L | Risk Impact H/M/L | Risk mitigation actions |
| --- | --- | --- | --- |

# Route to impact

Impact encompasses a wide range of benefits- including knowledge, skills and trained people, societal and economic benefits- and these can be realized over a wide variety of timescales. Consider what is reasonable and /or expected for this project.

- Who will benefit from the outcomes of this project

- How will they benefit (e.g. economic impact, policy, quality of life, etc.)

- What will be done to ensure that they have the opportunity to benefit from the outcomes of this project?

Specifically address how the project will be managed to engage users and beneficiaries and increase the likelihood of impact including (where appropriate):

- Methods for communication and engagement

- Collaboration and exploitation in the most effective and appropriate manner

- Track record in this area – reference to prior activities that had significant impact or resulted in commercial exploitation

- Milestones and measure of success of impact activities – include ways to measure the success of impact activities, e.g commercialization activities/plans

- Resources required for such activities

- Make reference to IP, diffusion of knowledge, market and commercialization aspects.

As reflected in the Logic Model adapted from RAND (www.rand.org) in the figure below, the anticipated output of the WSF is therefore to move beyond simply providing evidence in support of decision-making to a suite of practical and sustainable tools and technologies to assist practitioners and decision makers in the water sector.

Here the objective statement and underpinning strategic programme outcomes are used as the starting points. These reflect the WSF Focus Areas as discussed above.

To realise the desired impact some change has to be induced in the way the targeted stakeholder groupings address their mandated responsibilities. For the WSF these are defined as Intermediate Outcomes reflected in the second column from the right.

The Outputs of the Development and Implementation (D & I) activities carried out under the WSF are depicted in the central two columns demarcated by the dotted line in the Logic Model diagramme above. Technologies (or ‘tools’) developed by the CSIR that are at a Technology Readiness Level (TRL) above 5 form the basis for the ‘quick win’ D&I activities over the first 12 to 18 month period. As indicated, these activities can only be achieved through effective and efficient collaboration across the capabilities in CSIR and within its external network.

Although the final end users (or target population) are the ‘People of South Africa’, the various levels of government are mandated to act on behalf of their constituents and to ensure a healthy and safe environment and are therefore seen as the Intermediate Customers.

To this end the South African Government has agreed on 12 outcomes as a key focus of service delivery work up to 2014. Each outcome has a limited number of measureable outputs with targets. For example, the Delivery Agreement for Outcome 10: Environmental Assets and Natural Resources that are valued protected and continually enhanced (www.environment.gov.za) has as Output 1 ‘Enhanced quality and quantity of water resources’ with sub-outputs of (1) water demand management, (2) water resource protection, and (3) regulation of water quality.

Aligned to assist the above, the expected results of the WSF are therefore to (1) facilitate changes in knowledge, attitude and behaviour of planners, water users (and effluent dischargers), and authorities in terms of the implementation of the required practices, procedures and policies that influence water quality, and (2) the adoption of relevant technologies by owners, funders, managers and operators of waste water treatment works in municipalities.

# Project governance

The project plan should include a description of the organization that defines the persons responsible for the all various functions. Include a narrative of key project member responsibilities; this would include the person’s name, project position and key responsibilities. This information could be presented graphically.

As shown in the figure below, the size, multi- and interdisciplinary nature of the integrated solution warrants a dedicated project coordinating function that will oversee the three technical project management functions.

The Project Coordination Office (PCO) is established within the CSIR’s Natural Resources and the Environment (NRE).

Of importance is the establishment of a independent Oversight Board with membership taken from the stakeholder reference group so-as to ensure market relevance and maximise the opportunities for user-driven uptake.

# REFERENCES

2030 Water Resources Group, 2009. Charting Our Water Future: Economic frameworks to inform decision-making.

Ashton PJ; Hardwick D; Breen CM 2008. Changes in water availability and demand within South Africa's shared river basins as determinants of regional social and economical resilience. Exploring Sustainability Science: A Southern African Perspective, Pages: 279-310.

CSIR, 2010. A CSIR perspective on water in South Africa – 2010. Available at www.csir.co.za.

Department of Environmental Affairs (DEAT), 2006. State of Environment Outlook Report for 2006.

Department of Water Affairs (DWA), 2011. Water for Growth and Development in South Africa. Version 6.

Falkenmark, M., 1997: Society’s interaction with the water cycle: A conceptual framework for a more holistic approach, Hydrological Sciences Journal, 42, 451–66.

Falkenmark, M. and Folke, C. 2003: Theme issue: Freshwater and welfare fragility: Syndromes, vulnerabilities and challenges, Royal Society’s Philosophical Transactions B Biology, 358, p. 1440. (introduction to special issue on this topic)

Millennium Ecosystem Assessment, 2005. Ecosystems and Human Well-being: Synthesis. Island Press, Washington, DC.

APPENDIX A - CV

Attach a short CV of each core project team members.

APPENDIX B: INTERVENTION AREA 1

# Governance and Planning Component of Water Sustainability Flagship

Coordination: Dr Marius Claassen (NRE)

Brief

To achieve water quantity, quality & efficiency at basin level, specifically related to wastewater treatment works (WWTWs).

### 1. Activity/technology description

The Urban Growth Simulation Platform (UrbanSim) models spatially explicit patterns of urban growth over a 20-30 year period. The platform is ready for water specific applications in Nelson Mandela Bay, eThekwini, the City of Johannesburg and the Greater Gauteng City Region. Application of the simulation platform in the City of Cape Town and other secondary cities of South Africa would require concerted processes around data collation and preparation of approximately 6 months per study area. The Geo-Spatial Analysis Platform provides an analysis of spatial and temporal development trends at a regional scale to inform rigorous and robust debate amongst the various agencies of the state. The StepSA (Spatial and Temporal Evidence for Planning in South Africa) portal facilitates access to spatial and temporal evidence (incl. water related planning information) to support integrated and inter-governmental planning in South Africa.

Existing knowledge and technologies will be integrated into a spatial (GIS) based risk platform to assess, prioritise and mitigate the impact of WWTWs on ecosystem and human health. Decision support systems include the Assessment of Considerations for Water Use Allocations (ACWUA) Decision Support System (DSS), which utilizes a Bayesian engine to evaluate decisions based on multiple criteria, particularly where information related to the decision is incomplete (uncertain). The ECO2 (Ecology to Economy) model provides a robust framework for the analysis of development opportunities, taking the availability of resources into account. This framework provides a good platform to facilitate discussions in a multi-party environment. The structured decision support approaches are supported by the Water Sector Institutional Landscape (WSIL) Scenario analysis, which maps key drivers of change and facilitates the evaluation options and decisions under different future conditions. The National Freshwater Ecosystem Priority Areas (NFEPA) framework uses systematic conservation planning to provide strategic spatial priorities for conserving South Africa’s freshwater biodiversity, within the context of equitable social and economic development, whereas Solar Water Disinfection (SODIS), the Phosphate Sensitivity Index, and SWAT hydrological model can also contribute to achieving a balance between development (and consequent WWTWs) and protection (of human health and the environment).

### 2. Outputs/contribution to project

The main application of the platform to the Water Flagship Initiative, relates to its ability to model future household and enterprise water demand in a spatially explicit manner for all metropolitan regions of South Africa. UrbanSim has the ability to model future household and enterprise water demand in a spatially explicit manner for all metropolitan regions of South Africa. This will enable cities to anticipate the impact of residential and non-residential growth on water service delivery and inform investment decisions pertaining to reticulation and bulk infrastructure. Spatially explicit water demand modelling will also inform investment decisions pertaining to reticulation as well as bulk infrastructure with a view to ensure water security for the metropolitan growth engines of the country. By combining the evidence generated for all metropolitan regions of the country, the platform may even contribute to water demand planning at a national scale. The Geo-Spatial Analysis platform facilitates a shared understanding of development patterns and trends and the forces that shape them, by providing the evidence required to inform rigorous and robust debate amongst the various agencies of the state.

The ACWUA DDS, ECO2 model and Scenario approach mentioned earlier provides a robust framework for evaluating options in the context of current state and future trends for WWTWs. Catchment approaches, such as NFEPA, SWAT and SODIS will support spatial prioritisation of downstream areas that guides targeted upstream (e.g. engineering, governance and urban planning interventions at WWTWs), downstream (e.g. human health advisories and point of use treatment options) and in-stream responses (e.g. constructed wetlands) that reduce risks of WWTWs to ecosystem and human health. These technologies, in combination with spatial simulation, will facilitate engagement of different tiers and departments of government together with other stakeholders to promote cooperative governance.

The integrated solution will establish a platform to deliver different solutions at different levels, i.e. geographically (Plant, municipality, province, national), scales (small and large plants), governance (municipal, (inter)departmental, provincial, national), and temporal (short, medium and long term).

### 3. Tasks, Deliverables, TRL and Budget

| Activities & Deliverables | TRL CurrentTarget | Mnths | Budget |
| --- | --- | --- | --- |
| 2012/13 |  |  | 6.50M |
| Project management |  | 1-12 | 0.600M |
| D1: Established relationship between governance, human settlement, WWTWs and downstream users |  | 1-8 | 2.436M |
| T1.1: Policy context, institutional arrangements and decision processes defined for WWTWs - nationally and for case areas in particular |  | 1-4 | 677k |
| T1.2: Relationships between urban development and wastewater volumes and quality quantified - nationally and for case areas in particular |  | 1-6 | 536k |
| T1.3: Water infrastructure, capacity and consumption data acquired and incorporate into relational database |  | 1-4 | 514k |
| T1.4: Catchment (downstream users and environment) objectives and management options defined (NFEPA, and Human health) | NFEPA 99 | 1-8 | 709k |
| D2: Implement integrated platform for simulations, options and decisions |  | 3-10 | 2.686M |
| T2.1: Formalise and implement Living Lab process (ongoing) |  | 3-12 | 387k |
| T2.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA updated for case areas | UrbanSim 67 GS Platform 78 StepSA 78 | 3-9 | 1200k |
| T2.3: Technologies (ACWUA DSS, ECO2 model, WSIL Scenarios framework) and data incorporated in an integrated risk and options matrix | ACWUA 78 ECO2 67 WSIL Scenarios 77 | 4-10 | 1099k |
| D3: Consolidate and select intervention options |  | 6-12 | 0.715M |
| T3.1: UrbanSim, Geo-Spatial Analysis Platform and StepSA iterations and projections | UrbanSim 78 GS Platform 88 StepSA 78 | 6-11 | 315k |
| T3.2: Prioritize options for WWTWs in the case areas, based on the simulations (T2.2), real time monitoring (T3.1), conservation framework (T1.4), integrated risk-based matrix (T2.3), and key stakeholder engagement (T2.1) | ACWUA 78 ECO2 78 WSIL Scenarios 78 | 9-12 | 400k |
| 2013/14 |  |  | 5.6M |
| D4: Implementation of interventions from D3, monitor results and update models | All ..9 | 13-20 | 4.4M |
| D5: Assessment of impact of key interventions and roll out strategy to upscale solutions |  | 21-24 | 1.2M |
| 2014/15 |  |  | 4.5M |
| D6: Multiple roll-out of solution, monitoring, evaluation (incl. business model for replication) |  | 25-36 | 4.5M |

### 4. Team members

NRE: M Claassen, J Dabrowski, R Meissner, K Nortje, N Funke, C Ntombela, M du Preez, W Le Roux, P Oberholster, P MacMillan, L Hill, C Petersen, J Nel, D Le Maitre

BE: M Coetzee, L. Waldeck, A Le Roux, K. Wall, J Maritz, Y. Shapurjee, T, Leuta

MDS: N Siyakatshana

Biosciences: E Barros

### 5. Partners & co-funding (2012/13)

NRE: CoalTech (Upper Olifants)	 				R2.0M

NRE: Coaltech (Wetland Project)  					R1.5M

BE: IPDM and stepSA co-funding from DST   			R1.0M

BE: Flagship co-funding from core PG (Spatial Platforms)		R1.0M

NRE: Flagship co-funding from core PG (Aquabase Project)  	R1.2M

NRE: Flagship co-funding from core PG (Water Governance)  	R0.8M

Biosciences: Funding probes development				R1.5M

WSF Tasks

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Cause-Effect relationships |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: PM |  |  |  |  |  |
| Description: Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  | 31/5/2012: R75k; 30/6/2012: R50k; 31/7/2012: R75k; 31/8/2012: R50k; 30/9/2012: R75k; 31/10/2012: R50k; 30/11/2012: R75k; 31/12/2012: R25k; 31/1/2013: R50k; 28/2/2013: R63k; 31/3/2013: R75k |  |  |  |  |  |  |  |
|  |  | 28/02/2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R663k |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - None |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 120 |  | R 156 600 |  | R 35 000 |  |  |  | Travel and accommodation for meeting |  | - |
| R Meissner |  |  |  | 795 |  | 39 |  | R 31 005 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 39 |  | R 27 000 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 39 |  | R 31 005 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 39 |  | R 36 270 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 39 |  | R 26 325 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 39 |  | R 37 440 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 116 |  | R 127 020 |  | R 30 000 |  |  |  | Travel and accommodation for meeting |  | - |
| L. Waldeck |  |  |  | 1620 |  | 46 |  | R 74 520 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 40 |  | R 50 400 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 557 |  | R 597 585 |  |  | R 65 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
| Assumptions, Risk Factors & Contingencies: - Good overall project coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Cause-Effect relationships |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T1 |  |  |  |  |  |
| Description: Established relationship between governance, human settlement, WWTWs and downstream users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee, Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  | 31/5/2012: R0.35M; 30/6/2012: R0.35M; 31/7/2012:R0.35M; 31/8/2012: R0.35M; 30/9/2012: R0.35M ; 31/10/2012: R0.35M; 30/11/2012: R0.336M |  |  |  |  |  |  |  |
|  |  | 30/11/2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.436M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I1.1: Policy context, institutional arrangements and decision processes I1.2: Relationships between urban development and wastewater I1.3: Water infrastructure, capacity and consumption data I1.4: Catchment objectives and management options |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 175 |  | R 228 375 |  | R 140 000 |  |  |  | - Field work - Sample analysis - Software |  | - |
| R Meissner |  |  |  | 795 |  | 135 |  | R 107 325 |  |  |  |  |  |  |  |  |
| K Nortje |  |  |  | 675 |  | 54 |  | R 36 450 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 101 |  | R 68 175 |  |  |  |  |  |  |  |  |
| C Ntombela |  |  |  | 300 |  | 96 |  | R 28 800 |  |  |  |  |  |  |  |  |
| S Nienaber |  |  |  | 300 |  | 72 |  | R 21 600 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 101 |  | R 80 295 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 93 |  | R 86 490 |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  | 68 |  | R 42 840 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 96 |  | R 132 480 |  |  |  |  |  |  |  |  |
| P MacMillan |  |  |  | 540 |  | 68 |  | R 36 720 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 96 |  | R 51 840 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 135 |  | R 129 600 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 135 |  | R 113 400 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 153 |  | R 167 535 |  | R 530 000 |  |  |  | - Data acquisition - Field work - Sub-consulting |  | - |
| L. Waldeck |  |  |  | 1620 |  | 102 |  | R 165 240 |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  | 119 |  | R 67 830 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 48 |  | R 60 480 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 52 |  | R 39 780 |  |  |  |  |  |  |  |  |
| Y Shapurjee |  |  |  | 360 |  | 52 |  | R 18 720 |  |  |  |  |  |  |  |  |
| N Siyakatshana |  |  |  | 930 |  | 39 |  | R 36 270 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 2 058 |  | R 1 766 145 |  |  | R 670 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Good collaboration with stakeholders - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated Platform |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T2 |  |  |  |  |  |
| Description: Implement integrated platform for simulations, options and decisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen, Maria Coetzee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/7/2012 |  |  |  | Payment details: |  |  | 31/7/2012: R0.2M; 31/8/2012: R0.3M; 30/9/2012: R0.4M; 31/10/2012: R0.4M; 30/11/2012: R0.4M ; 31/12/2012: R0.2M; 31/1/2012: R0.4M; 28/2/2012: R0.386M |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.686M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I2.1: Formalise and implement Living Lab process (ongoing) I2.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA updated I2.3: Technologies and data incorporated in an integrated risk and options matrix |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - D1 |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 176 |  | R 229 680 |  | R 100 000 |  |  |  | - Field work - Sample analysis |  | - |
| R Meissner |  |  |  | 795 |  | 68 |  | R 54 060 |  |  |  |  |  |  |  |  |
| K Nortje |  |  |  | 675 |  | 116 |  | R 78 300 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| C Ntombela |  |  |  | 300 |  | 25 |  | R 7 500 |  |  |  |  |  |  |  |  |
| S Nienaber |  |  |  | 300 |  | 25 |  | R 7 500 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 170 |  | R 135 150 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 68 |  | R 93 840 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| C Petersen |  |  |  | 540 |  | 123 |  | R 66 420 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 68 |  | R 36 720 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 68 |  | R 65 280 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 68 |  | R 57 120 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 96 |  | R 105 120 |  | R 205 000 |  |  |  | - Data acquisition - Field work |  | - |
| L. Waldeck |  |  |  | 1620 |  | 297 |  | R 481 140 |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  | 297 |  | R 169 290 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 280 |  | R 352 800 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 315 |  | R 240 975 |  |  |  |  |  |  |  |  |
| N Siyakatshana |  |  |  | 930 |  | 116 |  | R 107 880 |  | R 0 |  |  |  |  |  | - |
| Totals: |  |  |  |  | 2 512 |  | R 2 380 575 |  |  | R 305 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T3 |  | Intervention options |  |
| Assumptions, Risk Factors & Contingencies: - Application of Technology demonstrators to particular context - Good collaboration with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Intervention options |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T3 |  |  |  |  |  |
| Description: Consolidate and select intervention options |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee, Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/10/2012 |  |  |  | Payment details: |  |  | 31/10/2012: R0.1M; 30/11/2012: R0.2M; 31/12/2012: R0.1M; 31/1/2012: R0.2M; 28/2/2012: R0.185M |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R0.785M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I3.1: Options, gap analysis and response framework for real-time WWTW monitoring system I3.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA iterations and projections I3.3: Prioritize options for WWTWs in the case areas, based on the simulations (I2.2), real time monitoring (I3.1), conservation framework (I1.4), integrated risk-based matrix (I2.3), and key stakeholder engagement (I2.1) |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - T1, T2 |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 100 |  | R 130 500 |  | R 45 000 |  |  |  | - Field work - Sample analysis |  | - |
| K Nortje |  |  |  | 675 |  | 48 |  | R 32 400 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 49 |  | R 38 955 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 34 |  | R 31 620 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 34 |  | R 46 920 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 51 |  | R 27 540 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 51 |  | R 48 960 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 34 |  | R 28 560 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 18 |  | R 19 710 |  | R 35 000 |  |  |  | - Field work |  | - |
| L. Waldeck |  |  |  | 1620 |  | 68 |  | R 110 160 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 60 |  | R 75 600 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 102 |  | R 78 030 |  |  |  |  |  |  |  |  |
| Y Shapurjee |  |  |  | 360 |  | 102 |  | R 36 720 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 751 |  | R 705 675 |  |  | R 80 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | None |  |
| Assumptions, Risk Factors & Contingencies: - Continued commitment from stakeholders - Acceptability of intervention options |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

External Co-Funding Task Sheets

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Coaltech – Sustainability |  |  |  |  |  |  |  |  |  | Task Ref. No.: CS |  |  |  |  |  |
| Description: Sustainable development related to water resources in the Olifants River Basin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.1M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Application of the SWAT model to WWTW context - Application of the Phosphate Sensitivity index model to WWTW context |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| K Nortje |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  |  |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  |  |  |  |  |  |  |  |  |  |  |
| A de Klerk |  |  |  | 420 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 1 750 000 |  |  | R 350 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Build on previous success in upper Olifants catchment - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Coaltech - Wetlands |  |  |  |  |  |  |  |  |  | Task Ref. No.: CW |  |  |  |  |  |
| Description: Sustainable development related to wetlands in the Olifants River Basin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.5M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Apply Wetland Index to assess function status of Wetlands - Define the role and potential of Wetlands in catchment process in context of WWTWs |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| K Nortje |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  |  |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  |  |  |  |  |  |  |  |  |  |  |
| A de Klerk |  |  |  | 420 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 1 250 000 |  |  | R 250 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Applicability of Wetland Index to WWTW context - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Core PG Co-Funding

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: BE Core PG: Living Lab |  |  |  |  |  |  |  |  |  | Task Ref. Number: LL PG |  |  |  |  |  |
| Description: Further Development of Living Lab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.0M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Development, refinement and application of Living Lab platform |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - Previous Living Lab funding |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Coetzee |  |  |  | 1095 |  |  |  |  |  |  |  |  |  |  | - |
| L. Waldeck |  |  |  | 1620 |  |  |  |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  |  |  |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  |  |  |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | 800 000 |  |  | 200 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T3 |  | Intervention options |  |
| Assumptions, Risk Factors & Contingencies: - Build on earlier success - Continued collaboration with government entities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: NRE Core PG: Aquabase |  |  |  |  |  |  |  |  | Task Ref. No.: AqB |  |  |  |  |  |
| Description: Understanding and managing freshwater ecosystem services in South Africa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.2M |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Apply Wetland Index to assess function status of Wetlands - Define the role and potential of Wetlands in catchment process in context of WWTWs |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| S Nienaber |  |  |  | 300 | 145 |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 | 417 |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 | 103 |  |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 | 152 |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 | 161 |  |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 | 190 |  |  |  |  |  |  |  |  |  |
| D le Maitre |  |  |  | 840 | 92 |  |  |  |  |  |  |  |  |  |
| A Maherry |  |  |  | 540 | 176 |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 960 000 |  | R 240 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Continued good relationship with project partners - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: NRE Core PG |  |  |  |  |  |  |  |  |  |  |  |  | Task Ref. No.: WSPG |  |  |  |  |  |
| Description: Water Sustainability – NRE Core PG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R750k |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Governance and Policy - Human health, ecosystems and downstream users - Ecotoxicology - Catchment approach |  |  |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  |  | Unit cost | Units |  |  | HR Cost |  |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  | 1305 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  | - |
| R Meissner |  |  | 795 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| K Nortje |  |  | 675 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  | 675 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| C Ntombela |  |  | 300 |  |  |  | 50 |  |  |  |  |  |  |  |  |  |  |  |
| S Nienaber |  |  | 300 |  |  |  | 75 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  | 795 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| M du Preez |  |  | 930 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  | 630 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  | 1380 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| P MacMillan |  |  | 540 |  |  |  | 80 |  |  |  |  |  |  |  |  |  |  |  |
| L Hill |  |  | 675 |  |  |  | 70 |  |  |  |  |  |  |  |  |  |  |  |
| M Thwala |  |  | 540 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| J Nel |  |  | 960 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  | 840 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  | 700k |  |  |  | 50k |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Good collaboration with stakeholders - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Bioscience - Core PG |  |  |  |  |  |  |  |  |  |  | Task Ref. No.: BSPG |  |  |  |  |  |
| Description: Water Sustainability – Biosciences Core PG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Eugenia Barros |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  |  | 1/4/2012 | Payment details: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R1.5M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Microbiological detection techniques |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  | Unit cost |  | Units |  |  | HR Cost |  |  | Running |  |  |  | Running costs |  | Capital |
| E Barros |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | 1 200k |  |  |  | 300k |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Collaboration with WSF project team members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

APPENDIX C: INTERVENTION AREA 2

REVITALISING WASTEWATER TREATMENT FACILITIES

CLEANER ENVIRONMENT AND RENEWABLE ENERGY GENERATION AT MUNICIPAL WASTEWATER TREATMENT FACILITIES

Contents

1.	Introduction	35

1.1.	Background	35

1.2.	Benefits of the project	36

2.	Goal	37

3.	The solution	37

3.1.	Brief description	37

3.2.	Scalability of the technology package	39

4.	Project approach and deliverables	41

4.1.	Detailed project activities	42

5.	Feasibility	43

6.	Risks	43

7.	Capacity building, job creation and HCD	44

8.	Scientific knowledge generation and dissemination	44

9.	Governance	45

10.	Budget estimate	45

11.	Appendix I: CSIR anaerobic digester	48

# Introduction

## Background

Gauteng province foresees an increase in the number of inhabitants due to natural population growth and migration into the area. As a consequence the amount of domestic waste water that needs treatment is increasing significantly. According to the Tshwane municipality and ERWAT in Johannesburg they already have overflows during peak periods and they need to address this urgently. Most of their waste water treatment (WWT) plants are operating at or over design capacity (most of these plants were designed before 1980). In addition, there are increasing electricity costs associated with the WWT plants and this is now the major running cost in many of these plants. Both ERWAT and Tshwane recognize this as an important area of focus.

Several domestic WWT plants exist in the Gauteng area in close proximity of urban settlements (such as the Klipgat plant in Mabopane) that are not operating in the most effective and efficient way. An increase in inflows to the treatment plants is posing a health threat to these communities. Whereas many municipal WWT plants have anaerobic digesters, many of them are in disuse, are often used as “storage” rather than digesters, do not produce optimum levels of biogas and lack the required capacity. This causes the sludge not to be de-activated which leads to associated health risks especially during peak periods when overflow can land in open veld. This also has a significant influence on contamination of water resources.

In addition, typical WWT plants do not have a power backup and hence they are not able to process the inflowing sewage during periods of power failure resulting into discharge of untreated effluent in the environment. They might also be selling active sludge to local farmers for use as fertiliser (which is illegal).  At the same time most WWT plants do not make (full) use of the biogas generation capacity of organic waste sludge and its potential electricity generation capacity. The treatment of sludge through an anaerobic process de-activates it and therefore makes it suitable and safe for direct application on fields as fertiliser. Current legislation prohibits the use of active sludge as fertiliser, but this is not always effectively enforced.

The CSIR has developed a new anaerobic digester (AD) technology package that improves the performance of anaerobic digestion considerably compared with existing processes and equipment used at WWT plants.  The process is novel and consists of a two-stage, fully automated anaerobic digester that includes control of the critical parameters to optimize the process.  The CSIR has developed and tested a pilot version of the new AD and the results indicated that the system provides more gas of a higher quality than existing systems.  In addition, it reduces the retention time of the sewage in the system by almost half, thus increasing the capacity of such a system significantly.

The CSIR, in collaboration with ERWAT (the WWT service provider to Ekurhuleni municipality), is proposing to pilot this innovative technology package at full scale at ERWAT’s Hartbeestfontein plant. In this regard the CSIR has been in discussions with the Department of Science and Technology (DST) regarding the potential funding of such a project.  At the request of the DST, the CSIR conducted a first order feasibility assessment of the project.  The report on this work is attached to this project proposal. A full description of the technology package is given in the feasibility report.

The proposed project will aim to:

- Implement the two-stage, automated AD technology package in one full scale biogas digester;

- Assist with the operation of the plant for at least six months;

- Verify and quantify the benefits obtained from such implementation, and

- Ensure that there are direct benefits to the surrounding community from the project (mainly from the manufacturing of fertiliser).

## Benefits of the project

This project will provide benefit in terms of:

- Cost savings in terms of electricity usage at municipal WWT plants which could translate to savings (or at least slower increases) in the cost of sewage service delivery;

- Increase in municipal capacity in terms of waste water treatment (due to the increased efficiency of the proposed solution) thus preventing or reducing the cost of required capacity increases;

- Lowering of the health risks associated with active sludge, especially to poorer communities that are located close to these plants as well as in reducing water resource contamination;

- General improvement in service delivery owing to the fact that increased capacity in waste water treatment allows for acceleration of housing development (waste water treatment capacity is often a major bottleneck);

- Job creation through a community programme to modify the de-activated sludge into fertiliser (the community programme will be driven by ERWAT) , and

- Contribution to meeting of emission reduction targets at a national level owing to the use of alternate energy sources (alternative to coal-based electricity generation).

# Goal

The overall goal of the project is to implement an innovative solution for waste water (sewage) treatment that mitigates health risks, increases municipal WWT plant capacity, provides usable de-activated sludge as fertiliser and provides renewable energy from a waste stream thus reducing emissions and plant operational costs. The project will demonstrate the ability of the technology and that the solution can be used on a country-wide scale. At the same time the project with have a number of direct and indirect benefits as discussed above.

# The solution

## Brief description

The proposal addresses the required steps to demonstrate and implement a technology package that provides a novel approach to waste water treatment through a two-stage, fully automated anaerobic digester.  The proposal builds on internally funded research at the CSIR towards the modelling and simulation of such a package. A key characteristic of the technology developed by the CSIR is the two-stage nature of the digester and automated control of optimal gas-producing conditions, allowing continuous operation compared with the current batch process at WWT plants. This novel approach is currently being patented by the CSIR.

A pilot scale model of the two-phase digester has been built at the Innovation Site of the CSIR Built Environment. This scale model has been thoroughly tested and yields good results. The proposed project will demonstrate the scalability of the technology and its application at municipal WWT plants.  The CSIR system produces slightly better amounts of biogas than the current standard rate biogas systems, but at a much shorter retention time (and hence reducing the required system size for the same output or alternatively being able to handle larger amounts of waste water flow).

The pilot system is fully automated:

- it maintains constant pH and temperature of the sludge which are critical parameters for optimal digestion;

- it is a continuous process with controlled feed of sludge into the system ensuring optimal digestion and preventing the process from stopping, and

- the stirring of the sludge is optimal based on the performance of the system.

A schematic diagramme of the pilot version of the plant is shown in Figure 1 below whereas Figure 2 shows a photograph of the system.

Figure 1:  Schematic diagramme of the system

Figure 2:  The CSIR anaerobic digester

The system has been operated on pure municipal WWT sludge producing biogas with a methane content of 60 to 67%. Currently the digester is being tested using co-digestion with WWT sludge and cow manure, which seem to result in higher biogas yields.

Based on the feasibility study, the goal of the project is to design, develop and implement a technology package at ERWAT’s Hartbeestfontein municipal waste water treatment plant that includes a two-stage anaerobic digester (adapted from existing one-stage AD as can be found at most WWT plants), two 65kW electricity generation units and associated hardware. The installed hardware will be operated for at least 6 months under supervision of the CSIR, in which period the hardware will be thoroughly tested and staff at the WWT plant be trained to operate the installation.

Details on the CSIR AD technology can be found in Appendix I to this proposal and in the attached report on the feasibility study.

## Scalability of the technology package

In up scaling of the technology package, the following critical parameters need to be considered:

•	Heating and stirring of a larger volume of sludge;

•	Control of the pH of a larger volume of sludge;

•	Electricity generation, and

•	Withdrawal of digested sludge from the system.

Heating and stirring

Heating and stirring of 2 million litres of sludge (the size of a typical AD at a municipal WWT plant) has been implemented in a number of cases (see feasibility study report).  The equipment such as stirrers and heat exchangers are commercially available.  There is therefore minimal technical risk associated with the heating and stirring of the sludge in the proposed project.

Traditional methods of heating the digesters at MWWTP required that the bio gas is used in an inefficient gas boiler system for the heating of water. Sludge would be extracted from the digester by means of electrical pumps and then circulated through the boiler system. This has proven to be a very inefficient method of operation. Modern heat exchanger systems have become available that increase the efficiency of heat transfer between the heated medium and the digestate. This is technology that is available off the shelf and has been proven on various sites to be efficient if connected to a Combined Heat and Power (CHP) system. When electricity is generated with an internal combustion engine or gas turbine, waste heat is also generated. This waste heat can be harvested through a CHP unit. This is technology that exists and can be procured off-the-shelf. Suppliers that have a proven track record in this field are Caterpillar, Jenbacher, Capstone, Turbec, GE, etc.

Control of the pH

As described in literature (see feasibility study report), once an AD has been brought to the right pH level, the pH can be controlled with the load of sludge into the system.  In the case of the CSIR system this is a continuous process, therefore the sludge load can be controlled by the automated system in response to the measurement of pH through a number of sensors in the AD. The continuous nature of the process requires a second, smaller tank where the supernatant is separated from the solids, thus making it unnecessary to stop the process – and thereby rendering the pH level unsuitable.  This principle has been implemented in practice so there is minimal risk to implementing it in the proposed project.

ERWAT has an existing operating system for the aerobic part of the plant. It is therefore possible to link the automation system of the anaerobic digester to existing infrastructure. This automation system will include sensors such as thermocouples and pH sensors. Valves that operate the digester will be replaced with electronically operated valves that will allow the PLC system to operate the valves on parameters that will be set by the operator. This will facilitate the implementation of the operating system.

Electricity generation

During the CSIR pilot project, no electricity was generated.  However, this is being done regularly by companies such as Ener-G, so the risk is once again minimal.  The equipment is readily available from companies such as Caterpillar, Jenbacher, Capstone, Turbec, GE, etc.  The CSIR has opted for two 65 kW combined heat and power (CHP) engines to be used for the project instead of one, larger CHP engine.  This decision was based on the amount of gas that is likely to be available from one AD as well as to allow flexibility should ERWAT decide to connect to the other digesters to the system as well (see feasibility study report).

# Project approach and deliverables

The proposed project is a co-operation between the CSIR and ERWAT who is owned by the Johannesburg Metro and is the waste water treatment service provider for the Ekurhuleni municipality. The CSIR has already spent in excess of R3,0m on the development of the biogas technology package, project planning, partner selection and technical feasibility studies.  The feasibility study report is attached to this proposal.  This preparatory work will position this project to be conducted within a maximum of 18 months.

Specific deliverables are:

- A fully developed and tested technology package of a two-stage anaerobic digestion process adjusted for implementation at ERWAT’s Hartbeestfontein WWT plant with the purpose of generating biogas for use in an internal combustion engine to generate renewable energy. Specific components of this deliverable include analysis of the expected biogas based on the characteristics of the waste processed at the WWT plant, technical designs, and an implementation plan for the physical works to be carried out.

- A fully operational pilot project at a municipal water treatment plant in which the technology package has been installed and which results in the generation of approximately 1 GWh per annum of renewable electricity offsetting approximately 936 tons of CO2 associated with the avoided use of grid electricity and providing the benefits as described above. Specific components of this deliverable include procurement of equipment, contracting of installers, the physical works on site and the training of operating staff.

As indicated in the feasibility study report, the technology package will be implemented, using an existing biogas digester that will be modified to two stage operation and two CHP units of 65 kWe. The full biogas to electricity installation is expected to have a life span of 25 to 30 years, with an Operation & Maintenance (O&M) cost of approximately R 500.000 / year, which will be carried by ERWAT. The operation of the technology package by ERWAT will be conducted in close collaboration with the CSIR to generate experience in operation modalities and identification of possible improvements in the technology package to enhance outcomes.

## Detailed project activities

To conduct he project, the following activities are planned:

Digester upgrade

The following tasks will be done:

- Decoupling of the digester from the current set of 10 digesters

- Confirmation of the state of the digester and detailed technical plans on the work to be carried out.

- Removal of grit from the digester. Site inspections have revealed that 45% by volume of the digester is filled with grit that needs to be removed.

- Removal of current, non-functional mixing equipment and piping for heating.

- Installation of new mixing equipment.

- Installation of heat exchangers to heat the sludge.

- Installation of pipes for the biogas: one link to the existing gas storage and one to the small CHP units.

- Design and construction of the second tank.

- Installation of gas polishers / scrubbers to remove unwanted content from the biogas.

- Installation of CHP units that will generate the required electricity and heat to run the digester at mesophylic temperature.

- Installation of pipes to the second stage for sludge transport.

- Installation of a control system, including required valves and measurement points and linking that to the existing ERWAT PLC controller.

We expect to start the physical work on the digesters once the technical designs have been finalised and the required procurement procedures have been followed. Actual work on the digester will require approximately 6 months.

Gas composition determination

In parallel, the sludge from Hartbeestfontein will be digested in the CSIR pilot plant to determine the characteristics of the sludge as well as the exact amount and quality of gas that can be expected.  The sludge will be used in the pilot plant for three months to determine the composition of the sludge, its energy potential and the amount of cleaning / scrubbing of the gas needed before it can be used in an engine.

Planning and execution of community fertiliser programme

This task will be conducted by ERWAT with assistance from the CSIR.  The treatment of the de-activated sludge to produce fertiliser will become part of the current ERWAT community programme.

ERWAT has indicated that community members will be involved in the following way:

- If a pellet machine is available at a WWTP site; jobs could be created where pellet machine operators  are required as well as people for packaging the compost pellets into bags;

- For large scale farms, people could be hired for loading or offloading the bags into trucks;

- For small scale farms, people could be hired to manually spread the compost by hand, whereas on large scale farms, drivers of tractors could be employed, and

- If the sludge is of very good quality; it might require large amounts of people being employed since it would be of high demand.

It is estimated that 20 to 40 jobs can be created in this way. Details are given in the attached feasibility study.

Training of operators

During the construction period operators of ERWAT will be made familiar with the (components of the) technology and will be provided with on-the-job training once the digester is fully operational.

# Feasibility

Recognizing that municipalities would not have the capacity to build and operate the relatively sophisticated technology package, a management model will be developed that will ensure sustained operation of the facility. During the implementation period of the project the CSIR will be involved in the daily operation to identify possible improvements in the technology package that can facilitate the operation thereof.

The feasibility study (see attached report) indicated that the project is technically and economically feasible.  Most of the equipment required is readily obtainable.  The scalability of the solutions is discussed in some detail in the feasibility report.  It is not foreseen that there will be major challenges in up scaling the pilot plant to a full size anaerobic digester.

# Risks

There are a number of risks to the project. These are analysed and discussed in detail in the feasibility study report.

The first relates to technology risk. As indicated before the technologies that will be applied (anaerobic digestion and an internal combustion engine to generate electricity) are both mature technologies. The technology risk is limited to the integration of these technologies into one technology package, which is limited due to earlier modelling work done by the CSIR as well as the development of the prototype.

Secondly risks related to the project timeline and budget. These risks will be managed through proper project management and the use of standardised procedures.

Thirdly the risk of limited capacity at the WWT plant where the technology package will be implemented. This risk will be mitigated through intensive staff training and capacity building. New technology concepts will be introduced in a phased manner in order to avoid too high innovation rates. Once the technology package has been implemented and tested, and the ERWAT staff trained in its use, management of the installation will be handed over to ERWAT in a gradual fashion.

Risk 4 is related to the policy and legislative requirements especially those related to environmental impact.  The proposed technology package will not require a full EIA as we will be upgrading existing digesters, or more specifically, bringing them back to working order. As the electricity generated will be used within the boundaries of the WWT plant, no generation licence is required as no electricity will be supplied to the electricity grid.  Seeing that ERWAT is au fait with the handling of biogas this is a low risk.

# Capacity building, job creation and HCD

The project is designed around existing WWT plants and ways to optimise their operation. The project will modify already existing infrastructure and will make use of existing staff of the WWT facility. It is therefore not foreseen that new jobs will be created. However, intensive collaboration between the CSIR and the WWT facility will result in increased capacity at the WWT facility.

The modification of the de-activated sludge to produce fertiliser through the ERWAT community programme will however create some jobs. This will be done through the current ERWAT community programme as described above.

It is expected that the proposed project will lend itself ideally for practical work by Masters students of local universities.  It is envisaged that three students will participate in the project.

# Scientific knowledge generation and dissemination

The project will make use of the results of ongoing scientific research at the CSIR towards optimisation of the anaerobic digestion process. The application of this technology at an existing WWT plant will result in additional scientific knowledge on technology implementation. It is expected that between the CSIR and the WWT plant operator a number of presentations will be given at local conferences and one or two scientific articles will be produced.

The CSIR approach is novel and a provisional patent has been registered after evaluation by patent attorneys. During the first phase of the project possible further IP that can be generated through the project will be identified.

# Governance

The proposed implementation of the waste to electricity technology will take place at an existing WWT plant currently operated as an ongoing concern. The technology package will result in a modification of the operation of the plant that can be incorporated into the current business model.

It is anticipated that the requested funds will be used towards optimising the technology, procurement and installation of the technology and training of the operations staff to handle the technology. An extensive period of support by the CSIR is envisaged before the installation is handed over fully to the WWT plant operator.

As the operation of the technology package will be fully embedded in existing structures no major issues are anticipated regarding the governance if the project.

Project expenditure will be subject to the CSIR governance rules and external auditors.

# Budget estimate

This proposal comes at the end of a two year feasibility study funded by R 3 million of Parliamentary Grant investment by four CSIR Operating Units into laboratory-scale and small prototype experimentation with the two-stage AD proposed for this project.

Detail of the budgeted costs for the project is given in Tables 1 to 4 below.

Table 1: Total project costs

Table 2:  Detailed costs

Table 3:  Breakdown of control system costs

Table 4:  Detail of labour costs (this excludes a contribution of R 500.000 by the CSIR towards the project management costs

# Appendix I: CSIR anaerobic digester

The anaerobic digestion process is the biological breakdown of organic matter in an environment void of atmospheric oxygen. The breakdown of the organic material is done through four stages namely Hydrolysis, Acidogenesis, Acetogenesis and Methanogenesis. The organic sludge cannot be classified as stabilised unless all four these stages has been completed. The bacteria required for these four processes require certain parameters to be at optimal levels for the most efficient performance. These parameters include temperature, pH, loading rate and mixing. When these parameters are controlled to the required levels from the micro flora it will bring about a more complete and efficient process.

Traditionally the above processes were maintained by daily readings and laboratory analysis to establish action required to alter the environment for the optimal performance of the digester. Automating such procedures will improve the efficiency of the digester by eliminating the human factor that often leads to failure.

Differences between CSIR technology and conventional technology

The CSIR has developed an Automated AD that monitors and maintains the pH, temperature, loading and mixing. This technology has proved that the maintenance and control of the loading rate can in fact adjust the pH of the digester if the loading rate for the specific digester is maintained and adjusted according to the pH measured in the digester sludge.

The thermal energy required for the maintenance of the mesophilic temperature within the digester was supplied by a thermal generator other than the traditional combustion of the bio gas produced for temperature maintenance. This has proven that 100% of the gas product can be then utilised for alternative uses.

The automation system allows for a 24 hour operation of the AD without the input from manual labour. This allows for the environment within the AD to be adjusted over 24 hours. It also allows spreading out the loading of the digester that limits the shock that is placed on the digester by the introduction of the full daily load of raw feedstock at once as per traditional method. The spreading out of the available feedstock ensures a more constant production of gas over a 24 hour period as opposed to the traditional methods of taking the daily available feedstock and introducing this at once.  The cooler feedstock also requires a higher energy input to maintain the temperature in the digester due to the higher percentage of sludge that is introduced.

The two stage design of the CSIR AD allows for the digestion process to be continuous. Traditional methods would require shutting down the AD for a period of 2-3 days in order to allow the sludge to separate in to different strata. This would allow then for the extraction of the strata for further treatment and disposal. The CSIR system allows for the separation to occur in a separate vessel other than the main Reactor / Digester. This allows for the continuous operation and will improve the capacity of any plant that employs such a system. The energy consumption of the traditional method is also higher than that of a continuous system due to the requirement to reheat the entire digester once the extraction of the strata is complete.

Conclusion

An Automated two stage system not only eliminates failures due to human error but allows for a more energy efficient operation of an AD. The maintenance of the loading rate, pH, temperature and mixing allows for improved performance of the technology in general. The CSIR technology has proven that an alternative method of heating the AD will allow for harvesting of 100% of the bio gas product to be used for alternative use. This will increase the electricity generation capacity by the same percentage as the gas that would traditionally be required for the heating of the digester.

APPENDIX D: INTERVENTION AREA 3

CSIR WATER SUSTAINABILITY FLAGSHIP

REAL-TIME MONITORING, EVALUATION AND RESPONSE SYSTEM

| By: | Shaba Shabane | Signature | Date |
| --- | --- | --- | --- |
| Designation: | Project Manager: CSIR CAS |  |  |
| Approved By: | Gerhard Smith | Signature | Date |
| Designation | General Manager: CSIR CAS |  |  |

Contents

1.	PROJECT BACKGROUND	52

Project Need/Problem	52

Project Purpose	52

Summary of investments and achievements to date	52

Programme Overview	53

2.	PROJECT SCOPE DEFINITION	54

3.	PROJECT OBJECTIVES (GOALS)	54

Sensing Station	54

Software Development	54

Server	55

Modeling	55

Business Processes	55

Site Support	56

4.	PROJECT PRIORITIES	56

5.	PROJECT KEY STAKEHOLDERS	56

6.	PROJECT CONSTRAINTS, ASSUMPTIONS AND DEPENDENCES	57

7.	LIST OF PROJECT DELIVERABLES AND MILESTONES	57

WQMS	57

Stakeholders	58

Potential Clients	58

8.	INITIAL PROJECT RISKS	58

9.	PROJECT COST ESTIMATES	59

10.	PROJECT SCHEDULE ESTIMATES	60

11.	PROJECT SUCCESS CRITERIA	60

Proof of Concept	60

Pilot	60

12.	CONCLUSION	60

# PROJECT BACKGROUND

## Project Need/Problem

Many of South Africa’s municipalities cannot afford to maintain their waste water treatment plants. This has resulted in the situation which currently exists which is that, as of April 2010/11, only 7% of South Africa’s assessed waste water treatment facilities work to international standards. Only 50% of the existing facilities were tested.

A need has been identified to provide municipal water treatment plants in South Africa with water quality monitoring equipment, which can relay data back to a central monitor and control station. This will allow much needed expertise to be sent to the plants as and when required.

CSIR has been contracted through its Consulting and Analytical Services (CAS) unit, to produce this system. Material Science and Manufacturing (MSM) is working with CAS to develop the electrical, electronic and mechanical hardware necessary to provide this Water Quality Monitoring System (WQMS).

## Project Purpose

The Green Drop certification programme forms part of incentive-based regulation implemented by the Department of Water Affairs to identify and develop core competencies required in wastewater management. Compliance with the Green Drop certification programme will ensure that all Water Service Authorities are gradually and sustainably able to improve the level of wastewater management.  Green Drop Certification, a program specifically aimed at Waste Water Treatment Works (WWTW), aims to ensure that WWTW continuously improve their operations so as not to impact negatively on the water bodies into which they discharge their end product.

The DWA’s 2010/11 Green Drop report assessed the quality of waste water effluent at about 850 Municipal waste water plants.  In order for plants to achieve Green Drop status, water quality monitoring is a key requirement. This is absent in almost 90% of the plants.  There are also monitoring skills shortages and options of remote monitoring are deemed expensive.

## Summary of investments and achievements to date

The WQMS sensing station, its electronics and electrical systems were designed and full specifications developed for software, electronics, mechanics and testing.  Four test units were produced and 20 prototypes have been manufactured for the pilot studies.  The ‘Hydra’ board was developed and tailored in-house specifically for the WQMS application. In addition this solution offers options for further expansion as needs are identified.

An initial version of the server software platform and user interface has been developed. It is currently in use with the data collected by the test units that have already been installed.  A demonstration version has also shown for the demo sensing station used in presentations to stakeholders. A thorough review of the software and user interface has recently been carried out, including all CSIR and Prime Africa team members to document all processes and identify gaps relating to further potential system enhancements and offerings as well as understand user and potential client requirements.

The key component of the CSIR’s WQMS is a real-time, remote water quality monitoring and data management component, tied into a monitoring and evaluation system to be developed for monitoring the Green Drop status.  Real-time management information will be available, and that laboratory costs of water quality monitoring will be reduced. The intent is to have this system help municipalities to obtain and keep Green Drop status for their respective treatment plants.

## Project Overview

The CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop certification. A decision was taken to focus initially on the first module, namely assisting with Green Drop certification. Thereafter, the platform and criteria and indicators will be incrementally modified to cover the other market areas, which potentially are larger than the Green Drop market. There will be continuous or iterative feedback loops to the modelling groups to ensure improvement of the algorithms used in a process of ongoing improvement.

# PROJECT SCOPE DEFINITION

This project will cover the first phase of completing the proof of concept (development, testing and debugging) of the WQMS, and the second phase required to achieve the envisaged impact of the WQMS, namely the piloting and the marketing of the concept. The pilot study installation would be of sizeable number of units with client municipalities.

The following illustration is a diagram of the current system design

# PROJECT OBJECTIVES (GOALS)

### Sensing Station

The manufacturing process is to be scaled up for regular production.  Upgraded versions of the Hydra board are planned and the station is to be modified to include further sensors which will require both hardware and software upgrades. Planned upgrades in firmware will entail the interfacing with a newly defined server protocol, as well as allowing firmware upgrades in the field. Extensive self-analysis and self-maintenance options are also planned. A sample turbidity probe has already been sourced which must be built into a test unit and tested in situ.  The current proof of concept installations will be completed by April 2012, while the manufacturing process is planned to be in place by mid 2012.

### Software Development

The software will be upgraded to ensure a high level of appropriateness and adaptability in relation to the following key processes:

- Sensing stations

  - Sending and receiving data and status messages

  - Configurations work flow

  - Installation and activation of stations

  - Maintenance and calibration processes

- Customer interface

- Deployment

- Monetization

- Immovable Asset Management (IAM) and integration with the CSIR’s IAM system

- Communication (command centre, customers and CSIR team members)

- Server management

  - Communications

  - Rules engine

  - Customer service

  - Notification service

- Rules

- Notifications

The information platform component is a critical backbone for many products within CAS. It will form the central repository for all management information for this platform and allow models to be used and management reports to be derived that are fit-for-purpose for different levels of management.

### Server

Additional hardware must be procured to establish the development environment required by the system.  This procurement and the related hosting of the infrastructure will take place in the first quarter of 2012/2013, with budget planned for upgrades or possible additional hardware requirements in 2013/2014.

### Modeling

For improved water quality algorithms, at least 400 data sets are required.  This requires sampling at eight more WWTPs, and taking three sets of 10 samples at each of these.  It is planned to complete this by August 2012.   As additional probes are added to the sensing station, new algorithms must be developed to utilise the new data available and further sampling and calibration must be done to ensure correlation with laboratory results.  This development and the refinement of algorithms will be a continuous process.

### Business Processes

Business development and project management of proof of concept and pilot study will continue.  The project management function will be essential to ensure that the platform as a whole is developed comprehensively. Given that CSIR CAS is ultimately responsible and accountable for delivery of this platform, an overall dedicated Project Manager has been appointed to assume ultimate accountability for delivery on the platform. The project manager will ensure delivery of all sub-projects and the appropriate alignment of resources and collaborators to ensure success. Each sub-project will be assigned junior project managers that will complete the sub-projects associated with the platform. These managers will meet regularly (as required) to ensure delivery is on brief, budget and time. The normal CSIR governance and support structures will apply.

### Site Support

It is the intent of this project to involve interns programs, to assist with initial water sampling and possible regular maintenance on the installed systems. Where this is not possible, an automated sampler will be installed to obtain the 24 hour sampling cycle as required. The project will procure a few of these auto-samplers to be used for the proof of concept and pilot sites as and where needed.

# PROJECT PRIORITIES

The sequence of activities would be as follows:

- Continuation of proof of concept sites, to be executed in parallel to pilot sites

- Selection of further pilot sites, physical contract in place

- Site-visit, inspection and evaluation

- Conduct initial water sampling

- Installation and commissioning of WQMS units

- Initial data reporting

- Rules development for pilot site, implemented on server

- Regular maintenance and calibration of the WQMS Station

- Maintenance response teams to assist under-capacitated municipalities

# PROJECT KEY STAKEHOLDERS

The following internal and external stakeholders were identified

STAKEHOLDERS

INTERNAL STAKEHOLDERS

Material, Science & Manufacturing - MSM

Consulting & Analytical Services - CAS

Natural Resources & Environment - NRE

Modelling & Digital Science - MDS

Built Environment - BE

ICT

Finance

Marketing

Procurement

EXTERNAL STAKEHOLDERS

Customer/user base

- Department of Water Affairs

- Various NGO’s (e.g. Municipalities)

- Department of Defence (TBC)

- Department of Health

- Water Board

Infrastructure & Services

- Cellular Providers (MTN, Vodacom, Cell C)

- ESKOM Power

Sub Contractors

- Installation & Maintenance providers (e.g. Electrical/Instrumentation contractor) - Emergency Services (internal or external)

- Modelling Experts (e.g. Prime Africa)

- Development (e.g. DVT)

Training Partners (e.g. MANDEVCO)

The following project task team was identified

| Name | Email | Group | Project Role |
| --- | --- | --- | --- |
| Gerhard Smith | gpsmith@csir.co.za | CSIR CAS | Project sponsor |
| Sumeshan Govender | sgovender1@csir.co.za | CSIR CAS | Business development |
| Karen van Breukelen | kvbreukelen@csir.co.za | CSIR CAS | Business development |
| Shaba Shabane | sshabane@csir.co.za | CSIR CAS | Project manager |
| Riaan Coetzee | rcoetzee@csir.co.za | CSIR MSM | Business development |
| Peter Bosscha | pbosscha@csir.co.za | CSIR MSM | System development |
| Kevin Wall | kwall@csir.co.sa | CSIR NRE | Subject Expert |

# PROJECT CONSTRAINTS, ASSUMPTIONS AND DEPENDENCES

The following constraints, assumptions and dependences were identified

| Item | Description |
| --- | --- |
| Constraints | ? |
| Assumptions | Full scale pilot sites are contracted |
| Dependences | Subcontractor of server software deliver on time |

# LIST OF PROJECT DELIVERABLES AND MILESTONES

### WQMS

The task team will embark on piloting this technology at full scale, with quality outcomes and benefits of 10 to 20 nodes. The CSIR is conducting a proof of concept to a number of stand-alone units within the Tshwane region, and now will be seeking to install pilot units at a larger scale.

Lepelle Northern Water (LNW) has kindly offered three WWTWs as potential sites for extending this pilot programme for a 12 month period. These pilot sites are Burgersfort, Marble Hall and Steelpoort.  A further 11 sites in the Sekhukune District Municipality will be sourced for the pilot.

### Stakeholders

The task team will engage with key external stakeholders to align project deliverables with their current strategic initiatives.

### Potential Clients

Strong relationships have been established and sustained with potential clients at the provincial and municipal level, in the Limpopo, Free State and KwaZulu/Natal in particular.  Numerous presentations to target groups and the broader water community at conferences have taken place, generating interest and deepening our knowledge of on-the-ground concerns and challenges.

# INITIAL PROJECT RISKS

The following high and medium level risks were identified

| Potential Risk | Risk Description |
| --- | --- |
| Funding | No funding received from the Executive to execute the system |
| Roll out | Lack of capacity to implement the system |
| Development | Debugging fixes may generate new errors on the system |
| Pilot sites | Not sufficient sites have been identified to test the system on larger scale |
| Lab testing | Lack of capacity to do sampling and lab tests as required by Green Drop |
| POC vs Pilot | Proof of concept not fully tested and proven to be executed along pilot |

# PROJECT COST ESTIMATES

| Task | 2012/2013 |
| --- | --- |
| Pilot Sites Units Yr 1 | R 1 694 000.00 |
| Configuration of Pilot Units Yr 1 | R 100 000.00 |
| Governance - Site Inspections | R 490 000.00 |
| Governance - Laboratory Testing | R 490 000.00 |
| Governance - WWTW Assessments | R 4 420 000.00 |
| Modelling & Algorithms | R 600 000.00 |
| Hardware & Software | R 800 000.00 |
| Next Generation | R 4 036 000.00 |
| Project Management | R 700 000.00 |
|  | R 13 330 000.00 |

# PROJECT SCHEDULE ESTIMATES

The near real-time monitoring, evaluation and response system will address short, medium and long term water quality issues, however this project will focus on immediate, 18 to 24 months deliverables. A detailed project schedule is scoped to outline a full work breakdown structure, and will be delivered to the WSF forum.

# PROJECT SUCCESS CRITERIA

### Proof of Concept

Five test sites are in place currently, two units are operating side-by-side at Daspoort Waste Water Treatment Works to provide data sets on which to measure repeatability across units.  A unit is installed in the north eastern dam on CSIR campus and a further unit is installed at Sunderland Waste Water Treatment Works. Finally, a unit is installed at the Refilwe (near Cullinan) Waste Water Treatment works. These sites will be maintained until at least the end of the 2012/2013 financial year.  This will require calibration, maintenance and regular sampling for laboratory comparisons.

### Pilot

Furthermore, pilot studies will be undertaken in the 2012/2013 financial year with partnering municipalities.  These studies will utilize most of the 20 prototype sensing stations already available and provide an essential “reality check” of the challenges facing the system when installed on a larger scale at WWTWs not necessarily functioning at the standard of the Tshwane WWTWs currently used as test sites.

# CONCLUSION

This project aims to make available a CSIR solution which provides a real-time monitoring, evaluation and response system to an NGO. This solution will provide municipalities with a system to obtain and maintain their Green Drop certification status. The solution will be marketed within South Africa initially but later on internationally, such that it will provide a steady source of income to the CSIR.

| TASK DETAIL SHEET |  |  |  | Date: | 24-Apr-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Pilot Sites Units Yr 1 |  |  | Task Ref. No.: | 3.1 |  |
| Description: | Installation, commissioning and maintenance of WQMS units at pilot sites |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 1 355 205.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Terblanche P. | R 665.00 | 160 | R 106 400.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 120 | R 145 200.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 639 | R 233 235.00 |  |  |  |
| Mbizeni A. | R 365.00 | 638 | R 232 870.00 |  |  |  |
|  |  |  |  | R 637 500.00 | S&T & installation |  |
| Totals |  |  | R 717 705.00 | R 637 500.00 |  |  |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Installation of Units on Site |  |  |  |  |  |
| 2 | Maintenance Reports |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • Installations need to be confirmed and approved by site owner, this process might take time. • Lacking Infrastructure might impose additional installation costs. • Assumed that site-visits (Inspect, Commissioning, Maintenance) will be combined trips, additional costs if not. |  |  |  |  |  |  |
| Various notes (including capital needs) Sub-Contractors will be used for electrical and basic plumbing, the installation amounts are estimated based on previous quotations. |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Notification and Alerting system |  |  |  |  |  |  |  | Task Ref. Number: 3.2 (E1.1) |  |  |  |  |
| Description: Implementation and development of the Wide Area Alerting Sub-system as component of the real-time monitoring and response system |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Graeme McFerren, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31August 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 70 000 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Integrate WAAS sub system, test and deploy Configure ISP for SMS notifications |  |  |  |  | Critical predecessor tasks: Operational monitoring system; databases and server Confirmed ISP |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 55 |  | 37950 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 50 |  | 32250 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 70200 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | The contract costs for the Short Message Service provider is not included in this budget |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Access will be allowed to sensor databases, server and software currently in use (b) a list of client subscribers are available for testing purposes. Contingencies: A suitable ISP provider has been contracted to provide bulk SMS services |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): A suitable ISP provider has been contracted to provide bulk SMS services |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated platform design |  |  |  |  |  |  |  | Task Ref. Number: 3.3 (E1.2) |  |  |  |  |
| Description: Design the architecture of the integrated water information platform based on open standards and open source software. |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31Dec 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 90 000 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| T van Zyl |  | 885 | 75 |  | 66375 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 20 |  | 24300 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 90675 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Specifications for open standards compliant platform, including data models and first level system components |  |  |  |  |  |  |  |  |  | Development of platform |  |  |
|  | Defined migration process from current to new system |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Configuration of Pilot Units Yr 1 |  |  | Task Ref. No.: | 3.4 |  |
| Description: | Configure communication & activate installed units |  |  |  |  |  |
| Responsible Resource: |  | Matthew Vassard |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Aug-12 |  |  |  |  |  |
| Total Budget | R 100 000.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: 3.1 Pilot Sites Units Yr 1 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| M Vassard | R 645.00 | 132 | R 85 140.00 |  |  |  |
|  |  |  |  | R 14 860.00 | S&T & disbursements |  |
| Totals |  |  | R 85 140.00 | R 14 860.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Operational units sending functional data |  |  | 3.6 | Governance - Lab Testing |  |
| Assumptions, Risk Factors & Contingencies • Units installed with sufficient GSM coverage |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - Site Inspections |  |  | Task Ref. No.: | 3.5 |  |
| Description: | Initial site inspections, gathering of data to prepare for detailed WWTW assessments & agree to placement of Units |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 30-Sep-12 |  |  |  |  |  |
| Total Budget | R 490 000.00 |  |  |  |  |  |
| Input & Specifications: Site managers' cooperation |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Adlem | R 745.00 | 200 | R 149 000.00 |  |  |  |
| Interns | R 70.00 | 672 | R 47 040.00 |  |  |  |
| Water lab resource | R 450.00 | 336 | R 151 200.00 |  |  |  |
| JJ Lottering | R 585.00 | 160 | R 93 600.00 |  |  |  |
|  |  |  |  | R 49 160.00 | S&T & disbursements |  |
| Totals |  |  | R 440 840.00 | R 49 160.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Inspection reports for each site |  |  | 3.1 | Pilot Sites Units Yr 1 |  |
|  | specific installation placement agreed to with operator |  |  | 3.4 | Configuration of Pilot Units Yr 1 |  |
| Assumptions, Risk Factors & Contingencies • cooperation of WWTW resources • coordination with task 3.1 as has to happen concurrently |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - Laboratory Testing |  |  | Task Ref. No.: | 3.6 |  |
| Description: | 24 hour sampling to determine water footprint on installation and regular testing to provide lab correlation to field data |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 442 288.00 |  |  |  |  |  |
| Input & Specifications: Site managers' cooperation |  |  | Critical predecessor tasks: 3.1, 3.2 and 3.3 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Adlem | R 745.00 | 28 | R 20 860.00 |  |  |  |
| CAS Water Lab |  |  | R 333 760.00 |  |  |  |
|  |  |  |  | R 40 628.00 | S&T & disbursements |  |
| Intern | R 70.00 | 672 | R 47 040.00 |  |  |  |
| Totals |  |  | R 401 660.00 | R 40 628.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Water footprint for each site |  |  | 3.8 | Modelling & Algorithms |  |
|  | regular samples tested in labs |  |  |  |  |  |
|  | data fed into modelling for correlation |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • availability & competence of interns / auto-samplers to collect 24 hours samples & other samples |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - WWTW Assessments |  |  | Task Ref. No.: | 3.7 |  |
| Description: | detailed assessments and recommendations for plant ops support and immovable asset management |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 30-Nov-12 |  |  |  |  |  |
| Total Budget | R 3 535 400.00 |  |  |  |  |  |
| Input & Specifications: WWTW specific info as available |  |  | Critical predecessor tasks: 3.3 Governance - Site Inspections |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Greyvensteyn | R 1 140.00 | 640 | R 729 600.00 |  |  |  |
| P Liebenberg | R 1 050.00 | 640 | R 672 000.00 |  |  |  |
| J Lottering | R 585.00 | 800 | R 468 000.00 | R 206 200.00 | S&T & disbursements |  |
| IAM QC team members | R 700.00 | 1228 | R 859 600.00 |  |  |  |
| M Moodley | R 750.00 | 800 | R 600 000.00 |  |  |  |
| Totals |  |  | R 3 329 200.00 | R 206 200.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | detailed assessment reports per site |  |  |  |  |  |
|  | recommendations for implementation at WWTW |  |  |  |  |  |
|  | asset registers and exec summaries per site |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • availability of sub-contractor & collaborator resources |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Modelling & Algorithms |  |  | Task Ref. No.: | 3.8 |  |
| Description: | Application of unit & lab test data to refine models & tailor site specific rules |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 600 000.00 |  |  |  |  |  |
| Input & Specifications: data received from field & labs |  |  | Critical predecessor tasks: 3.1, 3.4, 3.6 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| S Kok | R 1 350.00 | 110 | R 148 500.00 | R 7 750.00 | incidentals |  |
| O Ubbink | R 1 800.00 | 35 | R 63 000.00 |  |  |  |
| J Kekana | R 510.00 | 190 | R 96 900.00 |  |  |  |
| N Siyakatshana | R 930.00 | 145 | R 134 850.00 |  |  |  |
| C Adlem | R 745.00 | 200 | R 149 000.00 |  |  |  |
| Totals |  |  | R 592 250.00 | R 7 750.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | refined models with site specific requirements |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • sufficient data of confirmable quality • understanding of license measures for each site |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Hardware & Software |  |  | Task Ref. No.: | 3.9 |  |
| Description: | upgrade software, procure additional server & provide comms consumables (SIMS) |  |  |  |  |  |
| Responsible Resource: |  | Matthew Vassard |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 31-Aug-12 |  |  |  |  |  |
| Total Budget | R 800 000.00 |  |  |  |  |  |
| Input & Specifications: user requirements outputs & learnings from 3.7a-c |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| M Vassard | R 645.00 | 80 | R 51 600.00 |  | Server | R 250 000.00 |
|  |  |  |  | R 400 000.00 | software development |  |
|  |  |  |  | R 98 400.00 | SIMS & related |  |
| Totals |  |  | R 51 600.00 | R 498 400.00 |  | R 250 000.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | functional software & hardware infrastructure |  |  | 3.7a-c | to run in parallel effectively |  |
|  | comms between units & server |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • valid user input • procurement processes |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Near real time monitoring system |  |  |  |  |  |  |  | Task Ref. Number: 3.10 (E1.3) |  |  |  |  |
| Description: Develop and pilot (test) monitoring system and core integrated platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Dec 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 290700 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  | Server |  | 110000 |
| M Mtetsfwa |  | 645 | 80 |  | 51600 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 60 |  | 53100 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 160 |  | 103200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 290700 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): Server and backup hardware to be procured: R110 000 |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated near real time monitoring system |  |  |  |  |  |  |  | Task Ref. Number: 3.11 (E1.4) |  |  |  |  |
| Description: Near real-time monitoring system tested, validated and operational on core integrated platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Jan 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2013 |  |  |  |  |  |  |  |  |  |  |
|  |  | 369900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 100 |  | 64500 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 80 |  | 70800 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 160 |  | 103200 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 40 |  | 48600 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 369900 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Next Generation |  |  | Task Ref. No.: | 3.12 |  |
| Description: | Sensor updates & add-ons, electronics & mechanical updates, software updates & manufacturing ready data-pack. Manufacture of 10x additional units |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 3 228 017 |  |  |  |  |  |
| Input & Specifications: previous design, updates to be generated as first instance |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Terblanche P. | R 665.00 | 600 | R 399 000.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 604 | R 730 840.00 |  |  |  |
| Coetzee S. | R 585.00 | 712 | R 416 520.00 |  |  |  |
| Swart S. | R 429.00 | 328 | R 140 712.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 947 | R 345 655.00 |  |  |  |
| Mbizeni A. | R 365.00 | 946 | R 345 290.00 |  |  |  |
|  |  |  |  | R 850 000.00 | hardware / parts |  |
| Totals |  |  | R 2 378 017.00 | R 850 000.00 |  | R 0.00 |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Retrofit of existing units |  |  |  |  |  |
| 2 | Sensor Research, User and System Specifications |  |  |  |  |  |
| 3 | Improved Design |  |  |  |  |  |
| 4 | 10x Next Generation Units with production datapack, improved sensor data, more reliable and easier operation, better maintainable. |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • procurement processes / suppliers |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Project management |  |  | Task Ref. No.: | 3.13 |  |
| Description: | PM, monitoring & evaluation of progress |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 700 000.00 |  |  |  |  |  |
| Input & Specifications: info from all other tasks |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| K van Breukelen | R 850.00 | 800 | R 680 000.00 | R 20 000.00 | disbursements |  |
| Totals |  |  | R 680 000.00 | R 20 000.00 |  | R 0.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | good governance control of project |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Field Measurements & Project Management |  |  | Task Ref. No.: | 3.14 |  |
| Description: | MSM PG Co-Funding |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 1 000 205.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Coetzee R. | R 1 287.00 | 120 | R 154 440.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 240 | R 290 400.00 |  |  |  |
| Terblanche. P. | R 665.00 | 240 | R 159 600.00 |  |  |  |
| Coetzee S. | R 585.00 | 150 | R 87 750.00 |  |  |  |
| Swart S. | R 429.00 | 150 | R 64 350.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 211 | R 77 015.00 |  |  |  |
| Mbizeni A. | R 365.00 | 210 | R 76 650.00 |  |  |  |
|  |  |  |  | R 90 000.00 | Travel, Sensors, Installation |  |
| Totals |  |  | R 910 205.00 | R 90 000.00 |  |  |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Project Management of Tasks 3.1, 3.8 and 3.10 |  |  |  |  |  |
| 2 | Plant Inflow Measurement of Total Organic Loading |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • Access to site for inflow monitoring installation |  |  |  |  |  |  |
| Various notes (including capital needs) Sub-Contractors will be used for electrical and basic plumbing, the installation amounts are estimated based on previous quotations. |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | CAS Co-funding |  |  | Task Ref. No.: | 3.16 |  |
| Description: | CAS system & rules development |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Apr-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 7 000 000.00 |  |  |  |  |  |
| Input & Specifications: WQMS concept and business plan |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| CAS Team | R 800.00 | 4500 | R 3 600 000.00 | R 3 400 000.00 |  |  |
| Totals |  |  | R 3 600 000.00 | R 3 400 000.00 |  | R 0.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Pilot ready system and processes |  |  | All |  |  |
| Assumptions, Risk Factors & Contingencies • valid user input • procurement processes • integration with all tasks |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

APPENDIX E: ICT AS A CROSS-CUTTER:

# Meraka Contribution to the CSIR Water Sustainability Flagship

# Summary

The CSIR Meraka Institute has a well established capability and track record in developing and deploying operational sensor monitoring and alert platforms for environmental phenomena. The most prominent of these is the Advanced Fire Information System (AFIS) that monitors threatening wildfires, so-called ‘hotspots’, and provides near real-time notifications and alerts to a variety of clients. Another example is the Earth Observation Water Quality Monitoring and Mapping system developed as part of the Safe Water Earth Observation (SWEOS) CSIR Science Research Project.

Several mature technologies underpinning these platforms have been implemented; the Wide Area Alerting System, for example, is a TRL level 7 ICT platform that generates and disseminates data and information derived from data originating from heterogeneous sensors, models or monitoring processes, over multiple digital communications channels. This proposal addresses Intervention Areas 3 and 4 of the WSF through the following interventions:

- Collaboratively implement the dissemination component of a water quality monitoring system currently developed by CSIR Analytical Services(?) (CAS). The Wide Area Alerting System (WAAS) will be deployed to disseminate notification and alert messages through selected communications channels.

- Develop an open source, extensible, scalable and interoperable platform for near real-time water quality monitoring, sustainability assessment and response. The platform will be based on Open Standards compliant services and interfaces, and deploy technologies at Readiness Level 6 and higher. Sub-components of the initial pilot will be migrated to this platform.

## Contributors

Anwar Vahed

Graeme McFerren

Albert Lysko

Thomas Olwal

Louis Coetzee

# 1.  Introduction

The CSIR Meraka Institute is the leading practitioner in Africa for the development and deployment of standards compliant and open source ICT for environmental observation. The Advanced Fire Information System (AFIS) is a well-known operational system that monitors wild fires and provides near real-time information to clients such as ESKOM and farmers. Another example of implementation is the sensor observation and monitoring system developed as part of the Safe Water Earth Observation System (SWEOS). The system provides maps of eutrophication and cyanobacterial indices, water clarity and other water quality products for approximately 250 major dams in South Africa. A similar system is developed for the Acid Mine Drainage Science Research project for which data from in-situ water chemistry sensors is monitored.

The technologies deployed in these applications are domain agnostic, i.e., the code base is generalised and can be implemented for arbitrary environmental monitoring applications and for heterogeneous types of sensor (remote, air-borne or in-situ), the latter being technically the easiest to leverage. Deployment of a new application involves some configuration steps, styling of user interfaces and connecting databases of observations. It is important to note that this platform is designed to be layered, i.e., it is expressly not a single 'stovepipe' solution and aimed at making it possible to open up water quality and other observational data to a wide audience.

## 1.1  Open Standards and Interoperability

Different custodians of sensory data can employ different or even proprietary formats and models for provided data and derived products. This condition presents an interoperability impediment resulting in information isolation. The use of open standards and encodings in the provision of data products is a key requirement for sharing data and is encouraged by national strategy. Sensor Web Enablement is a well-established concept that provides a suite of standardised web service interfaces and encodings for sensory data exchange.

The Open Geospatial Consortium (OGC) open standards have been adopted in the South African Earth Observation System (SAEOS). A number of OGC compliant Sensor Web services have been deployed in SAEOS for, amongst others, weather stations, oceanographic and remote sensors. These specifications include models for encoding sensor observations and measurements, for describing sensor systems and associated processes, interfaces for requesting and retrieving sensor data, and for publishing and subscribing to alert notifications from sensors. The OGC standards ensure interoperability and they are fundamental to developing sensor observation and monitoring services in a cost-effective and sustainable manner.

Several such services are deployed operationally in systems such as the Advanced Fire Information System (AFIS) and the Safe Waters Earth Observation System (SWEOS SRP), and more are being developed for, for example, the Acid Mine Drainage (AMD) SRP. A GIS-based information platform is being developed for the AMD SRP which will include a monitoring and alerting capability (in part developed for water quality sensors) and a time series visualisation component.  Such components fit naturally into the WSF ICT platform. Particular contributions would include rapidly deployable operational Sensor Observation Services and Web Feature Services for water chemistry sensors. Open standards based monitoring and alerting services will be implemented for near real-time (e.g., hourly) data streams.

# 2.  Proposal

The Meraka Institute proposes to contribute to the WSF as follows.

- Alert and Notification Subsystem: Collaboratively implement the dissemination component of a water quality monitoring system currently developed by the CSIR Analytical Services unit (CAS). The Wide Area Alerting System (WAAS) will be deployed to disseminate notification and alert messages through selected communications channels. This technology can be deployed operationally within two months from the start of project activities.

- Integrated Platform: Design and implement an open standards, integrated Water Resources Information System - an ICT platform that provides ready access to water data and seamlessly links information production (research) and information consumption (planning and decision making). Open source sensory data provisioning services (implementations of Open Geospatial Consortium standardised web services), a monitoring and alerting system (the Wide Area Alerting System), and a research platform that integrates EO and domain data are readily available technologies relevant to the WSF.

Figure 1 shows a high level conceptual architecture of the proposed system. The explicit objective is to avoid ‘stove pipe’ implementations and support the development of the integrated solutions (thus a contribution to Implementation Area 4). The platform will be open standards compliant and, as far as practicable, open source with the core technology components already developed as described above. Additional components can be rapidly developed and deployed operationally.

Figure 1: High-level conceptual architecture of the Integrated Water Resources Information System

The platform enables the proactive development of environmentally sustainable responses and planning decisions to water resource challenges. The following functional requirements are integrated from end-to-end:

- Ingest water data via diverse types of sensors, including remote and in-situ;

- Collate water information and services from custodians;

- Support the analyses of water consumption and availability using models and incorporating analytical and modelling tools (e.g., UrbanSim);

- Disseminate timely information to stakeholders through standardised services and interfaces

The high level architectural modules comprise as follows:

- A Sensor Hardware Layer that provides measurements and observations in a standards complaint format ranging from in-situ water quality sensors to remote sensing satellite data sources.

- The Middleware Layer provides the means to archive sensor observations and to provide access to other data archives on various, distributed databases and file systems through standardised services and interfaces. Water quality simulation and evaluation models are also maintained at this level.

- The Integration and Analysis Layer hosts software tools for processing and analytics, workflows that process observations, some of which may be long-running to monitor anomalous events, as well as orchestration modules that trigger sequences of processing activities on the occurrence of certain events or combinations of events.

- The Dissemination Layer incorporates the Wide Area Alerting System providing alerts and notifications to subscribed clients, “dashboard” functionalities for visualisation (mapping etc) and the provision of data sets at standardised interfaces for incorporation into client applications.

## 2.1  Implementation

System development and deployment will be needs driven, i.e., will be developed through close interaction with partners and users. Compliance in interoperability will be supported through the adoption of open standards for data encoding, information models, services and interfaces. An iterative specification-implementation cycle will be followed: in the first year of development, the identified use case of near-real-time monitoring and evaluation will be addressed.  The system will be extended to more sensors and a wider area of coverage in subsequent years. More advanced applications include user formulated queries, data transformations and simulations that support e.g., urban planning in terms of both water quality and quantity.

Year 1

WAAS deployment: The Alert and Notification subsystem will be implemented in the first year of development; the design and development of the integrated platform will commence with PG co-investment with more advanced implementations in the following years. The implementation time frame for the core infrastructure is 8 months, with a fully operational core platform in 12 months. Spatial and aspatial water data will be represented in compliance with open standards encodings (WaterML 2.0). Open standards (OGC compliant) services will be developed to expose data from water quality sensors in an interoperable manner.

Platform architecture: Concurrently, an end-to-end platform will be designed that complies with open standards and incorporates and supplement existing non-compliant water data provisioning components.

Core platform: The integrated platform will host these services and the process chains that monitor and identify anomalous events registered by water quality sensors (based on the technologies implemented for the Advanced Fire Information System). The Wide Area Alerting System (WAAS) will be deployed as part of this platform to disseminate alert notifications to users for evaluation.

Years 2 and 3

Implementation in years 2 and 3 entail the following

Refinement and expansion: The monitoring and evaluation process chain will be extended to 20 or more sensors as they are deployed in other areas.

Platform migration:  The system will be migrated to an open standards and open source architecture. Where required, systems will run in parallel until with controlled phase-over of the existing components.

Integration and simulation environment: Other water data sources and models will be integrated into the platform: Open source applications (such as UrbanSim) will be incorporated in a modelling and analysis environment that enables the creation of workflows for simulation and analysis of human settlement and water consumption dynamics

Robust sensor networks: Communications hardware, protocols and services will be implemented to enable the deployment of sensors in locations with unreliable or no power sources or poor digital communications infrastructure.

## 2.2 Schedule of tasks

The following table lists the task implementation time line, together with existing technologies to be implemented, deliverables and outputs. Individual tasks are described separately in greater detail.

| Months | Task number: Activity/Description |  | Technology (TRL): Deliverable |
| --- | --- | --- | --- |
| Year 1 |  |  |  |
| 01 – 06 | E1.1 Incorporate Wide Area Alerting System in existing CAS proposed system | WAAS (7): System able to send SMS messages to subscribed users |  |
| 04 – 06 | E1.2 Specify first level system architecture | Architecture specification report |  |
| 07 – 09 | E1.3 Monitoring system and integrated platform core infrastructure | EO4Vistrails (46): Open source geospatial data base, feeder modules, sensor services and interfaces implemented |  |
| 09 – 12 | E1.4 Operational integrated platform for monitoring and alerting | Validated web interface dashboard with alerting services |  |
| Year 2 |  |  |  |
| 13 – 18 | E2.1 Data series viewing functionality and subscription services; 20 sensor/probe inputs | TSV (5 6): Time series viewer implemented; system expanded to accommodate 20 sensors |  |
| 13 – 24 | E2.2 Foraging cognitive radio communication infrastructure | Wireless broadband device and ability to acquire alternative energy sources |  |
| 19 – 30 | E2.3 Implement fully integrated platform | Functional analytical environment implemented and deployed |  |
| 13 – 30 | E2.4 Modelling and analysis workflow environment | EO4V (6): Simulation and evaluation component integration completed |  |
| Year 3 |  |  |  |
| 24 – 32 | E3.1 integrated simulation models and data sources; Extension to further applications | EO4V (4 7): EO4Vistrails with analytical software implemented |  |
| 31 – 36 | E3.2 Advanced water quality and quantity modelling and evaluation applications | System extended to other applications (e.g. Blue drop) |  |

Table 1: Task implementation schedule

Much of the Year 1 activities above align with and contribute to Tasks and Deliverables specified in the Governance component of the overall proposal; in particular, Deliverables D2 (Implement integrated platform for simulations, options and decisions) and D3 (Consolidate and select intervention options, Task T3.1).

# 3.  Resources

## 3.1  Budget

The budgeted costs (Table 1) are for the human resources only; Running costs are detailed separately for each Task. PG funding will be co-invested in the development of the Integrated Platform.

| Activity/Task | Year 1 (ZAR) | Year 2 (ZAR) | Year 3 (ZAR) |
| --- | --- | --- | --- |
| [3.2] E1.1: Integrate dissemination (alerting notification) subsystem bases on WAAS* | 70 200 |  |  |
| [3.3] E1.2: Design end-to-end integrated platform | 90 675 |  |  |
| [3.10] E1.3 Implement near real time monitoring and simulation environment core infrastructure | 290 700 |  |  |
| [3.11] E1.4 Implement and migrate system to integrated platform | 369 900 |  |  |
| E2.1 Expand system to 20 geo-located sensors |  | 311 700 |  |
| E2.2 Foraging cognitive radio communication infrastructure |  | 1 068 267 | 534 133 |
| E2.3 Implement fully integrated platform |  | 546 900 | 372 900 |
| E2.4 Implement workflow modelling environment |  | 420 675 | 582 225 |
| E3.1 Fully integrated simulation environment |  |  | 926 100 |
| E3.2 Implement advanced applications |  |  | 821 100 |
| E3.3 Power saving for remote sensors |  | 635 000 |  |
| Total | 820 475 | 2 981 867 | 3 234 233 |

Table 2: Yearly budget (*These figures exclude amounts budgeted for these tasks in the Governance section)

Figures in Table 1 include the amount of R500 000 budgeted in Section 3 of the Governance component of the proposal. An amount of R160 000 PG funding will be co-invested in the first year, and further PG funds will be budgeted in subsequent years.  The following relevant projects provide complimentary funding.

| Project name | Budget (ZAR) |
| --- | --- |
| SWEOS (Safe Waters Earth Observation System) | 330 000 |
| Acid Mine Drainage (AMD) project | 1 432 000 |
| FP7 EO2HEAVEN (Earth Observation and the Mitigation of Health Risks) | 4 040 855 |
| EO2HEAVEN DST co-investment | 1 219 250 |

The SWEOS and AMD projects include the development of the same technologies as proposed here. EO2HEAVEN entails the development of models and technologies in support of the mitigation of water-borne health risks.

# Appendix D1

Existing technologies useful for the WSF

### A.1  Open Standards Compliant Sensor Web Services

Open standards (Open Geospatial Consortium) compliant services for sensor data ensure interoperability and are key to developing sensor observation and monitoring services in a cost-effective and sustainable manner. Several such services are deployed operationally in systems such as the Advanced Fire Information System (AFIS) and the Safe Waters Earth Observation System (SWEOS SRP), and more are developed for, for example, the Acid Mine Drainage (AMD SRP).

### A.2  Wide Area Alerting System

The Wide Area Alerting System (WAAS) is a TRL level 7 ICT platform that generates and disseminates data and information derived from data originating from heterogeneous sensors, models and/or monitoring processes, over multiple digital communications channels. Again, AFIS, is one example where this technology have been applied very successfully. The system facilitates

  - Ease of Administration; manage user subscriptions individually or group wise;

  - Flexibility; handles data about heterogeneous phenomena from different sensors;

  - Allow complex alert conditions to be configured – e.g. combine several phenomena but filter them by attributes, spatial location and time;

  - Extensible – easy to re-use system in different scenarios;

  - Scalable – handles observation/notification configurations in the order of hundreds of thousands, for thousands of users

  - Support for multiple notification channels, principally SMS, Internet and E-mail, and also via Instant Messaging, even radio.

### A.3  Earth Observation water quality monitoring and mapping

An sensor observation and monitoring system has been developed as part of the Safe Water Earth Observation System (SWEOS) that ingests MERIS and MODIS sensor data at 300 – 500m resolution. The system provides maps of eutrophication and cyanobacterial indices, water clarity and other for water quality products for approximately 250 major dams in South Africa. The following figure shows examples for some local dams. This technology is at TRL 7.

### A.4  EO4Vistrails

EO4VisTrails is an open-source scientific workflow and provenance management system based on Vistrails. VisTrails was designed to manage repeatable, rapidly-evolving different, but related, workflows created interactively. A key feature of VisTrails is its comprehensive provenance infrastructure that maintains a detailed history information about the processes, data and derived data products (history tree) produced during their executions. Figure 2 shows an example of the workflow history tree, a workflow (far top right) and the visual outputs produced (bottom).

The EO4Vistrails environment provides a platform to leverage sensor data resources together with analytical tools for simulations, data exploration and visualization. Scientific workflows are used to develop and robustly execute applications that are exploratory and dynamic in nature. Examples of such applications are near-real-time and long-running observation and monitoring processes. Spatio temporal processing often utilises large datasets requiring extensive CPU and memory resources in their processing. Other features currently implemented in EO4Vostrails include open standards compliant services and interfaces for accessing spatio temporal data resources and models as well as statistical analysis and visualisation tools to process, transform and render information.

Figure: Example of Vistrails application

### A.4  Minimum maintenance, autonomous and robust wireless networks for monitoring water conditions

This contribution includes a set of components permitting to establish a long-life power-efficient self-configuring wireless sensor network. The key features are:

- Minimum maintenance, long life and power efficiency

- Robust and able to re-route information, e.g. in case of a fault

- Autonomous; having the capability to operate on its own in a remote/inaccessible area

- Throughput, security; directed beam offers lower interference and lower probability of intercept

### A.5  Ultra-power-efficient array antenna to improve operation/life time of low power sensor nodes

An antenna able to have a narrow focussed beam pointing towards the desired receiver may help to save power. Estimates show that, for low power nodes, it is possible to improve the life/operation time by factor of ~5X, compared to single omni-directional antenna.

Envisioned applications: mass market or devices requiring long autonomous operation on batteries

Current status: theory, a prototype, measured low power consumption

Development required: 6-8 months (increase antenna gain and reduce antenna’s size)

### A.6  Algorithm development for localization / self-position-determination (without GPS, also minimizing the power consumption)

Many applications require the knowledge of its node’s geo-spatial position within the network. Some applications require lower cost devices, some others (e.g. underground mining) simply cannot receive GPS signal. This contribution offers algorithms capable of reliable determination of the position (localization) using wireless metrics free of GPS.

Envisioned applications: wireless sensor networks, underground mining

Current status: algorithms tested in wireless network simulator and showing superior performance (also resulted in PhD)

Development required: 6-18 months, depending on the requirements (inputs, mobility etc.)

### A.7  Wireless mesh networking device and routing algorithms for mesh networking

In many applications, it is necessary to be able to set up a network providing reliable services and capable of self-configuration and self-healing. The mesh networks with their peer-to-peer routing based connectivity do exactly that.

Envisioned applications: wireless sensor networks, underground mining

Current status: being manufactured and installed in South Africa to connect rural schools (over 200 installations), supports 2.4 GHz and 5.8 GHz frequency bands

Development required: adaptation to the specific requirements may be required

### 2.8  Foraging cognitive radio architecture (FOCORA) for broadband information relay over long distance in remote areas.

The architecture is developed into commodity wireless routers and it is a software that combines the functionality of wireless green and TV white space networking capabilities. The main features are that: the wireless network can transport broadband services (a converged voice, data, and video) information over long distance connectivity using spectrum band ~80MHz-1GHz of unused TV spectrum in most South African rural areas and optimised transmission power levels in energy-constrained application. It is anticipated that the FOCORA will relay green water information situated remotely to the water treatment plants as well as to water quality decision making organs in real time. In this framework architecture, wireless sensors, underwater sensors, underground sensors are deployed in water catchment areas and the FOCORA routers form back-haul links that connect the gathered data to the treatment plants and decision organs.

Envisioned applications: wireless back-haul for broadband applications

Current status: optimal transmission power control algorithm has been severally tested via simulations. Prototype development in wireless Mesh Lab is ongoing. Cognitive radio test-bed via USRP equipment has been demonstrated.

Development required: 12 to 18 months of FOCORA firmware development and real-life application.

Figure 1: Applications of self-configured FOCORA networking for broadband services relay

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Expand system to 20 sensors |  |  |  |  |  |  |  | Task Ref. Number: E2.1 |  |  |  |  |
| Description: Near real-time monitoring system is expanded to monitor at least 20 more water quality sensors |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 369900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 120 |  | 77400 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 40 |  | 35400 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 180 |  | 116100 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 311700 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 04/05/2012 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Foraging cognitive radio (FOCORA) communication infrastructure |  |  |  |  |  |  |  | Task Ref. Number: E2.2 |  |  |  |  |
| Description: It is a sustainable broadband based wireless backhaul communication infrastructure for Water quality data transport between water catchment areas, treatment stations, decision making points and usage points. It is characterized by ability to forage energy freely from the environment and opportunistically perform spectrum management of TV white spaces |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Thomas Olwal, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | Yr2 Mnth 01 |  | Payment details: |  | The WSF Project contribution is envisaged to take 12 months effective Approval of funds. |  |  |  |  |  |  |
|  |  | Yr3 Mnth 18 |  |  |  |  |  |  |  |  |  |  |
|  |  | 1602400 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: +wireless broadband communication device. +Ability to acquire alternative energy sources and transmit with optimal energy +Ability to scan TV white spaces and use spectrum judiciously +Software defined radios ability |  |  |  |  | Critical predecessor tasks: +optimal transmission energy been tested. +Cognitive radio TV white space trails are ongoing. +Spectrum monitoring platform has been implemented. |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost |  | Running |  | Notes for running costs |  |  | Capital |
| Fisseha Mekuria |  | 1170 | 360 |  | 421 200 |  | 45 000 |  | Field travels |  |  | 466 200 |
| Thomas Olwal |  | 765 | 720 |  | 550 800 |  | 55 000 |  | Field travels |  |  | 605 800 |
| Moshe Masonta |  | 570 | 720 |  | 410 400 |  | 55 000 |  | Field travels |  |  | 465 400 |
| Experimental equipment |  | 12000 | 5 |  | 00 |  | 60 000 |  | USRP+ Antennas |  |  | 60 000 |
| Sensors |  | 1000 | 5 |  | 00 |  | 5 000 |  | Multi-purpose sensors |  |  | 5 000 |
| Totals: |  |  |  |  | 1382400 |  | 220000 |  |  |  |  | 1602400 |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |
| Assumptions, Risk Factors & Contingencies: Assumption: multipurpose sensors exist off-the-shelves in local markets and no need to order overseas for highly specialised sensor types. Risks: Technical complexity, there is likelihood that equipment assembly might be complex causing a possible delay of the experimental deliverables. Contingencies: The system will utilise SDR approach to minimise Hardware complexities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Implement fully integrated platform |  |  |  |  |  |  |  | Task Ref. Number: E2.3 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 919800 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 300 |  | 207000 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 200 |  | 129000 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 200 |  | 177000 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 480 |  | 309600 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 80 |  | 97200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 919800 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Workflow modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E2.4 |  |  |  |  |
| Description: EO4VisTrails implemented for simulation and modelling environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 30 Sep 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 1002900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 420 |  | 289800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 180 |  | 116100 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 160 |  | 141600 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 480 |  | 309600 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 120 |  | 145800 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 1002900 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Operational version of modelling and simulation environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Fully integrated simulation and modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E3.1 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment, data sources and extension to further applications |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2014 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2015 |  |  |  |  |  |  |  |  |  |  |
|  |  | 926100 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 360 |  | 248400 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 240 |  | 154800 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 120 |  | 106200 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 420 |  | 270900 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 120 |  | 145800 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 926100 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Fully integrated platform including data sources and further applications (eg UrbanSim) |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Fully integrated simulation and modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E3.2 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment, data sources and extension to further applications |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2014 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2015 |  |  |  |  |  |  |  |  |  |  |
|  |  | 821100 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 360 |  | 248400 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 240 |  | 154800 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 100 |  | 88500 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 360 |  | 232200 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 80 |  | 97200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 821100 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Advanced applications including water quantity and other water quality aspects |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-25 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Power saving for remote sensors |  |  |  |  |  |  |  | Task Ref. Number: E3.3 |  |  |  |  |
| Description: Adaptation of the technology to the wireless sensor [network] nodes, permitting to increase the device longevity by up to 4-5 times. |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Albert Lysko, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | Yr2, Mnth 01 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | Yr2, Mnth 12 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Host device (wireless sensor mote) - Environmental and casing requirements - Access to software on the device and network of devices |  |  |  |  | Critical predecessor tasks: - The host device (wireless sensor mote) must be able to function standalone - Network topology/config. well have been defined |  |  |  |  |  |  |  |
| Resources |  | Unit cost R/hour | Units |  | HR Cost |  | Running |  |  | Notes for running costs |  | Capital |
| Albert Lysko |  | 885 | 560 |  | 459,600 |  | 50,000 |  |  | manufacturing |  |  |
| Sensor device’s owner unit |  | 1000 | 140 |  | 140,000 |  | 12,000 |  |  | Fitting into existing device |  |  |
| Totals: |  |  |  |  | 635,600 |  | 62,000 |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
| Assumptions, Risk Factors & Contingencies: It is assumed: 1) the sensor device exists and already works with a traditional antenna, 2) the software running on the wireless node is open for access, 3) there is no need to design a custom enclosure (i.e. it is possible to fit the antenna into the existing device or to find a suitable commercially available enclosure). Contingencies to (3): (i) design time for the enclosure (~R100K?) and (ii) more running needed (~R50K per iteration X 2-3 iterations). |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

For application in this context

R730k contingency is also available as part of the contingency pool

National Freshwater Ecosystem Priority Areas

Urban Growth Simulation Platform

Geo-Spatial Analysis Platform

Spatial and Temporal Evidence for Planning in South Africa

Assessment of Considerations for Water Use Allocations

Ecology (to) Economy Model

Water Sector Institutional Landscape Scenarios

Unit PG

http://code.google.com/p/eo4vistrails/

http://www.vistrails.org/index.php/Main_Page#VisTrails_Overview