DRAFT 3: (05-05-2012)

Contents

THE OBJECTS OF THE CSIR	3

CSIR CEO AND PRESIDENT DR SIBUSISO SIBISI ON THE WATER SUSTAINABILITY FLAGSHIP	3

EXECUTIVE SUMMARY	4

1.0	FLAGSHIP SCOPE AND PROBLEM STATEMENT	8

2.0	OBJECTIVES AND GOALS	15

3.0	EXPECTED RESULTS	16

4.0	APPROACH	17

5.0	THE PROJECT DESCRIPTION	18

6.0	COMPONENTS OF THE INTEGRATED SOLUTION	21

7.0	PROJECT DETAIL	22

8.0	FINANCIALS	23

9.0`RISK ASSESSMENT	24

10.0	STAKEHOLDER ENGAGEMENT	25

11.0	PROPOSED WSF GOVERNANCE STRUCTURE	26

REFERENCES	27

APPENDIX A: INTERVENTION AREA 1	28

APPENDIX B: INTERVENTION AREA 2	42

APPENDIX C: INTERVENTION AREA 3	58

APPENDIX D: ICT AS A CROSS-CUTTER:	83

APPENDIX E: MEASURABLES, BUDGET, GANTT AND CASH-FLOW	102

APPENDIX F: LOGFRAME WITH DELIVERABLES FOR STAGE-GATE ASSESSMENT (Year 1)	111

THE OBJECTS OF THE CSIR

The Council for Scientific and Industrial Research (CSIR) was established on 5 October 1945.

The CSIR's mandate is as stipulated in the Scientific Research Council Act (Act 46 of 1988, as amended by Act 71 of 1990), section 3: Objects of CSIR:

"The objects of the CSIR are, through directed and particularly multi-disciplinary research and technological innovation, to foster, in the national interest and in fields which in its opinion should receive preference, industrial and scientific development, either by itself or in co-operation with principals from the private or public sectors, and thereby to contribute to the improvement of the quality of life of the people of the Republic, and to perform any other functions that may be assigned to the CSIR by or under this Act."

www.csir.co.za

CSIR CEO AND PRESIDENT DR SIBUSISO SIBISI ON THE WATER SUSTAINABILITY FLAGSHIP

‘Flagship programmes are large, integrated development and innovation endeavours.  They are seen as delivery and implementation programmes, are impact-driven, with objectives that can be achieved in a set time.

The CSIR’s multidisciplinary nature perfectly positions the organisation to intervene in the area of water sustainability, where many of our competences can be applied in the areas of water infrastructure; water resource management; adaption to and mitigation of climate change, industrialisation and urbanisation; water and human health; mine, industrial and waste water treatment; and water quality monitoring.’

EXECUTIVE SUMMARY

Available information indicate that large areas in South Africa experience ‘water stress’ and this situation is likely to continue in future. There are escalating demands for water from a growing population and expanding economy.

The disparity in service delivery provides many challenges associated with the requirement to address this and water is needed to ensure food security and energy security. There is a worsening of water quality in many rivers with a deterioration of reservoirs and ecosystems and especially rural communities face growing risks of water shortages and the health impacts of contamination.

Given the situation, problems and associated implications described above, the CSIR’s Water Sustainability Flagship (WSF) as indicated above, provides a mechanism to focus the organization’s capabilities and invite collaboration from strategic partners in contributing to solving the country’s water challenges. This provides an opportunity to give effect to the outputs from the CSIR’s R&D activities done under for example the Research Impact Areas (RIAs).

As depicted above, two parallel intervention processes are being followed, namely (1) a short-term approach focused on the water quality and efficiency components at Waste Water Treatment Works where the results should be realised within 1 to 2 years, and (2) the bigger picture where water quantity, quality and treatment efficiency at water basin scale are addressed and results realised within 3 to 5 years.

Since the intention of the CSIR Flagship initiative is to develop and implement current CSIR Technology Demonstrators (TRL 5 and above) to at least pilot scale (TRL 7 and above), a process was followed to identify suitable TRL 5+ products within CSIR that aligned with and addressed the needs within the identified Intervention Areas.

The essence (or overall objective) of the WSF is “to contribute to the equitable, efficient and sustainable use of water to ensure that South Africa attains its national and economic growth and development aspirations.” The expectation is that, through the WSF, products of research and technological/knowledge development produced by the CSIR will be further developed for implementation within a relatively short time frame and that these will have a positive/noticeable impact on the economy and society.

The failure of waste water treatment works at municipal level is being taken seriously by the relevant authorities. The DWA recently announced that the cost of addressing the problem is in the order of R500Billion. Taking a 1% (R50billion) as the market potential for the CSIR packaged solution, the risk of delays in packaging the technologies for role out is significant.

As reflected in the Logic Model adapted from RAND (www.rand.org) in the figure below, the anticipated output of the WSF is therefore to move beyond simply providing evidence in support of decision-making to a suite of practical and sustainable tools and technologies to assist practitioners and decision makers in the water sector.

Here the objective statement and underpinning strategic programme outcomes are used as the starting points. These reflect the WSF Focus Areas as discussed above.

To realise the desired impact some change has to be induced in the way the targeted stakeholder groupings address their mandated responsibilities. For the WSF these are defined as Intermediate Outcomes reflected in the second column from the right.

The key aspects of the WSF is seen to be the fact that the D & I activities are packaged as an integrated solution aimed at national and even regional replication. The innovation therefore lies in:

An integrated , multi-disciplinary solution, piloted in an Urban and Peri-urban environment that includes a predictive ability to provide current and future scenario-based insight into the quantity and composition of the effluent stream entering the waste water treatment system.

The focus on increasing the longevity of aging WWT plants by rehabilitating and upgrading the Anaerobic Digester component that leads to compliance of the solid waste stream, an energy cost reduction via biogas production and the value add (and associated job creation) of producing safe compost for sale and use in community gardens.

An efficient low cost integrated near real-time 1st level water quality monitoring system that allows for timely compliance evaluation and response at key nodes within the whole system to influence the Green Drop status of targeted municipalities.

As detailed in Appendix E, the WSF is a collaborative project that brings together researchers from across the CSIR and the private sector.

The detailed cashflow from the WSF fund for the first year of the integrated project is shown in Appendix E and summarised in the table below. The PG and Other funding is shown in the table in Appendix E

|  | May ‘12 | June | July | Aug | Sept | Oct | Nov | Dec | Jan ’13 | Feb | Mrch |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IA1 | 425 | 400 | 625 | 700 | 825 | 900 | 1011 | 325 | 650 | 564 | 75 |
| IA2 | 290 | 275 | 255 | 325 | 940 | 1025 | 1050 | 1165 | 325 | 400 | 250 |
| IA3 | 495 | 1274 | 1159 | 1289 | 1079 | 1064 | 1174 | 1124 | 1169 | 1184 | 1064 |
| Coord | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 240 |
| Cont Pool1 | 700 |  |  | 700 |  |  | 700 |  |  | 785 |  |
| TOTAL | 2110 | 2149 | 2239 | 3214 | 3044 | 3189 | 4135 | 2814 | 2344 | 3133 | 1629 |

Note 1: The Contingency Pool is a shared reserve to be managed by the Project Coordination Team to cover unforeseen expenses

A stage-gate assessment approach is proposed with the Logframe (Appendix F) forming the basis for regular progress assessments

1.0	FLAGSHIP SCOPE AND PROBLEM STATEMENT

Water challenges in South Africa are well known and documented (e.g. DEAT, 2006; 2030 Water Resources Group, 2009; CSIR, 2010; DWA, 2011). The most significant challenges include increasing water scarcity, poor and ageing infrastructure, skills and capacity shortages in the water sector, increasing pollution, failure to meet environmental flow requirements, poor enforcement of regulations and potential impacts of a changing climate.

Given that water is a crucial, cross-sectoral input for all development and growth, its availability (and quality) will be a limiting factor across the country. Many initiatives to address these challenges have been taken up in the different sectors, though these have been fragmented and isolated often resulting in ineffective solutions at the national level. These include (1) The Department of Water Affairs (DWA) Water for Growth and Development (WfGD) Framework (January 2009) and (2) the (draft) DWA National Water Resources Strategy (NWRS II) (DWA, 2011)

The WfGD represents DWA’s strategic turnaround approach in managing the country’s water more effectively and efficiently in order to enhance economic and development goals as well as to respond to concerns raised regarding the state of water in the country over the past two years. These concerns include that South Africa will experience severe water shortages by 2025; Gauteng will run out of water in 2013; the state of South Africa’s water resources infrastructure (i.e. dams) is in a poor condition; South Africa’s rivers are severely polluted; and that municipal infrastructure (in particular waste water treatment plants) are failing, the latter having an added effect on the state of the rivers. A further concern highlighted is the lack of skills and capacity at various technical and managerial levels within the water sector.The WfGD Framework is responsive to the needs of various economic sectors and points to the relationship between water availability and the forms of economic activity that are dependent on available water supply of varying levels of quantity and quality depending on the technologies being used.

The (draft) National Water Resources Strategy (NWRS II) (DWA, 2011), identifies four challenges in the water perspective for South Africa, namely (1) Water underpins the socio-economic development of SA, (2) water resources in SA are limited and under stress, (3) SA’s future depends on timely resource planning, and (4) SA strives to be a responsible neighbour and global player. It lists three main water concerns which are associated with three of the challenges. These are:  (A) decreasing water security; (B) deterioration of ecosystems; and (C) deterioration of water & wastewater infrastructure.

In September 2008 the Minister of Water Affairs introduced a regulatory approach that has gained significant momentum as an Incentive-based Regulation. Two programmes, the Blue Drop Certification Programme for Drinking Water Quality Management Regulation and the Green Drop Certification Programme for Wastewater Quality Management Regulation define the concept.

The Green Drop process measures and compares the results of the performance of Water Service Authorities and their providers, and subsequently rewards (or penalises) the municipality upon evidence of their excellence (or failures) according to the minimum standards or requirements as defined. Awareness of this performance is obtained by pressure through the customers, the media, political classes and NGOs. The strategy revolves around the identification of mediocre performing municipalities who consequently correct the identified shortcomings, as well as the introduction of competitiveness amongst the municipalities and using benchmarking in a market where competition is difficult to implement.

Water Quality

A key conclusion from the Green Drop Certification Programme showed that many of South Africa’s waste water collection and treatment systems are failing. This impacts directly onto the water quality in the water resource system.

Waste water treatment occurs via one or more natural systems (i.e. wetlands, natural side-channel vegetation, sand or soil filters and in-stream reedbed systems), the so-called ecosystem services. Man-made waste water treatment works take on many forms with the conventional municipal works typically consisting of a combination of components including anaerobic digester technology.

The 2011 Green Drop Report (DWA, 2011) shows that the Green Drop Certification programme of 2010/11 verified the status of wastewater service delivery by hundred and fifty-six (156) municipalities that provide services via an infrastructure network comprising of 821 wastewater collector and treatment systems. Statistics taken from the DWA, (2011) report are summarised in the figure below and show that a significant number of the waste water collector and treatment systems did not reach the compliance threshold of above 50%. The Free State, Northern Cape and Limpopo Provinces have the largest challenges.

Green Drop Status: Water and waste treatment during 2010 – 2011

http://www.ewisa.co.za/misc/BLUE_GREENDROPREPORT/GreenDrop2011.htm

The Cumulative Risk Rating (CRR) included in the report provides a risk analysis that focuses on the wastewater treatment function specifically. It provides insight into the treatment component of the total municipal waste water management value chain. This component is one of the high risk components within the production chain and allows the municipality to identify and prioritise the critical risk areas within its wastewater treatment process and to take corrective measures to abate these. The results for 2011 show that the biggest deviation from the maximum value (CRRmax) that the deviation can reach occurs in the Free State, Limpopo and Eastern Cape Provinces with deviation values of 83%, 79% and 78% respectively. The deviation limits that define a critical state are in the range (90-100%).

Water Quantity

An indication of the quantity of water available from a specific river basin to the dependent population is reflected as the Water Crowding Index (WCI). The idea that water security or, conversely, vulnerability to variability and limitations in water supply could be expressed in a simple index was pioneered by Dr Malin Falkenmark (1997). It has been used by the Millennium Ecosystem Assessment (2005) report as one measure of human well-being in relation to water resources. Ashton et al. (2008) applied it in an analysis of the available water resources in transboundary river basins and showed its usefulness as a Monitoring and Evaluation indicator as illustrated in the table below.

The information shows that the Limpopo river basin is one of the critical systems where the WCI exceeds the accepted international threshold of 1000 people per million cubic metres of available water (Ashton et al., 2008)

Water Crowding Index for four transboundary river systems

Available statistics show that of the 19 South African river basins, 5 water systems far exceed the threshold, 7 systems are approaching the threshold and 7 are below the threshold.

In 2010 the CSIR published a document ‘that summarises the many issues related to water resource management in South Africa, providing the CSIR perspective. http://www.csir.co.za/nre/docs/CSIR%20Perspective%20on%20Water_2010.PDF

Conclusion

The available information therefore indicates that large areas in South Africa experience ‘water stress’ and this situation is likely to continue in future. There are escalating demands for water from a growing population and expanding economy.

The disparity in service delivery provides many challenges associated with the requirement to address this and water is needed to ensure food security and energy security. There is a worsening of water quality in many rivers with a deterioration of reservoirs and ecosystems and especially rural communities face growing risks of water shortages and the health impacts of contamination.

Water quality problems in the Olifants River Basin

As indicated by the Green Drop Report (DWA 2011) and in particular the Cumulative Risk Rating (CRR) assessment, the failure of many urban, peri-urban and rural waste water treatment plants poses a real health threat to downstream populations as well as the functioning of natural resource systems. The figure below depicts the main components of the system and their logical linkages within which the waste water treatment plant forms the central point.

The schematic below is a simplified version of the wider system depicted above within which the problem occurs.

As shown in the figure above, the systems analysis reflects three logical clusters of interlinked ‘Intervention Areas’, each with an associated focusing problem statement defined below:

Planning and Governance in relation to Waste Water Treatment Works

Associated problem statement:

Inadequate strategic, integrated and cooperative governance and planning for water sustainability constrains equitable access as well as sustainable and inclusive development.

Solid waste/sludge treatment & management

Associated problem statement:

Failing sewage treatment works impact on people’s health and water resources.

(Near) real-time monitoring system for Waste Water Treatment Works

Associated problem statement:

The lack of (near) real-time system performance information hampers effective and efficient response

2.0	OBJECTIVES AND GOALS

Given the situation, problems and associated implications described above, the CSIR’s Water Sustainability Flagship (WSF) provides a mechanism to focus the organization’s capabilities and invite collaboration from strategic partners in contributing to solving the country’s water challenges. This provides an opportunity to give effect to the outputs from the CSIR’s R&D activities done under for example the Research Impact Areas (RIAs).

The essence (or overall objective) of the WSF is “to contribute to the equitable, efficient and sustainable use of water to ensure that South Africa attains its national and economic growth and development aspirations.”

The expectation is that, through the WSF, products of research and technological/knowledge development produced by the CSIR will be further developed for implementation within a relatively short time frame and that these will have a positive/noticeable impact on the economy and society.

As reflected in the Logic Model adapted from RAND (www.rand.org) in the figure below, the anticipated output of the WSF is therefore to move beyond simply providing evidence in support of decision-making to a suite of practical and sustainable tools and technologies to assist practitioners and decision makers in the water sector.

Here the objective statement and underpinning strategic programme outcomes are used as the starting points. These reflect the WSF Focus Areas as discussed above.

To realise the desired impact some change has to be induced in the way the targeted stakeholder groupings address their mandated responsibilities. For the WSF these are defined as Intermediate Outcomes reflected in the second column from the right.

The Outputs of the Development and Implementation (D & I) activities carried out under the WSF are depicted in the central two columns demarcated by the dotted line in the Logic Model diagramme above. Technologies (or ‘tools’) developed by the CSIR that are at a Technology Readiness Level (TRL) above 5 form the basis for the ‘quick win’ D&I activities over the first 12 to 18 month period. As indicated, these activities can only be achieved through effective and efficient collaboration across the capabilities in CSIR and within its external network.

3.0	EXPECTED RESULTS

Although the final end users (or target population) are the ‘People of South Africa’, the various levels of government are mandated to act on behalf of their constituents and to ensure a healthy and safe environment and are therefore seen as the Intermediate Customers.

The South African Government has agreed on 12 outcomes as a key focus of service delivery work up to 2014. Each outcome has a limited number of measureable outputs with targets. For example, the Delivery Agreement for Outcome 10: Environmental Assets and Natural Resources that are valued protected and continually enhanced (www.environment.gov.za) has as Output 1 ‘Enhanced quality and quantity of water resources’ with sub-outputs of (1) water demand management, (2) water resource protection, and (3) regulation of water quality.

4.0	APPROACH

Two parallel intervention processes are being followed, namely (1) a short-term approach focused on the water quality and efficiency components at Waste Water Treatment Works where the results should be realised within 1 to 2 years, and (2) the bigger picture where water quantity, quality and treatment efficiency at water basin scale are addressed and results realised within 3 to 5 years.

Since the intention of the CSIR Flagship initiative is to develop and implement current CSIR Technology Demonstrators (TRL 5 and above) to at least pilot scale (TRL 7 and above), a process was followed to identify suitable TRL 5+ products within CSIR that aligned with and addressed the needs within the identified Intervention Areas.

The intervention plan is depicted in the summary figure below.

5.0	THE PROJECT DESCRIPTION

As described above, the key aspects of WSF is seen to be the fact that the D & I activities are packaged as an integrated solution aimed at national and even regional replication. The innovation therefore lies in:

An integrated , multi-disciplinary solution, piloted in an Urban and Peri-urban environment that includes a predictive ability to provide current and future scenario-based insight into the quantity and composition of the effluent stream entering the waste water treatment system.

The focus on increasing the longevity of aging WWT plants by rehabilitating and upgrading the Anaerobic Digester component that leads to compliance of the solid waste stream, an energy cost reduction via biogas production and the value add (and associated job creation) of producing safe compost for sale and use in community gardens.

An efficient low cost integrated near real-time 1st level water quality monitoring system that allows for timely compliance evaluation and response at key nodes within the whole system to influence the Green Drop status of targeted municipalities.

The following criteria were defined for selecting the pilot sites where the technology demonstration would be focused:

- Integrated solution (co-location)

- Local community-level need or high-risk water problem

- Representative of national scale problem

- Co-funding available from local sources

- Ease of access to the pilot area by CSIR teams

- Current CSIR initiatives underway (co-locate)

  - Good relationship with key stakeholders

  - Current externally funded complementary projects

The application of the selection criteria resulted in the definition of a single integrated experiment piloted in two complementary locations, namely:

- The ERWAT managed Olifantsfontein WWTW located within an Urban setting in the  upper Crocodile River catchment. The intervention would be focused on ‘Fit-for-use / purpose’ infrastructure improvement with a secondary aim for community job creation and household level impact via waste beneficiation and a community garden.

- The Sekhukhune District Municipality which is located in a  Peri-Urban setting in the Upper Olifants River catchment where the focus will be on Green Drop status improvement.

The pilot sites are shown in the figures below.

The Olifantsfontein Waste Water Treatment Works is located in an Urban environment in the Upper Crocodile River catchment

The Winnie Mandela Park community borders the Olifantsfontein WWTW, providing opportunities for job creation through waste beneficiation projects

6.0	COMPONENTS OF THE INTEGRATED SOLUTION

A number of CSIR technology demonstrators that are aligned with the proposed integrated solution were identified. Three core technologies were chosen as depicted in the figure below. They are all at TRL 5 or above. The technical detail, along with the activities associated with the development and implementation of each are described in Appendices A, B and C.

The implementation of the technologies requires collaboration amongst researchers from BE, NRE, CAS, MSM, MDS and Meraka.

7.0	PROJECT DETAIL

As discussed above, the first part of the WSF is focused on short-term (1 to 2 years) focused intervention followed by a medium term (3 to 5 Year) period where the packaged integrated solution will be expanded to catchment scale and more components of the system (e.g. the water quantity aspects) will be addressed.

The project plan, in the form of a Gantt Chart is shown below. The detailed technical plan and associated Task Detail sheets for Year 1 (2012/13) are shown in Appendix D. The work packages, resource allocations, milestones, deliverables, payment schedules and technical risk assessment for each of the Intervention Areas are all shown in the Task Detail Sheets for each of the work packages (or Intervention Areas.

Regular progress reviews will be held at specific stage-gates where Go, Redirect or Stop decisions will be made.

8.0	FINANCIALS

The indicative budget for the first three years is summarised in the figure above. The detailed breakdown of tasks and associated budget are provided in Appendices A, B, C and D with a summary provided in Appendix E. Task Detail Sheets are provided for each of the project tasks (those funded under the WSF, PG and from external sources) for the IAs.  A breakdown of the CSIR-PG co-funding associated with each of the Intervention Areas is shown in the table below.

|  | 2012/13 | 2013/14 | 2014/15 |
| --- | --- | --- | --- |
| IA 11 | 4.5 | 5 | 5 |
| IA 2 | 2 | 2 | 3 |
| IA 32 | 1.16 | 3 | 2 |
| TOTAL | 7.61 | 10 | 10 |

Note 1: Includes NRE, BE and Biosciences

Note 2: Includes MSM, MDS and Meraka

The detailed cashflow from the WSF fund for the first year of the integrated project is shown in Appendix E and summarised in the table below. The PG and Other funding is shown in the table in Appendix E

|  | May ‘12 | June | July | Aug | Sept | Oct | Nov | Dec | Jan ’13 | Feb | Mrch |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IA1 | 425 | 400 | 625 | 700 | 825 | 900 | 1011 | 325 | 650 | 564 | 75 |
| IA2 | 290 | 275 | 255 | 325 | 940 | 1025 | 1050 | 1165 | 325 | 400 | 250 |
| IA3 | 495 | 1274 | 1159 | 1289 | 1079 | 1064 | 1174 | 1124 | 1169 | 1184 | 1064 |
| Coord | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 240 |
| Cont Pool1 | 700 |  |  | 700 |  |  | 700 |  |  | 785 |  |
| TOTAL | 2110 | 2149 | 2239 | 3214 | 3044 | 3189 | 4135 | 2814 | 2344 | 3133 | 1629 |

Note 1: The Contingency Pool is a shared reserve to be managed by the Project Coordination Team to cover unforeseen expenses

9.0`RISK ASSESSMENT

The integrated solution is aimed at pre-competitive development and implementation of CSIR technology packages at TRL 5. Thus the solutions have been proven at laboratory scale. The risk therefore does exist in the scaling up the lab scale technologies to ‘real-life’ pilot scale. It is for this reason that both Urban and Peri-Urban settings were chosen for the pilots and where active collaboration with the user community is key.

A key component to mitigate this risk is the decision to implement scientifically designed experiments to ensure that the results are statistically defendable, whether positive or negative. This will directly inform the stage-gate project progress reviews.

As indicated in the figure below, the failure of waste water treatment works at municipal level is being taken seriously by the relevant authorities. The DWA recently announced that the cost of addressing the problem is in the order of R500Billion. Taking a 1% (R50billion) as the market potential for the CSIR packaged solution, the risk of delays in packaging the technologies for role out is significant. It is estimated that the spread of the source of funding is as indicated below.

10.0	STAKEHOLDER ENGAGEMENT

Initial and ongoing engagement with key stakeholders is taking place. A key stakeholder group is the  Water Sector Leadership Group (WSLG). This WSLG group is a well organized water networking grouping with membership from various institutions and sectors. All key sectors are represented on WSLG (Water, Environment,  Agriculture, Energy, Domestic, Industry; WISA, WRC and CSIR are also represented; these sectors range between both public, private spheres including organised NGOs) where DGs of key sector departments like DWA. DEA, DAFF, CoGTA, SALGA as well as senior staff from Eskom, SASOL, the CE's of Water Boards and relevant research institutions, NGOs Chamber of Mines, etc.) attend.

Regular  focused discussions with key stakeholder groups (DST, DWA, SALGA, ERWAT and Tshwane) as well as  the DWA and local municipalities in the Limpopo and Mpumalanga provinces have been initiated and will continue for the duration of the project. Key representatives of these bodies will be invited to serve on the WSF Reference group.

11.0	PROPOSED WSF GOVERNANCE STRUCTURE

As shown in the figure below, the size, multi- and interdisciplinary nature of the integrated solution warrants a dedicated project coordinating function that will oversee the three technical project management functions.

An option is to establish the Project Coordination Office (PCO) within the CSIR’s Strategic Initiatives Implementation Group (SIIG) with a possibility of a senior project coordinator being seconded to the PCO for a to be defined timeframe.

Of importance is the establishment of a independent Oversight Board with membership taken from the stakeholder reference group so-as to ensure market relevance and maximise the opportunities for user-driven uptake.

REFERENCES

2030 Water Resources Group, 2009. Charting Our Water Future: Economic frameworks to inform decision-making.

Ashton PJ; Hardwick D; Breen CM 2008. Changes in water availability and demand within South Africa's shared river basins as determinants of regional social and economical resilience. Exploring Sustainability Science: A Southern African Perspective, Pages: 279-310.

CSIR, 2010. A CSIR perspective on water in South Africa – 2010. Available at www.csir.co.za.

Department of Environmental Affairs (DEAT), 2006. State of Environment Outlook Report for 2006.

Department of Water Affairs (DWA), 2011. Water for Growth and Development in South Africa. Version 6.

Falkenmark, M., 1997: Society’s interaction with the water cycle: A conceptual framework for a more holistic approach, Hydrological Sciences Journal, 42, 451–66.

Falkenmark, M. and Folke, C. 2003: Theme issue: Freshwater and welfare fragility: Syndromes, vulnerabilities and challenges, Royal Society’s Philosophical Transactions B Biology, 358, p. 1440. (introduction to special issue on this topic)

Millennium Ecosystem Assessment, 2005. Ecosystems and Human Well-being: Synthesis. Island Press, Washington, DC.

APPENDIX A: INTERVENTION AREA 1

# Governance and Planning Component of Water Sustainability Flagship

Coordination: Dr Marius Claassen (NRE)

Brief

To achieve water quantity, quality & efficiency at basin level, specifically related to wastewater treatment works (WWTWs).

### 1. Activity/technology description

The Urban Growth Simulation Platform (UrbanSim) models spatially explicit patterns of urban growth over a 20-30 year period. The platform is ready for water specific applications in Nelson Mandela Bay, eThekwini, the City of Johannesburg and the Greater Gauteng City Region. Application of the simulation platform in the City of Cape Town and other secondary cities of South Africa would require concerted processes around data collation and preparation of approximately 6 months per study area. The Geo-Spatial Analysis Platform provides an analysis of spatial and temporal development trends at a regional scale to inform rigorous and robust debate amongst the various agencies of the state. The StepSA (Spatial and Temporal Evidence for Planning in South Africa) portal facilitates access to spatial and temporal evidence (incl. water related planning information) to support integrated and inter-governmental planning in South Africa.

Existing knowledge and technologies will be integrated into a spatial (GIS) based risk platform to assess, prioritise and mitigate the impact of WWTWs on ecosystem and human health. Decision support systems include the Assessment of Considerations for Water Use Allocations (ACWUA) Decision Support System (DSS), which utilizes a Bayesian engine to evaluate decisions based on multiple criteria, particularly where information related to the decision is incomplete (uncertain). The ECO2 (Ecology to Economy) model provides a robust framework for the analysis of development opportunities, taking the availability of resources into account. This framework provides a good platform to facilitate discussions in a multi-party environment. The structured decision support approaches are supported by the Water Sector Institutional Landscape (WSIL) Scenario analysis, which maps key drivers of change and facilitates the evaluation options and decisions under different future conditions. The National Freshwater Ecosystem Priority Areas (NFEPA) framework uses systematic conservation planning to provide strategic spatial priorities for conserving South Africa’s freshwater biodiversity, within the context of equitable social and economic development, whereas Solar Water Disinfection (SODIS), the Phosphate Sensitivity Index, and SWAT hydrological model can also contribute to achieving a balance between development (and consequent WWTWs) and protection (of human health and the environment).

### 2. Outputs/contribution to project

The main application of the platform to the Water Flagship Initiative, relates to its ability to model future household and enterprise water demand in a spatially explicit manner for all metropolitan regions of South Africa. UrbanSim has the ability to model future household and enterprise water demand in a spatially explicit manner for all metropolitan regions of South Africa. This will enable cities to anticipate the impact of residential and non-residential growth on water service delivery and inform investment decisions pertaining to reticulation and bulk infrastructure. Spatially explicit water demand modelling will also inform investment decisions pertaining to reticulation as well as bulk infrastructure with a view to ensure water security for the metropolitan growth engines of the country. By combining the evidence generated for all metropolitan regions of the country, the platform may even contribute to water demand planning at a national scale. The Geo-Spatial Analysis platform facilitates a shared understanding of development patterns and trends and the forces that shape them, by providing the evidence required to inform rigorous and robust debate amongst the various agencies of the state.

The ACWUA DDS, ECO2 model and Scenario approach mentioned earlier provides a robust framework for evaluating options in the context of current state and future trends for WWTWs. Catchment approaches, such as NFEPA, SWAT and SODIS will support spatial prioritisation of downstream areas that guides targeted upstream (e.g. engineering, governance and urban planning interventions at WWTWs), downstream (e.g. human health advisories and point of use treatment options) and in-stream responses (e.g. constructed wetlands) that reduce risks of WWTWs to ecosystem and human health. These technologies, in combination with spatial simulation, will facilitate engagement of different tiers and departments of government together with other stakeholders to promote cooperative governance.

The integrated solution will establish a platform to deliver different solutions at different levels, i.e. geographically (Plant, municipality, province, national), scales (small and large plants), governance (municipal, (inter)departmental, provincial, national), and temporal (short, medium and long term).

### 3. Tasks, Deliverables, TRL and Budget

| Activities & Deliverables | TRL CurrentTarget | Mnths | Budget |
| --- | --- | --- | --- |
| 2012/13 |  |  | 6.50M |
| Project management |  | 1-12 | 0.600M |
| D1: Established relationship between governance, human settlement, WWTWs and downstream users |  | 1-8 | 2.436M |
| T1.1: Policy context, institutional arrangements and decision processes defined for WWTWs - nationally and for case areas in particular |  | 1-4 | 677k |
| T1.2: Relationships between urban development and wastewater volumes and quality quantified - nationally and for case areas in particular |  | 1-6 | 536k |
| T1.3: Water infrastructure, capacity and consumption data acquired and incorporate into relational database |  | 1-4 | 514k |
| T1.4: Catchment (downstream users and environment) objectives and management options defined (NFEPA, and Human health) | NFEPA 99 | 1-8 | 709k |
| D2: Implement integrated platform for simulations, options and decisions |  | 3-10 | 2.686M |
| T2.1: Formalise and implement Living Lab process (ongoing) |  | 3-12 | 387k |
| T2.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA updated for case areas | UrbanSim 67 GS Platform 78 StepSA 78 | 3-9 | 1200k |
| T2.3: Technologies (ACWUA DSS, ECO2 model, WSIL Scenarios framework) and data incorporated in an integrated risk and options matrix | ACWUA 78 ECO2 67 WSIL Scenarios 77 | 4-10 | 1099k |
| D3: Consolidate and select intervention options |  | 6-12 | 0.715M |
| T3.1: UrbanSim, Geo-Spatial Analysis Platform and StepSA iterations and projections | UrbanSim 78 GS Platform 88 StepSA 78 | 6-11 | 315k |
| T3.2: Prioritize options for WWTWs in the case areas, based on the simulations (T2.2), real time monitoring (T3.1), conservation framework (T1.4), integrated risk-based matrix (T2.3), and key stakeholder engagement (T2.1) | ACWUA 78 ECO2 78 WSIL Scenarios 78 | 9-12 | 400k |
| 2013/14 |  |  | 5.6M |
| D4: Implementation of interventions from D3, monitor results and update models | All ..9 | 13-20 | 4.4M |
| D5: Assessment of impact of key interventions and roll out strategy to upscale solutions |  | 21-24 | 1.2M |
| 2014/15 |  |  | 4.5M |
| D6: Multiple roll-out of solution, monitoring, evaluation (incl. business model for replication) |  | 25-36 | 4.5M |

### 4. Team members

NRE: M Claassen, J Dabrowski, R Meissner, K Nortje, N Funke, C Ntombela, M du Preez, W Le Roux, P Oberholster, P MacMillan, L Hill, C Petersen, J Nel, D Le Maitre

BE: M Coetzee, L. Waldeck, A Le Roux, K. Wall, J Maritz, Y. Shapurjee, T, Leuta

MDS: N Siyakatshana

Biosciences: E Barros

### 5. Partners & co-funding (2012/13)

NRE: CoalTech (Upper Olifants)	 				R2.0M

NRE: Coaltech (Wetland Project)  					R1.5M

BE: IPDM and stepSA co-funding from DST   			R1.0M

BE: Flagship co-funding from core PG (Spatial Platforms)		R1.0M

NRE: Flagship co-funding from core PG (Aquabase Project)  	R1.2M

NRE: Flagship co-funding from core PG (Water Governance)  	R0.8M

Biosciences: Funding probes development				R1.5M

WSF Tasks

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Cause-Effect relationships |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: PM |  |  |  |  |  |
| Description: Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  | 31/5/2012: R75k; 30/6/2012: R50k; 31/7/2012: R75k; 31/8/2012: R50k; 30/9/2012: R75k; 31/10/2012: R50k; 30/11/2012: R75k; 31/12/2012: R25k; 31/1/2013: R50k; 28/2/2013: R63k; 31/3/2013: R75k |  |  |  |  |  |  |  |
|  |  | 28/02/2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R663k |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - None |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 120 |  | R 156 600 |  | R 35 000 |  |  |  | Travel and accommodation for meeting |  | - |
| R Meissner |  |  |  | 795 |  | 39 |  | R 31 005 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 39 |  | R 27 000 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 39 |  | R 31 005 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 39 |  | R 36 270 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 39 |  | R 26 325 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 39 |  | R 37 440 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 116 |  | R 127 020 |  | R 30 000 |  |  |  | Travel and accommodation for meeting |  | - |
| L. Waldeck |  |  |  | 1620 |  | 46 |  | R 74 520 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 40 |  | R 50 400 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 557 |  | R 597 585 |  |  | R 65 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
| Assumptions, Risk Factors & Contingencies: - Good overall project coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Cause-Effect relationships |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T1 |  |  |  |  |  |
| Description: Established relationship between governance, human settlement, WWTWs and downstream users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee, Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  | 31/5/2012: R0.35M; 30/6/2012: R0.35M; 31/7/2012:R0.35M; 31/8/2012: R0.35M; 30/9/2012: R0.35M ; 31/10/2012: R0.35M; 30/11/2012: R0.336M |  |  |  |  |  |  |  |
|  |  | 30/11/2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.436M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I1.1: Policy context, institutional arrangements and decision processes I1.2: Relationships between urban development and wastewater I1.3: Water infrastructure, capacity and consumption data I1.4: Catchment objectives and management options |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 175 |  | R 228 375 |  | R 140 000 |  |  |  | - Field work - Sample analysis - Software |  | - |
| R Meissner |  |  |  | 795 |  | 135 |  | R 107 325 |  |  |  |  |  |  |  |  |
| K Nortje |  |  |  | 675 |  | 54 |  | R 36 450 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 101 |  | R 68 175 |  |  |  |  |  |  |  |  |
| C Ntombela |  |  |  | 300 |  | 96 |  | R 28 800 |  |  |  |  |  |  |  |  |
| S Nienaber |  |  |  | 300 |  | 72 |  | R 21 600 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 101 |  | R 80 295 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 93 |  | R 86 490 |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  | 68 |  | R 42 840 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 96 |  | R 132 480 |  |  |  |  |  |  |  |  |
| P MacMillan |  |  |  | 540 |  | 68 |  | R 36 720 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 96 |  | R 51 840 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 135 |  | R 129 600 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 135 |  | R 113 400 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 153 |  | R 167 535 |  | R 530 000 |  |  |  | - Data acquisition - Field work - Sub-consulting |  | - |
| L. Waldeck |  |  |  | 1620 |  | 102 |  | R 165 240 |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  | 119 |  | R 67 830 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 48 |  | R 60 480 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 52 |  | R 39 780 |  |  |  |  |  |  |  |  |
| Y Shapurjee |  |  |  | 360 |  | 52 |  | R 18 720 |  |  |  |  |  |  |  |  |
| N Siyakatshana |  |  |  | 930 |  | 39 |  | R 36 270 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 2 058 |  | R 1 766 145 |  |  | R 670 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Good collaboration with stakeholders - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated Platform |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T2 |  |  |  |  |  |
| Description: Implement integrated platform for simulations, options and decisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen, Maria Coetzee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/7/2012 |  |  |  | Payment details: |  |  | 31/7/2012: R0.2M; 31/8/2012: R0.3M; 30/9/2012: R0.4M; 31/10/2012: R0.4M; 30/11/2012: R0.4M ; 31/12/2012: R0.2M; 31/1/2012: R0.4M; 28/2/2012: R0.386M |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.686M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I2.1: Formalise and implement Living Lab process (ongoing) I2.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA updated I2.3: Technologies and data incorporated in an integrated risk and options matrix |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - D1 |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 176 |  | R 229 680 |  | R 100 000 |  |  |  | - Field work - Sample analysis |  | - |
| R Meissner |  |  |  | 795 |  | 68 |  | R 54 060 |  |  |  |  |  |  |  |  |
| K Nortje |  |  |  | 675 |  | 116 |  | R 78 300 |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| C Ntombela |  |  |  | 300 |  | 25 |  | R 7 500 |  |  |  |  |  |  |  |  |
| S Nienaber |  |  |  | 300 |  | 25 |  | R 7 500 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 170 |  | R 135 150 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 68 |  | R 93 840 |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 |  | 68 |  | R 45 900 |  |  |  |  |  |  |  |  |
| C Petersen |  |  |  | 540 |  | 123 |  | R 66 420 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 68 |  | R 36 720 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 68 |  | R 65 280 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 68 |  | R 57 120 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 96 |  | R 105 120 |  | R 205 000 |  |  |  | - Data acquisition - Field work |  | - |
| L. Waldeck |  |  |  | 1620 |  | 297 |  | R 481 140 |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  | 297 |  | R 169 290 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 280 |  | R 352 800 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 315 |  | R 240 975 |  |  |  |  |  |  |  |  |
| N Siyakatshana |  |  |  | 930 |  | 116 |  | R 107 880 |  | R 0 |  |  |  |  |  | - |
| Totals: |  |  |  |  | 2 512 |  | R 2 380 575 |  |  | R 305 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T3 |  | Intervention options |  |
| Assumptions, Risk Factors & Contingencies: - Application of Technology demonstrators to particular context - Good collaboration with stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Intervention options |  |  |  |  |  |  |  |  |  |  | Task Ref. Number: T3 |  |  |  |  |  |
| Description: Consolidate and select intervention options |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee, Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/10/2012 |  |  |  | Payment details: |  |  | 31/10/2012: R0.1M; 30/11/2012: R0.2M; 31/12/2012: R0.1M; 31/1/2012: R0.2M; 28/2/2012: R0.185M |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R0.785M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: I3.1: Options, gap analysis and response framework for real-time WWTW monitoring system I3.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA iterations and projections I3.3: Prioritize options for WWTWs in the case areas, based on the simulations (I2.2), real time monitoring (I3.1), conservation framework (I1.4), integrated risk-based matrix (I2.3), and key stakeholder engagement (I2.1) |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - T1, T2 |  |  |  |  |
| Resources |  |  |  | Unit cost |  | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  |  | 1305 |  | 100 |  | R 130 500 |  | R 45 000 |  |  |  | - Field work - Sample analysis |  | - |
| K Nortje |  |  |  | 675 |  | 48 |  | R 32 400 |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  | 49 |  | R 38 955 |  |  |  |  |  |  |  |  |
| M du Preez |  |  |  | 930 |  | 34 |  | R 31 620 |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  | 34 |  | R 46 920 |  |  |  |  |  |  |  |  |
| M Thwala |  |  |  | 540 |  | 51 |  | R 27 540 |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 |  | 51 |  | R 48 960 |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  |  | 840 |  | 34 |  | R 28 560 |  |  |  |  |  |  |  |  |
| M Coetzee |  |  |  | 1095 |  | 18 |  | R 19 710 |  | R 35 000 |  |  |  | - Field work |  | - |
| L. Waldeck |  |  |  | 1620 |  | 68 |  | R 110 160 |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  | 60 |  | R 75 600 |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  | 102 |  | R 78 030 |  |  |  |  |  |  |  |  |
| Y Shapurjee |  |  |  | 360 |  | 102 |  | R 36 720 |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 751 |  | R 705 675 |  |  | R 80 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | None |  |
| Assumptions, Risk Factors & Contingencies: - Continued commitment from stakeholders - Acceptability of intervention options |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

External Co-Funding Task Sheets

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Coaltech – Sustainability |  |  |  |  |  |  |  |  |  | Task Ref. No.: CS |  |  |  |  |  |
| Description: Sustainable development related to water resources in the Olifants River Basin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R2.1M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Application of the SWAT model to WWTW context - Application of the Phosphate Sensitivity index model to WWTW context |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| K Nortje |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  |  |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  |  |  |  |  |  |  |  |  |  |  |
| A de Klerk |  |  |  | 420 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 1 750 000 |  |  | R 350 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Build on previous success in upper Olifants catchment - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Coaltech - Wetlands |  |  |  |  |  |  |  |  |  | Task Ref. No.: CW |  |  |  |  |  |
| Description: Sustainable development related to wetlands in the Olifants River Basin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.5M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Apply Wetland Index to assess function status of Wetlands - Define the role and potential of Wetlands in catchment process in context of WWTWs |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| K Nortje |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 |  |  |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  |  | 630 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 |  |  |  |  |  |  |  |  |  |  |  |
| A de Klerk |  |  |  | 420 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 1 250 000 |  |  | R 250 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Applicability of Wetland Index to WWTW context - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Core PG Co-Funding

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: BE Core PG: Living Lab |  |  |  |  |  |  |  |  |  | Task Ref. Number: LL PG |  |  |  |  |  |
| Description: Further Development of Living Lab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Maria Coetzee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/3/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.0M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Development, refinement and application of Living Lab platform |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - Previous Living Lab funding |  |  |  |  |
| Resources |  |  |  | Unit cost | Units |  | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| M Coetzee |  |  |  | 1095 |  |  |  |  |  |  |  |  |  |  | - |
| L. Waldeck |  |  |  | 1620 |  |  |  |  |  |  |  |  |  |  |  |
| A Le Roux |  |  |  | 570 |  |  |  |  |  |  |  |  |  |  |  |
| K Wall |  |  |  | 1260 |  |  |  |  |  |  |  |  |  |  |  |
| J Maritz |  |  |  | 765 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | 800 000 |  |  | 200 000 |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | T3 |  | Intervention options |  |
| Assumptions, Risk Factors & Contingencies: - Build on earlier success - Continued collaboration with government entities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: NRE Core PG: Aquabase |  |  |  |  |  |  |  |  | Task Ref. No.: AqB |  |  |  |  |  |
| Description: Understanding and managing freshwater ecosystem services in South Africa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Paul Oberholster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  | Payment details: |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R1.2M |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Apply Wetland Index to assess function status of Wetlands - Define the role and potential of Wetlands in catchment process in context of WWTWs |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  | Unit cost | Units | HR Cost |  | Running |  |  |  | Running costs |  | Capital |
| S Nienaber |  |  |  | 300 | 145 |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  |  | 795 | 417 |  |  |  |  |  |  |  |  |  |
| K Schachtschneider |  |  |  | 675 | 103 |  |  |  |  |  |  |  |  |  |
| L Hill |  |  |  | 675 | 152 |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  |  | 1380 | 161 |  |  |  |  |  |  |  |  |  |
| J Nel |  |  |  | 960 | 190 |  |  |  |  |  |  |  |  |  |
| D le Maitre |  |  |  | 840 | 92 |  |  |  |  |  |  |  |  |  |
| A Maherry |  |  |  | 540 | 176 |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | R 960 000 |  | R 240 000 |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Continued good relationship with project partners - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: NRE Core PG |  |  |  |  |  |  |  |  |  |  |  |  | Task Ref. No.: WSPG |  |  |  |  |  |
| Description: Water Sustainability – NRE Core PG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Marius Claassen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1/4/2012 |  |  |  | Payment details: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | R750k |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Governance and Policy - Human health, ecosystems and downstream users - Ecotoxicology - Catchment approach |  |  |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  |  |  |  | Unit cost | Units |  |  | HR Cost |  |  | Running |  |  |  | Running costs |  | Capital |
| M Claassen |  |  | 1305 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  | - |
| R Meissner |  |  | 795 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| K Nortje |  |  | 675 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| N Funke |  |  | 675 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| C Ntombela |  |  | 300 |  |  |  | 50 |  |  |  |  |  |  |  |  |  |  |  |
| S Nienaber |  |  | 300 |  |  |  | 75 |  |  |  |  |  |  |  |  |  |  |  |
| J Dabrowski |  |  | 795 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| M du Preez |  |  | 930 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| W Le Roux |  |  | 630 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| P Oberholster |  |  | 1380 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| P MacMillan |  |  | 540 |  |  |  | 80 |  |  |  |  |  |  |  |  |  |  |  |
| L Hill |  |  | 675 |  |  |  | 70 |  |  |  |  |  |  |  |  |  |  |  |
| M Thwala |  |  | 540 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| J Nel |  |  | 960 |  |  |  | 100 |  |  |  |  |  |  |  |  |  |  |  |
| D Le Maitre |  |  | 840 |  |  |  | 60 |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  |  |  | 700k |  |  |  | 50k |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Good collaboration with stakeholders - Data availability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  |  |  |  | Date: 9/5/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Bioscience - Core PG |  |  |  |  |  |  |  |  |  |  | Task Ref. No.: BSPG |  |  |  |  |  |
| Description: Water Sustainability – Biosciences Core PG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Eugenia Barros |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  |  | 1/4/2012 | Payment details: |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 31/03/2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | R1.5M |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Microbiological detection techniques |  |  |  |  |  |  |  |  |  |  |  | Critical predecessor tasks: - None |  |  |  |  |
| Resources |  | Unit cost |  | Units |  |  | HR Cost |  |  | Running |  |  |  | Running costs |  | Capital |
| E Barros |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Totals: |  |  |  |  |  | 1 200k |  |  |  | 300k |  |  |  |  |  | - |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | T2 |  | Integrated Platform |  |
| Assumptions, Risk Factors & Contingencies: - Collaboration with WSF project team members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): - None |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

APPENDIX B: INTERVENTION AREA 2

REVITALISING WASTEWATER TREATMENT FACILITIES

CLEANER ENVIRONMENT AND RENEWABLE ENERGY GENERATION AT MUNICIPAL WASTEWATER TREATMENT FACILITIES

Contents

1.	Introduction	35

1.1.	Background	35

1.2.	Benefits of the project	36

2.	Goal	37

3.	The solution	37

3.1.	Brief description	37

3.2.	Scalability of the technology package	39

4.	Project approach and deliverables	41

4.1.	Detailed project activities	42

5.	Feasibility	43

6.	Risks	43

7.	Capacity building, job creation and HCD	44

8.	Scientific knowledge generation and dissemination	44

9.	Governance	45

10.	Budget estimate	45

11.	Appendix I: CSIR anaerobic digester	48

# Introduction

## Background

Gauteng province foresees an increase in the number of inhabitants due to natural population growth and migration into the area. As a consequence the amount of domestic waste water that needs treatment is increasing significantly. According to the Tshwane municipality and ERWAT in Johannesburg they already have overflows during peak periods and they need to address this urgently. Most of their waste water treatment (WWT) plants are operating at or over design capacity (most of these plants were designed before 1980). In addition, there are increasing electricity costs associated with the WWT plants and this is now the major running cost in many of these plants. Both ERWAT and Tshwane recognize this as an important area of focus.

Several domestic WWT plants exist in the Gauteng area in close proximity of urban settlements (such as the Klipgat plant in Mabopane) that are not operating in the most effective and efficient way. An increase in inflows to the treatment plants is posing a health threat to these communities. Whereas many municipal WWT plants have anaerobic digesters, many of them are in disuse, are often used as “storage” rather than digesters, do not produce optimum levels of biogas and lack the required capacity. This causes the sludge not to be de-activated which leads to associated health risks especially during peak periods when overflow can land in open veld. This also has a significant influence on contamination of water resources.

In addition, typical WWT plants do not have a power backup and hence they are not able to process the inflowing sewage during periods of power failure resulting into discharge of untreated effluent in the environment. They might also be selling active sludge to local farmers for use as fertiliser (which is illegal).  At the same time most WWT plants do not make (full) use of the biogas generation capacity of organic waste sludge and its potential electricity generation capacity. The treatment of sludge through an anaerobic process de-activates it and therefore makes it suitable and safe for direct application on fields as fertiliser. Current legislation prohibits the use of active sludge as fertiliser, but this is not always effectively enforced.

The CSIR has developed a new anaerobic digester (AD) technology package that improves the performance of anaerobic digestion considerably compared with existing processes and equipment used at WWT plants.  The process is novel and consists of a two-stage, fully automated anaerobic digester that includes control of the critical parameters to optimize the process.  The CSIR has developed and tested a pilot version of the new AD and the results indicated that the system provides more gas of a higher quality than existing systems.  In addition, it reduces the retention time of the sewage in the system by almost half, thus increasing the capacity of such a system significantly.

The CSIR, in collaboration with ERWAT (the WWT service provider to Ekurhuleni municipality), is proposing to pilot this innovative technology package at full scale at ERWAT’s Hartbeestfontein plant. In this regard the CSIR has been in discussions with the Department of Science and Technology (DST) regarding the potential funding of such a project.  At the request of the DST, the CSIR conducted a first order feasibility assessment of the project.  The report on this work is attached to this project proposal. A full description of the technology package is given in the feasibility report.

The proposed project will aim to:

- Implement the two-stage, automated AD technology package in one full scale biogas digester;

- Assist with the operation of the plant for at least six months;

- Verify and quantify the benefits obtained from such implementation, and

- Ensure that there are direct benefits to the surrounding community from the project (mainly from the manufacturing of fertiliser).

## Benefits of the project

This project will provide benefit in terms of:

- Cost savings in terms of electricity usage at municipal WWT plants which could translate to savings (or at least slower increases) in the cost of sewage service delivery;

- Increase in municipal capacity in terms of waste water treatment (due to the increased efficiency of the proposed solution) thus preventing or reducing the cost of required capacity increases;

- Lowering of the health risks associated with active sludge, especially to poorer communities that are located close to these plants as well as in reducing water resource contamination;

- General improvement in service delivery owing to the fact that increased capacity in waste water treatment allows for acceleration of housing development (waste water treatment capacity is often a major bottleneck);

- Job creation through a community programme to modify the de-activated sludge into fertiliser (the community programme will be driven by ERWAT) , and

- Contribution to meeting of emission reduction targets at a national level owing to the use of alternate energy sources (alternative to coal-based electricity generation).

# Goal

The overall goal of the project is to implement an innovative solution for waste water (sewage) treatment that mitigates health risks, increases municipal WWT plant capacity, provides usable de-activated sludge as fertiliser and provides renewable energy from a waste stream thus reducing emissions and plant operational costs. The project will demonstrate the ability of the technology and that the solution can be used on a country-wide scale. At the same time the project with have a number of direct and indirect benefits as discussed above.

# The solution

## Brief description

The proposal addresses the required steps to demonstrate and implement a technology package that provides a novel approach to waste water treatment through a two-stage, fully automated anaerobic digester.  The proposal builds on internally funded research at the CSIR towards the modelling and simulation of such a package. A key characteristic of the technology developed by the CSIR is the two-stage nature of the digester and automated control of optimal gas-producing conditions, allowing continuous operation compared with the current batch process at WWT plants. This novel approach is currently being patented by the CSIR.

A pilot scale model of the two-phase digester has been built at the Innovation Site of the CSIR Built Environment. This scale model has been thoroughly tested and yields good results. The proposed project will demonstrate the scalability of the technology and its application at municipal WWT plants.  The CSIR system produces slightly better amounts of biogas than the current standard rate biogas systems, but at a much shorter retention time (and hence reducing the required system size for the same output or alternatively being able to handle larger amounts of waste water flow).

The pilot system is fully automated:

- it maintains constant pH and temperature of the sludge which are critical parameters for optimal digestion;

- it is a continuous process with controlled feed of sludge into the system ensuring optimal digestion and preventing the process from stopping, and

- the stirring of the sludge is optimal based on the performance of the system.

A schematic diagramme of the pilot version of the plant is shown in Figure 1 below whereas Figure 2 shows a photograph of the system.

Figure 1:  Schematic diagramme of the system

Figure 2:  The CSIR anaerobic digester

The system has been operated on pure municipal WWT sludge producing biogas with a methane content of 60 to 67%. Currently the digester is being tested using co-digestion with WWT sludge and cow manure, which seem to result in higher biogas yields.

Based on the feasibility study, the goal of the project is to design, develop and implement a technology package at ERWAT’s Hartbeestfontein municipal waste water treatment plant that includes a two-stage anaerobic digester (adapted from existing one-stage AD as can be found at most WWT plants), two 65kW electricity generation units and associated hardware. The installed hardware will be operated for at least 6 months under supervision of the CSIR, in which period the hardware will be thoroughly tested and staff at the WWT plant be trained to operate the installation.

Details on the CSIR AD technology can be found in Appendix I to this proposal and in the attached report on the feasibility study.

## Scalability of the technology package

In up scaling of the technology package, the following critical parameters need to be considered:

•	Heating and stirring of a larger volume of sludge;

•	Control of the pH of a larger volume of sludge;

•	Electricity generation, and

•	Withdrawal of digested sludge from the system.

Heating and stirring

Heating and stirring of 2 million litres of sludge (the size of a typical AD at a municipal WWT plant) has been implemented in a number of cases (see feasibility study report).  The equipment such as stirrers and heat exchangers are commercially available.  There is therefore minimal technical risk associated with the heating and stirring of the sludge in the proposed project.

Traditional methods of heating the digesters at MWWTP required that the bio gas is used in an inefficient gas boiler system for the heating of water. Sludge would be extracted from the digester by means of electrical pumps and then circulated through the boiler system. This has proven to be a very inefficient method of operation. Modern heat exchanger systems have become available that increase the efficiency of heat transfer between the heated medium and the digestate. This is technology that is available off the shelf and has been proven on various sites to be efficient if connected to a Combined Heat and Power (CHP) system. When electricity is generated with an internal combustion engine or gas turbine, waste heat is also generated. This waste heat can be harvested through a CHP unit. This is technology that exists and can be procured off-the-shelf. Suppliers that have a proven track record in this field are Caterpillar, Jenbacher, Capstone, Turbec, GE, etc.

Control of the pH

As described in literature (see feasibility study report), once an AD has been brought to the right pH level, the pH can be controlled with the load of sludge into the system.  In the case of the CSIR system this is a continuous process, therefore the sludge load can be controlled by the automated system in response to the measurement of pH through a number of sensors in the AD. The continuous nature of the process requires a second, smaller tank where the supernatant is separated from the solids, thus making it unnecessary to stop the process – and thereby rendering the pH level unsuitable.  This principle has been implemented in practice so there is minimal risk to implementing it in the proposed project.

ERWAT has an existing operating system for the aerobic part of the plant. It is therefore possible to link the automation system of the anaerobic digester to existing infrastructure. This automation system will include sensors such as thermocouples and pH sensors. Valves that operate the digester will be replaced with electronically operated valves that will allow the PLC system to operate the valves on parameters that will be set by the operator. This will facilitate the implementation of the operating system.

Electricity generation

During the CSIR pilot project, no electricity was generated.  However, this is being done regularly by companies such as Ener-G, so the risk is once again minimal.  The equipment is readily available from companies such as Caterpillar, Jenbacher, Capstone, Turbec, GE, etc.  The CSIR has opted for two 65 kW combined heat and power (CHP) engines to be used for the project instead of one, larger CHP engine.  This decision was based on the amount of gas that is likely to be available from one AD as well as to allow flexibility should ERWAT decide to connect to the other digesters to the system as well (see feasibility study report).

# Project approach and deliverables

The proposed project is a co-operation between the CSIR and ERWAT who is owned by the Johannesburg Metro and is the waste water treatment service provider for the Ekurhuleni municipality. The CSIR has already spent in excess of R3,0m on the development of the biogas technology package, project planning, partner selection and technical feasibility studies.  The feasibility study report is attached to this proposal.  This preparatory work will position this project to be conducted within a maximum of 18 months.

Specific deliverables are:

- A fully developed and tested technology package of a two-stage anaerobic digestion process adjusted for implementation at ERWAT’s Hartbeestfontein WWT plant with the purpose of generating biogas for use in an internal combustion engine to generate renewable energy. Specific components of this deliverable include analysis of the expected biogas based on the characteristics of the waste processed at the WWT plant, technical designs, and an implementation plan for the physical works to be carried out.

- A fully operational pilot project at a municipal water treatment plant in which the technology package has been installed and which results in the generation of approximately 1 GWh per annum of renewable electricity offsetting approximately 936 tons of CO2 associated with the avoided use of grid electricity and providing the benefits as described above. Specific components of this deliverable include procurement of equipment, contracting of installers, the physical works on site and the training of operating staff.

As indicated in the feasibility study report, the technology package will be implemented, using an existing biogas digester that will be modified to two stage operation and two CHP units of 65 kWe. The full biogas to electricity installation is expected to have a life span of 25 to 30 years, with an Operation & Maintenance (O&M) cost of approximately R 500.000 / year, which will be carried by ERWAT. The operation of the technology package by ERWAT will be conducted in close collaboration with the CSIR to generate experience in operation modalities and identification of possible improvements in the technology package to enhance outcomes.

## Detailed project activities

To conduct he project, the following activities are planned:

Digester upgrade

The following tasks will be done:

- Decoupling of the digester from the current set of 10 digesters

- Confirmation of the state of the digester and detailed technical plans on the work to be carried out.

- Removal of grit from the digester. Site inspections have revealed that 45% by volume of the digester is filled with grit that needs to be removed.

- Removal of current, non-functional mixing equipment and piping for heating.

- Installation of new mixing equipment.

- Installation of heat exchangers to heat the sludge.

- Installation of pipes for the biogas: one link to the existing gas storage and one to the small CHP units.

- Design and construction of the second tank.

- Installation of gas polishers / scrubbers to remove unwanted content from the biogas.

- Installation of CHP units that will generate the required electricity and heat to run the digester at mesophylic temperature.

- Installation of pipes to the second stage for sludge transport.

- Installation of a control system, including required valves and measurement points and linking that to the existing ERWAT PLC controller.

We expect to start the physical work on the digesters once the technical designs have been finalised and the required procurement procedures have been followed. Actual work on the digester will require approximately 6 months.

Gas composition determination

In parallel, the sludge from Hartbeestfontein will be digested in the CSIR pilot plant to determine the characteristics of the sludge as well as the exact amount and quality of gas that can be expected.  The sludge will be used in the pilot plant for three months to determine the composition of the sludge, its energy potential and the amount of cleaning / scrubbing of the gas needed before it can be used in an engine.

Planning and execution of community fertiliser programme

This task will be conducted by ERWAT with assistance from the CSIR.  The treatment of the de-activated sludge to produce fertiliser will become part of the current ERWAT community programme.

ERWAT has indicated that community members will be involved in the following way:

- If a pellet machine is available at a WWTP site; jobs could be created where pellet machine operators  are required as well as people for packaging the compost pellets into bags;

- For large scale farms, people could be hired for loading or offloading the bags into trucks;

- For small scale farms, people could be hired to manually spread the compost by hand, whereas on large scale farms, drivers of tractors could be employed, and

- If the sludge is of very good quality; it might require large amounts of people being employed since it would be of high demand.

It is estimated that 20 to 40 jobs can be created in this way. Details are given in the attached feasibility study.

Training of operators

During the construction period operators of ERWAT will be made familiar with the (components of the) technology and will be provided with on-the-job training once the digester is fully operational.

# Feasibility

Recognizing that municipalities would not have the capacity to build and operate the relatively sophisticated technology package, a management model will be developed that will ensure sustained operation of the facility. During the implementation period of the project the CSIR will be involved in the daily operation to identify possible improvements in the technology package that can facilitate the operation thereof.

The feasibility study (see attached report) indicated that the project is technically and economically feasible.  Most of the equipment required is readily obtainable.  The scalability of the solutions is discussed in some detail in the feasibility report.  It is not foreseen that there will be major challenges in up scaling the pilot plant to a full size anaerobic digester.

# Risks

There are a number of risks to the project. These are analysed and discussed in detail in the feasibility study report.

The first relates to technology risk. As indicated before the technologies that will be applied (anaerobic digestion and an internal combustion engine to generate electricity) are both mature technologies. The technology risk is limited to the integration of these technologies into one technology package, which is limited due to earlier modelling work done by the CSIR as well as the development of the prototype.

Secondly risks related to the project timeline and budget. These risks will be managed through proper project management and the use of standardised procedures.

Thirdly the risk of limited capacity at the WWT plant where the technology package will be implemented. This risk will be mitigated through intensive staff training and capacity building. New technology concepts will be introduced in a phased manner in order to avoid too high innovation rates. Once the technology package has been implemented and tested, and the ERWAT staff trained in its use, management of the installation will be handed over to ERWAT in a gradual fashion.

Risk 4 is related to the policy and legislative requirements especially those related to environmental impact.  The proposed technology package will not require a full EIA as we will be upgrading existing digesters, or more specifically, bringing them back to working order. As the electricity generated will be used within the boundaries of the WWT plant, no generation licence is required as no electricity will be supplied to the electricity grid.  Seeing that ERWAT is au fait with the handling of biogas this is a low risk.

# Capacity building, job creation and HCD

The project is designed around existing WWT plants and ways to optimise their operation. The project will modify already existing infrastructure and will make use of existing staff of the WWT facility. It is therefore not foreseen that new jobs will be created. However, intensive collaboration between the CSIR and the WWT facility will result in increased capacity at the WWT facility.

The modification of the de-activated sludge to produce fertiliser through the ERWAT community programme will however create some jobs. This will be done through the current ERWAT community programme as described above.

It is expected that the proposed project will lend itself ideally for practical work by Masters students of local universities.  It is envisaged that three students will participate in the project.

# Scientific knowledge generation and dissemination

The project will make use of the results of ongoing scientific research at the CSIR towards optimisation of the anaerobic digestion process. The application of this technology at an existing WWT plant will result in additional scientific knowledge on technology implementation. It is expected that between the CSIR and the WWT plant operator a number of presentations will be given at local conferences and one or two scientific articles will be produced.

The CSIR approach is novel and a provisional patent has been registered after evaluation by patent attorneys. During the first phase of the project possible further IP that can be generated through the project will be identified.

# Governance

The proposed implementation of the waste to electricity technology will take place at an existing WWT plant currently operated as an ongoing concern. The technology package will result in a modification of the operation of the plant that can be incorporated into the current business model.

It is anticipated that the requested funds will be used towards optimising the technology, procurement and installation of the technology and training of the operations staff to handle the technology. An extensive period of support by the CSIR is envisaged before the installation is handed over fully to the WWT plant operator.

As the operation of the technology package will be fully embedded in existing structures no major issues are anticipated regarding the governance if the project.

Project expenditure will be subject to the CSIR governance rules and external auditors.

# Budget estimate

This proposal comes at the end of a two year feasibility study funded by R 3 million of Parliamentary Grant investment by four CSIR Operating Units into laboratory-scale and small prototype experimentation with the two-stage AD proposed for this project.

Detail of the budgeted costs for the project is given in Tables 1 to 4 below.

Table 1: Total project costs

Table 2:  Detailed costs

Table 3:  Breakdown of control system costs

Table 4:  Detail of labour costs (this excludes a contribution of R 500.000 by the CSIR towards the project management costs

# Appendix I: CSIR anaerobic digester

The anaerobic digestion process is the biological breakdown of organic matter in an environment void of atmospheric oxygen. The breakdown of the organic material is done through four stages namely Hydrolysis, Acidogenesis, Acetogenesis and Methanogenesis. The organic sludge cannot be classified as stabilised unless all four these stages has been completed. The bacteria required for these four processes require certain parameters to be at optimal levels for the most efficient performance. These parameters include temperature, pH, loading rate and mixing. When these parameters are controlled to the required levels from the micro flora it will bring about a more complete and efficient process.

Traditionally the above processes were maintained by daily readings and laboratory analysis to establish action required to alter the environment for the optimal performance of the digester. Automating such procedures will improve the efficiency of the digester by eliminating the human factor that often leads to failure.

Differences between CSIR technology and conventional technology

The CSIR has developed an Automated AD that monitors and maintains the pH, temperature, loading and mixing. This technology has proved that the maintenance and control of the loading rate can in fact adjust the pH of the digester if the loading rate for the specific digester is maintained and adjusted according to the pH measured in the digester sludge.

The thermal energy required for the maintenance of the mesophilic temperature within the digester was supplied by a thermal generator other than the traditional combustion of the bio gas produced for temperature maintenance. This has proven that 100% of the gas product can be then utilised for alternative uses.

The automation system allows for a 24 hour operation of the AD without the input from manual labour. This allows for the environment within the AD to be adjusted over 24 hours. It also allows spreading out the loading of the digester that limits the shock that is placed on the digester by the introduction of the full daily load of raw feedstock at once as per traditional method. The spreading out of the available feedstock ensures a more constant production of gas over a 24 hour period as opposed to the traditional methods of taking the daily available feedstock and introducing this at once.  The cooler feedstock also requires a higher energy input to maintain the temperature in the digester due to the higher percentage of sludge that is introduced.

The two stage design of the CSIR AD allows for the digestion process to be continuous. Traditional methods would require shutting down the AD for a period of 2-3 days in order to allow the sludge to separate in to different strata. This would allow then for the extraction of the strata for further treatment and disposal. The CSIR system allows for the separation to occur in a separate vessel other than the main Reactor / Digester. This allows for the continuous operation and will improve the capacity of any plant that employs such a system. The energy consumption of the traditional method is also higher than that of a continuous system due to the requirement to reheat the entire digester once the extraction of the strata is complete.

Conclusion

An Automated two stage system not only eliminates failures due to human error but allows for a more energy efficient operation of an AD. The maintenance of the loading rate, pH, temperature and mixing allows for improved performance of the technology in general. The CSIR technology has proven that an alternative method of heating the AD will allow for harvesting of 100% of the bio gas product to be used for alternative use. This will increase the electricity generation capacity by the same percentage as the gas that would traditionally be required for the heating of the digester.

APPENDIX C: INTERVENTION AREA 3

CSIR WATER SUSTAINABILITY FLAGSHIP

REAL-TIME MONITORING, EVALUATION AND RESPONSE SYSTEM

28 MARCH 2012

| By: | Shaba Shabane | Signature | Date |
| --- | --- | --- | --- |
| Designation: | Project Manager: CSIR CAS |  |  |
| Approved By: | Gerhard Smith | Signature | Date |
| Designation | General Manager: CSIR CAS |  |  |

Contents

1.	PROJECT BACKGROUND	52

Project Need/Problem	52

Project Purpose	52

Summary of investments and achievements to date	52

Programme Overview	53

2.	PROJECT SCOPE DEFINITION	54

3.	PROJECT OBJECTIVES (GOALS)	54

Sensing Station	54

Software Development	54

Server	55

Modeling	55

Business Processes	55

Site Support	56

4.	PROJECT PRIORITIES	56

5.	PROJECT KEY STAKEHOLDERS	56

6.	PROJECT CONSTRAINTS, ASSUMPTIONS AND DEPENDENCES	57

7.	LIST OF PROJECT DELIVERABLES AND MILESTONES	57

WQMS	57

Stakeholders	58

Potential Clients	58

8.	INITIAL PROJECT RISKS	58

9.	PROJECT COST ESTIMATES	59

10.	PROJECT SCHEDULE ESTIMATES	60

11.	PROJECT SUCCESS CRITERIA	60

Proof of Concept	60

Pilot	60

12.	CONCLUSION	60

# PROJECT BACKGROUND

## Project Need/Problem

Many of South Africa’s municipalities cannot afford to maintain their waste water treatment plants. This has resulted in the situation which currently exists which is that, as of April 2010/11, only 7% of South Africa’s assessed waste water treatment facilities work to international standards. Only 50% of the existing facilities were tested.

A need has been identified to provide municipal water treatment plants in South Africa with water quality monitoring equipment, which can relay data back to a central monitor and control station. This will allow much needed expertise to be sent to the plants as and when required.

CSIR has been contracted through its Consulting and Analytical Services (CAS) unit, to produce this system. Material Science and Manufacturing (MSM) is working with CAS to develop the electrical, electronic and mechanical hardware necessary to provide this Water Quality Monitoring System (WQMS).

## Project Purpose

The Green Drop certification programme forms part of incentive-based regulation implemented by the Department of Water Affairs to identify and develop core competencies required in wastewater management. Compliance with the Green Drop certification programme will ensure that all Water Service Authorities are gradually and sustainably able to improve the level of wastewater management.  Green Drop Certification, a program specifically aimed at Waste Water Treatment Works (WWTW), aims to ensure that WWTW continuously improve their operations so as not to impact negatively on the water bodies into which they discharge their end product.

The DWA’s 2010/11 Green Drop report assessed the quality of waste water effluent at about 850 Municipal waste water plants.  In order for plants to achieve Green Drop status, water quality monitoring is a key requirement. This is absent in almost 90% of the plants.  There are also monitoring skills shortages and options of remote monitoring are deemed expensive.

## Summary of investments and achievements to date

The WQMS sensing station, its electronics and electrical systems were designed and full specifications developed for software, electronics, mechanics and testing.  Four test units were produced and 20 prototypes have been manufactured for the pilot studies.  The ‘Hydra’ board was developed and tailored in-house specifically for the WQMS application. In addition this solution offers options for further expansion as needs are identified.

An initial version of the server software platform and user interface has been developed. It is currently in use with the data collected by the test units that have already been installed.  A demonstration version has also shown for the demo sensing station used in presentations to stakeholders. A thorough review of the software and user interface has recently been carried out, including all CSIR and Prime Africa team members to document all processes and identify gaps relating to further potential system enhancements and offerings as well as understand user and potential client requirements.

The key component of the CSIR’s WQMS is a real-time, remote water quality monitoring and data management component, tied into a monitoring and evaluation system to be developed for monitoring the Green Drop status.  Real-time management information will be available, and that laboratory costs of water quality monitoring will be reduced. The intent is to have this system help municipalities to obtain and keep Green Drop status for their respective treatment plants.

## Project Overview

The CSIR’s comprehensive solution looks to put in place systems, processes and procedures to complement those already in place and ensure the achievement and sustainability of Green Drop certification. A decision was taken to focus initially on the first module, namely assisting with Green Drop certification. Thereafter, the platform and criteria and indicators will be incrementally modified to cover the other market areas, which potentially are larger than the Green Drop market. There will be continuous or iterative feedback loops to the modelling groups to ensure improvement of the algorithms used in a process of ongoing improvement.

# PROJECT SCOPE DEFINITION

This project will cover the first phase of completing the proof of concept (development, testing and debugging) of the WQMS, and the second phase required to achieve the envisaged impact of the WQMS, namely the piloting and the marketing of the concept. The pilot study installation would be of sizeable number of units with client municipalities.

The following illustration is a diagram of the current system design

# PROJECT OBJECTIVES (GOALS)

### Sensing Station

The manufacturing process is to be scaled up for regular production.  Upgraded versions of the Hydra board are planned and the station is to be modified to include further sensors which will require both hardware and software upgrades. Planned upgrades in firmware will entail the interfacing with a newly defined server protocol, as well as allowing firmware upgrades in the field. Extensive self-analysis and self-maintenance options are also planned. A sample turbidity probe has already been sourced which must be built into a test unit and tested in situ.  The current proof of concept installations will be completed by April 2012, while the manufacturing process is planned to be in place by mid 2012.

### Software Development

The software will be upgraded to ensure a high level of appropriateness and adaptability in relation to the following key processes:

- Sensing stations

  - Sending and receiving data and status messages

  - Configurations work flow

  - Installation and activation of stations

  - Maintenance and calibration processes

- Customer interface

- Deployment

- Monetization

- Immovable Asset Management (IAM) and integration with the CSIR’s IAM system

- Communication (command centre, customers and CSIR team members)

- Server management

  - Communications

  - Rules engine

  - Customer service

  - Notification service

- Rules

- Notifications

The information platform component is a critical backbone for many products within CAS. It will form the central repository for all management information for this platform and allow models to be used and management reports to be derived that are fit-for-purpose for different levels of management.

### Server

Additional hardware must be procured to establish the development environment required by the system.  This procurement and the related hosting of the infrastructure will take place in the first quarter of 2012/2013, with budget planned for upgrades or possible additional hardware requirements in 2013/2014.

### Modeling

For improved water quality algorithms, at least 400 data sets are required.  This requires sampling at eight more WWTPs, and taking three sets of 10 samples at each of these.  It is planned to complete this by August 2012.   As additional probes are added to the sensing station, new algorithms must be developed to utilise the new data available and further sampling and calibration must be done to ensure correlation with laboratory results.  This development and the refinement of algorithms will be a continuous process.

### Business Processes

Business development and project management of proof of concept and pilot study will continue.  The project management function will be essential to ensure that the platform as a whole is developed comprehensively. Given that CSIR CAS is ultimately responsible and accountable for delivery of this platform, an overall dedicated Project Manager has been appointed to assume ultimate accountability for delivery on the platform. The project manager will ensure delivery of all sub-projects and the appropriate alignment of resources and collaborators to ensure success. Each sub-project will be assigned junior project managers that will complete the sub-projects associated with the platform. These managers will meet regularly (as required) to ensure delivery is on brief, budget and time. The normal CSIR governance and support structures will apply.

### Site Support

It is the intent of this project to involve interns programs, to assist with initial water sampling and possible regular maintenance on the installed systems. Where this is not possible, an automated sampler will be installed to obtain the 24 hour sampling cycle as required. The project will procure a few of these auto-samplers to be used for the proof of concept and pilot sites as and where needed.

# PROJECT PRIORITIES

The sequence of activities would be as follows:

- Continuation of proof of concept sites, to be executed in parallel to pilot sites

- Selection of further pilot sites, physical contract in place

- Site-visit, inspection and evaluation

- Conduct initial water sampling

- Installation and commissioning of WQMS units

- Initial data reporting

- Rules development for pilot site, implemented on server

- Regular maintenance and calibration of the WQMS Station

- Maintenance response teams to assist under-capacitated municipalities

# PROJECT KEY STAKEHOLDERS

The following internal and external stakeholders were identified

STAKEHOLDERS

INTERNAL STAKEHOLDERS

Material, Science & Manufacturing - MSM

Consulting & Analytical Services - CAS

Natural Resources & Environment - NRE

Modelling & Digital Science - MDS

Built Environment - BE

ICT

Finance

Marketing

Procurement

EXTERNAL STAKEHOLDERS

Customer/user base

- Department of Water Affairs

- Various NGO’s (e.g. Municipalities)

- Department of Defence (TBC)

- Department of Health

- Water Board

Infrastructure & Services

- Cellular Providers (MTN, Vodacom, Cell C)

- ESKOM Power

Sub Contractors

- Installation & Maintenance providers (e.g. Electrical/Instrumentation contractor) - Emergency Services (internal or external)

- Modelling Experts (e.g. Prime Africa)

- Development (e.g. DVT)

Training Partners (e.g. MANDEVCO)

The following project task team was identified

| Name | Email | Group | Project Role |
| --- | --- | --- | --- |
| Gerhard Smith | gpsmith@csir.co.za | CSIR CAS | Project sponsor |
| Sumeshan Govender | sgovender1@csir.co.za | CSIR CAS | Business development |
| Karen van Breukelen | kvbreukelen@csir.co.za | CSIR CAS | Business development |
| Shaba Shabane | sshabane@csir.co.za | CSIR CAS | Project manager |
| Riaan Coetzee | rcoetzee@csir.co.za | CSIR MSM | Business development |
| Peter Bosscha | pbosscha@csir.co.za | CSIR MSM | System development |
| Kevin Wall | kwall@csir.co.sa | CSIR NRE | Subject Expert |

# PROJECT CONSTRAINTS, ASSUMPTIONS AND DEPENDENCES

The following constraints, assumptions and dependences were identified

| Item | Description |
| --- | --- |
| Constraints | ? |
| Assumptions | Full scale pilot sites are contracted |
| Dependences | Subcontractor of server software deliver on time |

# LIST OF PROJECT DELIVERABLES AND MILESTONES

### WQMS

The task team will embark on piloting this technology at full scale, with quality outcomes and benefits of 10 to 20 nodes. The CSIR is conducting a proof of concept to a number of stand-alone units within the Tshwane region, and now will be seeking to install pilot units at a larger scale.

Lepelle Northern Water (LNW) has kindly offered three WWTWs as potential sites for extending this pilot programme for a 12 month period. These pilot sites are Burgersfort, Marble Hall and Steelpoort.  A further 11 sites in the Sekhukune District Municipality will be sourced for the pilot.

### Stakeholders

The task team will engage with key external stakeholders to align project deliverables with their current strategic initiatives.

### Potential Clients

Strong relationships have been established and sustained with potential clients at the provincial and municipal level, in the Limpopo, Free State and KwaZulu/Natal in particular.  Numerous presentations to target groups and the broader water community at conferences have taken place, generating interest and deepening our knowledge of on-the-ground concerns and challenges.

# INITIAL PROJECT RISKS

The following high and medium level risks were identified

| Potential Risk | Risk Description |
| --- | --- |
| Funding | No funding received from the Executive to execute the system |
| Roll out | Lack of capacity to implement the system |
| Development | Debugging fixes may generate new errors on the system |
| Pilot sites | Not sufficient sites have been identified to test the system on larger scale |
| Lab testing | Lack of capacity to do sampling and lab tests as required by Green Drop |
| POC vs Pilot | Proof of concept not fully tested and proven to be executed along pilot |

# PROJECT COST ESTIMATES

| Task | 2012/2013 |
| --- | --- |
| Pilot Sites Units Yr 1 | R 1 694 000.00 |
| Configuration of Pilot Units Yr 1 | R 100 000.00 |
| Governance - Site Inspections | R 490 000.00 |
| Governance - Laboratory Testing | R 490 000.00 |
| Governance - WWTW Assessments | R 4 420 000.00 |
| Modelling & Algorithms | R 600 000.00 |
| Hardware & Software | R 800 000.00 |
| Next Generation | R 4 036 000.00 |
| Project Management | R 700 000.00 |
|  | R 13 330 000.00 |

# PROJECT SCHEDULE ESTIMATES

The near real-time monitoring, evaluation and response system will address short, medium and long term water quality issues, however this project will focus on immediate, 18 to 24 months deliverables. A detailed project schedule is scoped to outline a full work breakdown structure, and will be delivered to the WSF forum.

# PROJECT SUCCESS CRITERIA

### Proof of Concept

Five test sites are in place currently, two units are operating side-by-side at Daspoort Waste Water Treatment Works to provide data sets on which to measure repeatability across units.  A unit is installed in the north eastern dam on CSIR campus and a further unit is installed at Sunderland Waste Water Treatment Works. Finally, a unit is installed at the Refilwe (near Cullinan) Waste Water Treatment works. These sites will be maintained until at least the end of the 2012/2013 financial year.  This will require calibration, maintenance and regular sampling for laboratory comparisons.

### Pilot

Furthermore, pilot studies will be undertaken in the 2012/2013 financial year with partnering municipalities.  These studies will utilize most of the 20 prototype sensing stations already available and provide an essential “reality check” of the challenges facing the system when installed on a larger scale at WWTWs not necessarily functioning at the standard of the Tshwane WWTWs currently used as test sites.

# CONCLUSION

This project aims to make available a CSIR solution which provides a real-time monitoring, evaluation and response system to an NGO. This solution will provide municipalities with a system to obtain and maintain their Green Drop certification status. The solution will be marketed within South Africa initially but later on internationally, such that it will provide a steady source of income to the CSIR.

| TASK DETAIL SHEET |  |  |  | Date: | 24-Apr-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Pilot Sites Units Yr 1 |  |  | Task Ref. No.: | 3.1 |  |
| Description: | Installation, commissioning and maintenance of WQMS units at pilot sites |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 1 355 205.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Terblanche P. | R 665.00 | 160 | R 106 400.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 120 | R 145 200.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 639 | R 233 235.00 |  |  |  |
| Mbizeni A. | R 365.00 | 638 | R 232 870.00 |  |  |  |
|  |  |  |  | R 637 500.00 | S&T & installation |  |
| Totals |  |  | R 717 705.00 | R 637 500.00 |  |  |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Installation of Units on Site |  |  |  |  |  |
| 2 | Maintenance Reports |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • Installations need to be confirmed and approved by site owner, this process might take time. • Lacking Infrastructure might impose additional installation costs. • Assumed that site-visits (Inspect, Commissioning, Maintenance) will be combined trips, additional costs if not. |  |  |  |  |  |  |
| Various notes (including capital needs) Sub-Contractors will be used for electrical and basic plumbing, the installation amounts are estimated based on previous quotations. |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Notification and Alerting system |  |  |  |  |  |  |  | Task Ref. Number: 3.2 (E1.1) |  |  |  |  |
| Description: Implementation and development of the Wide Area Alerting Sub-system as component of the real-time monitoring and response system |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Graeme McFerren, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31August 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 70 000 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Integrate WAAS sub system, test and deploy Configure ISP for SMS notifications |  |  |  |  | Critical predecessor tasks: Operational monitoring system; databases and server Confirmed ISP |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 55 |  | 37950 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 50 |  | 32250 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 70200 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | The contract costs for the Short Message Service provider is not included in this budget |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Access will be allowed to sensor databases, server and software currently in use (b) a list of client subscribers are available for testing purposes. Contingencies: A suitable ISP provider has been contracted to provide bulk SMS services |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): A suitable ISP provider has been contracted to provide bulk SMS services |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated platform design |  |  |  |  |  |  |  | Task Ref. Number: 3.3 (E1.2) |  |  |  |  |
| Description: Design the architecture of the integrated water information platform based on open standards and open source software. |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31Dec 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 90 000 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| T van Zyl |  | 885 | 75 |  | 66375 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 20 |  | 24300 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 90675 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Specifications for open standards compliant platform, including data models and first level system components |  |  |  |  |  |  |  |  |  | Development of platform |  |  |
|  | Defined migration process from current to new system |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Configuration of Pilot Units Yr 1 |  |  | Task Ref. No.: | 3.4 |  |
| Description: | Configure communication & activate installed units |  |  |  |  |  |
| Responsible Resource: |  | Matthew Vassard |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Aug-12 |  |  |  |  |  |
| Total Budget | R 100 000.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: 3.1 Pilot Sites Units Yr 1 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| M Vassard | R 645.00 | 132 | R 85 140.00 |  |  |  |
|  |  |  |  | R 14 860.00 | S&T & disbursements |  |
| Totals |  |  | R 85 140.00 | R 14 860.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Operational units sending functional data |  |  | 3.6 | Governance - Lab Testing |  |
| Assumptions, Risk Factors & Contingencies • Units installed with sufficient GSM coverage |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - Site Inspections |  |  | Task Ref. No.: | 3.5 |  |
| Description: | Initial site inspections, gathering of data to prepare for detailed WWTW assessments & agree to placement of Units |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 30-Sep-12 |  |  |  |  |  |
| Total Budget | R 490 000.00 |  |  |  |  |  |
| Input & Specifications: Site managers' cooperation |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Adlem | R 745.00 | 200 | R 149 000.00 |  |  |  |
| Interns | R 70.00 | 672 | R 47 040.00 |  |  |  |
| Water lab resource | R 450.00 | 336 | R 151 200.00 |  |  |  |
| JJ Lottering | R 585.00 | 160 | R 93 600.00 |  |  |  |
|  |  |  |  | R 49 160.00 | S&T & disbursements |  |
| Totals |  |  | R 440 840.00 | R 49 160.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Inspection reports for each site |  |  | 3.1 | Pilot Sites Units Yr 1 |  |
|  | specific installation placement agreed to with operator |  |  | 3.4 | Configuration of Pilot Units Yr 1 |  |
| Assumptions, Risk Factors & Contingencies • cooperation of WWTW resources • coordination with task 3.1 as has to happen concurrently |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - Laboratory Testing |  |  | Task Ref. No.: | 3.6 |  |
| Description: | 24 hour sampling to determine water footprint on installation and regular testing to provide lab correlation to field data |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 442 288.00 |  |  |  |  |  |
| Input & Specifications: Site managers' cooperation |  |  | Critical predecessor tasks: 3.1, 3.2 and 3.3 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Adlem | R 745.00 | 28 | R 20 860.00 |  |  |  |
| CAS Water Lab |  |  | R 333 760.00 |  |  |  |
|  |  |  |  | R 40 628.00 | S&T & disbursements |  |
| Intern | R 70.00 | 672 | R 47 040.00 |  |  |  |
| Totals |  |  | R 401 660.00 | R 40 628.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Water footprint for each site |  |  | 3.8 | Modelling & Algorithms |  |
|  | regular samples tested in labs |  |  |  |  |  |
|  | data fed into modelling for correlation |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • availability & competence of interns / auto-samplers to collect 24 hours samples & other samples |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Governance - WWTW Assessments |  |  | Task Ref. No.: | 3.7 |  |
| Description: | detailed assessments and recommendations for plant ops support and immovable asset management |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 30-Nov-12 |  |  |  |  |  |
| Total Budget | R 3 535 400.00 |  |  |  |  |  |
| Input & Specifications: WWTW specific info as available |  |  | Critical predecessor tasks: 3.3 Governance - Site Inspections |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| C Greyvensteyn | R 1 140.00 | 640 | R 729 600.00 |  |  |  |
| P Liebenberg | R 1 050.00 | 640 | R 672 000.00 |  |  |  |
| J Lottering | R 585.00 | 800 | R 468 000.00 | R 206 200.00 | S&T & disbursements |  |
| IAM QC team members | R 700.00 | 1228 | R 859 600.00 |  |  |  |
| M Moodley | R 750.00 | 800 | R 600 000.00 |  |  |  |
| Totals |  |  | R 3 329 200.00 | R 206 200.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | detailed assessment reports per site |  |  |  |  |  |
|  | recommendations for implementation at WWTW |  |  |  |  |  |
|  | asset registers and exec summaries per site |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • availability of sub-contractor & collaborator resources |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Modelling & Algorithms |  |  | Task Ref. No.: | 3.8 |  |
| Description: | Application of unit & lab test data to refine models & tailor site specific rules |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 600 000.00 |  |  |  |  |  |
| Input & Specifications: data received from field & labs |  |  | Critical predecessor tasks: 3.1, 3.4, 3.6 |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| S Kok | R 1 350.00 | 110 | R 148 500.00 | R 7 750.00 | incidentals |  |
| O Ubbink | R 1 800.00 | 35 | R 63 000.00 |  |  |  |
| J Kekana | R 510.00 | 190 | R 96 900.00 |  |  |  |
| N Siyakatshana | R 930.00 | 145 | R 134 850.00 |  |  |  |
| C Adlem | R 745.00 | 200 | R 149 000.00 |  |  |  |
| Totals |  |  | R 592 250.00 | R 7 750.00 |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | refined models with site specific requirements |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • sufficient data of confirmable quality • understanding of license measures for each site |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Hardware & Software |  |  | Task Ref. No.: | 3.9 |  |
| Description: | upgrade software, procure additional server & provide comms consumables (SIMS) |  |  |  |  |  |
| Responsible Resource: |  | Matthew Vassard |  |  |  |  |
| Start Date | 01-Jun-12 | Payment details |  |  |  |  |
| Finish Date | 31-Aug-12 |  |  |  |  |  |
| Total Budget | R 800 000.00 |  |  |  |  |  |
| Input & Specifications: user requirements outputs & learnings from 3.7a-c |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| M Vassard | R 645.00 | 80 | R 51 600.00 |  | Server | R 250 000.00 |
|  |  |  |  | R 400 000.00 | software development |  |
|  |  |  |  | R 98 400.00 | SIMS & related |  |
| Totals |  |  | R 51 600.00 | R 498 400.00 |  | R 250 000.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | functional software & hardware infrastructure |  |  | 3.7a-c | to run in parallel effectively |  |
|  | comms between units & server |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • valid user input • procurement processes |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Near real time monitoring system |  |  |  |  |  |  |  | Task Ref. Number: 3.10 (E1.3) |  |  |  |  |
| Description: Develop and pilot (test) monitoring system and core integrated platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2012 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Dec 2012 |  |  |  |  |  |  |  |  |  |  |
|  |  | 290700 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  | Server |  | 110000 |
| M Mtetsfwa |  | 645 | 80 |  | 51600 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 60 |  | 53100 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 160 |  | 103200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 290700 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): Server and backup hardware to be procured: R110 000 |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Integrated near real time monitoring system |  |  |  |  |  |  |  | Task Ref. Number: 3.11 (E1.4) |  |  |  |  |
| Description: Near real-time monitoring system tested, validated and operational on core integrated platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Jan 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2013 |  |  |  |  |  |  |  |  |  |  |
|  |  | 369900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 100 |  | 64500 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 80 |  | 70800 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 160 |  | 103200 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 40 |  | 48600 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 369900 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback Contingencies: Current AFIS system specifications can serve as ‘template’. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Next Generation |  |  | Task Ref. No.: | 3.12 |  |
| Description: | Sensor updates & add-ons, electronics & mechanical updates, software updates & manufacturing ready data-pack. Manufacture of 10x additional units |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 3 228 017 |  |  |  |  |  |
| Input & Specifications: previous design, updates to be generated as first instance |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Terblanche P. | R 665.00 | 600 | R 399 000.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 604 | R 730 840.00 |  |  |  |
| Coetzee S. | R 585.00 | 712 | R 416 520.00 |  |  |  |
| Swart S. | R 429.00 | 328 | R 140 712.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 947 | R 345 655.00 |  |  |  |
| Mbizeni A. | R 365.00 | 946 | R 345 290.00 |  |  |  |
|  |  |  |  | R 850 000.00 | hardware / parts |  |
| Totals |  |  | R 2 378 017.00 | R 850 000.00 |  | R 0.00 |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Retrofit of existing units |  |  |  |  |  |
| 2 | Sensor Research, User and System Specifications |  |  |  |  |  |
| 3 | Improved Design |  |  |  |  |  |
| 4 | 10x Next Generation Units with production datapack, improved sensor data, more reliable and easier operation, better maintainable. |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • procurement processes / suppliers |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Project management |  |  | Task Ref. No.: | 3.13 |  |
| Description: | PM, monitoring & evaluation of progress |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 700 000.00 |  |  |  |  |  |
| Input & Specifications: info from all other tasks |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| K van Breukelen | R 850.00 | 800 | R 680 000.00 | R 20 000.00 | disbursements |  |
| Totals |  |  | R 680 000.00 | R 20 000.00 |  | R 0.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | good governance control of project |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | Field Measurements & Project Management |  |  | Task Ref. No.: | 3.14 |  |
| Description: | MSM PG Co-Funding |  |  |  |  |  |
| Responsible Resource: |  | Peter Bosscha |  |  |  |  |
| Start Date | 01-May-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 1 000 205.00 |  |  |  |  |  |
| Input & Specifications: Site identification |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| Coetzee R. | R 1 287.00 | 120 | R 154 440.00 |  |  |  |
| Bosscha P. | R 1 210.00 | 240 | R 290 400.00 |  |  |  |
| Terblanche. P. | R 665.00 | 240 | R 159 600.00 |  |  |  |
| Coetzee S. | R 585.00 | 150 | R 87 750.00 |  |  |  |
| Swart S. | R 429.00 | 150 | R 64 350.00 |  |  |  |
| Tyatiantsi A. | R 365.00 | 211 | R 77 015.00 |  |  |  |
| Mbizeni A. | R 365.00 | 210 | R 76 650.00 |  |  |  |
|  |  |  |  | R 90 000.00 | Travel, Sensors, Installation |  |
| Totals |  |  | R 910 205.00 | R 90 000.00 |  |  |
| Ref | Deliverables |  |  | Critical Successor tasks |  |  |
| 1 | Project Management of Tasks 3.1, 3.8 and 3.10 |  |  |  |  |  |
| 2 | Plant Inflow Measurement of Total Organic Loading |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies • Access to site for inflow monitoring installation |  |  |  |  |  |  |
| Various notes (including capital needs) Sub-Contractors will be used for electrical and basic plumbing, the installation amounts are estimated based on previous quotations. |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  | Date: | 17-May-12 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Task heading: | CAS Co-funding |  |  | Task Ref. No.: | 3.16 |  |
| Description: | CAS system & rules development |  |  |  |  |  |
| Responsible Resource: |  | Karen van Breukelen |  |  |  |  |
| Start Date | 01-Apr-12 | Payment details |  |  |  |  |
| Finish Date | 31-Mar-13 |  |  |  |  |  |
| Total Budget | R 7 000 000.00 |  |  |  |  |  |
| Input & Specifications: WQMS concept and business plan |  |  | Critical predecessor tasks: |  |  |  |
| Resources | Unit cost | Units | HR Cost | Running | Notes for running costs | Capital |
| CAS Team | R 800.00 | 4500 | R 3 600 000.00 | R 3 400 000.00 |  |  |
| Totals |  |  | R 3 600 000.00 | R 3 400 000.00 |  | R 0.00 |
| Ref | Notes on Outputs, Specifications & Controls |  |  | Critical Successor tasks |  |  |
|  | Pilot ready system and processes |  |  | All |  |  |
| Assumptions, Risk Factors & Contingencies • valid user input • procurement processes • integration with all tasks |  |  |  |  |  |  |
| Various notes (including capital needs) |  |  |  |  |  |  |

APPENDIX D: ICT AS A CROSS-CUTTER:

# Meraka Contribution to the CSIR Water Sustainability Flagship

# Summary

The CSIR Meraka Institute has a well established capability and track record in developing and deploying operational sensor monitoring and alert platforms for environmental phenomena. The most prominent of these is the Advanced Fire Information System (AFIS) that monitors threatening wildfires, so-called ‘hotspots’, and provides near real-time notifications and alerts to a variety of clients. Another example is the Earth Observation Water Quality Monitoring and Mapping system developed as part of the Safe Water Earth Observation (SWEOS) CSIR Science Research Project.

Several mature technologies underpinning these platforms have been implemented; the Wide Area Alerting System, for example, is a TRL level 7 ICT platform that generates and disseminates data and information derived from data originating from heterogeneous sensors, models or monitoring processes, over multiple digital communications channels. This proposal addresses Intervention Areas 3 and 4 of the WSF through the following interventions:

- Collaboratively implement the dissemination component of a water quality monitoring system currently developed by CSIR Analytical Services(?) (CAS). The Wide Area Alerting System (WAAS) will be deployed to disseminate notification and alert messages through selected communications channels.

- Develop an open source, extensible, scalable and interoperable platform for near real-time water quality monitoring, sustainability assessment and response. The platform will be based on Open Standards compliant services and interfaces, and deploy technologies at Readiness Level 6 and higher. Sub-components of the initial pilot will be migrated to this platform.

## Contributors

Anwar Vahed

Graeme McFerren

Albert Lysko

Thomas Olwal

Louis Coetzee

# 1.  Introduction

The CSIR Meraka Institute is the leading practitioner in Africa for the development and deployment of standards compliant and open source ICT for environmental observation. The Advanced Fire Information System (AFIS) is a well-known operational system that monitors wild fires and provides near real-time information to clients such as ESKOM and farmers. Another example of implementation is the sensor observation and monitoring system developed as part of the Safe Water Earth Observation System (SWEOS). The system provides maps of eutrophication and cyanobacterial indices, water clarity and other water quality products for approximately 250 major dams in South Africa. A similar system is developed for the Acid Mine Drainage Science Research project for which data from in-situ water chemistry sensors is monitored.

The technologies deployed in these applications are domain agnostic, i.e., the code base is generalised and can be implemented for arbitrary environmental monitoring applications and for heterogeneous types of sensor (remote, air-borne or in-situ), the latter being technically the easiest to leverage. Deployment of a new application involves some configuration steps, styling of user interfaces and connecting databases of observations. It is important to note that this platform is designed to be layered, i.e., it is expressly not a single 'stovepipe' solution and aimed at making it possible to open up water quality and other observational data to a wide audience.

## 1.1  Open Standards and Interoperability

Different custodians of sensory data can employ different or even proprietary formats and models for provided data and derived products. This condition presents an interoperability impediment resulting in information isolation. The use of open standards and encodings in the provision of data products is a key requirement for sharing data and is encouraged by national strategy. Sensor Web Enablement is a well-established concept that provides a suite of standardised web service interfaces and encodings for sensory data exchange.

The Open Geospatial Consortium (OGC) open standards have been adopted in the South African Earth Observation System (SAEOS). A number of OGC compliant Sensor Web services have been deployed in SAEOS for, amongst others, weather stations, oceanographic and remote sensors. These specifications include models for encoding sensor observations and measurements, for describing sensor systems and associated processes, interfaces for requesting and retrieving sensor data, and for publishing and subscribing to alert notifications from sensors. The OGC standards ensure interoperability and they are fundamental to developing sensor observation and monitoring services in a cost-effective and sustainable manner.

Several such services are deployed operationally in systems such as the Advanced Fire Information System (AFIS) and the Safe Waters Earth Observation System (SWEOS SRP), and more are being developed for, for example, the Acid Mine Drainage (AMD) SRP. A GIS-based information platform is being developed for the AMD SRP which will include a monitoring and alerting capability (in part developed for water quality sensors) and a time series visualisation component.  Such components fit naturally into the WSF ICT platform. Particular contributions would include rapidly deployable operational Sensor Observation Services and Web Feature Services for water chemistry sensors. Open standards based monitoring and alerting services will be implemented for near real-time (e.g., hourly) data streams.

# 2.  Proposal

The Meraka Institute proposes to contribute to the WSF as follows.

- Alert and Notification Subsystem: Collaboratively implement the dissemination component of a water quality monitoring system currently developed by the CSIR Analytical Services unit (CAS). The Wide Area Alerting System (WAAS) will be deployed to disseminate notification and alert messages through selected communications channels. This technology can be deployed operationally within two months from the start of project activities.

- Integrated Platform: Design and implement an open standards, integrated Water Resources Information System - an ICT platform that provides ready access to water data and seamlessly links information production (research) and information consumption (planning and decision making). Open source sensory data provisioning services (implementations of Open Geospatial Consortium standardised web services), a monitoring and alerting system (the Wide Area Alerting System), and a research platform that integrates EO and domain data are readily available technologies relevant to the WSF.

Figure 1 shows a high level conceptual architecture of the proposed system. The explicit objective is to avoid ‘stove pipe’ implementations and support the development of the integrated solutions (thus a contribution to Implementation Area 4). The platform will be open standards compliant and, as far as practicable, open source with the core technology components already developed as described above. Additional components can be rapidly developed and deployed operationally.

Figure 1: High-level conceptual architecture of the Integrated Water Resources Information System

The platform enables the proactive development of environmentally sustainable responses and planning decisions to water resource challenges. The following functional requirements are integrated from end-to-end:

- Ingest water data via diverse types of sensors, including remote and in-situ;

- Collate water information and services from custodians;

- Support the analyses of water consumption and availability using models and incorporating analytical and modelling tools (e.g., UrbanSim);

- Disseminate timely information to stakeholders through standardised services and interfaces

The high level architectural modules comprise as follows:

- A Sensor Hardware Layer that provides measurements and observations in a standards complaint format ranging from in-situ water quality sensors to remote sensing satellite data sources.

- The Middleware Layer provides the means to archive sensor observations and to provide access to other data archives on various, distributed databases and file systems through standardised services and interfaces. Water quality simulation and evaluation models are also maintained at this level.

- The Integration and Analysis Layer hosts software tools for processing and analytics, workflows that process observations, some of which may be long-running to monitor anomalous events, as well as orchestration modules that trigger sequences of processing activities on the occurrence of certain events or combinations of events.

- The Dissemination Layer incorporates the Wide Area Alerting System providing alerts and notifications to subscribed clients, “dashboard” functionalities for visualisation (mapping etc) and the provision of data sets at standardised interfaces for incorporation into client applications.

## 2.1  Implementation

System development and deployment will be needs driven, i.e., will be developed through close interaction with partners and users. Compliance in interoperability will be supported through the adoption of open standards for data encoding, information models, services and interfaces. An iterative specification-implementation cycle will be followed: in the first year of development, the identified use case of near-real-time monitoring and evaluation will be addressed.  The system will be extended to more sensors and a wider area of coverage in subsequent years. More advanced applications include user formulated queries, data transformations and simulations that support e.g., urban planning in terms of both water quality and quantity.

Year 1

WAAS deployment: The Alert and Notification subsystem will be implemented in the first year of development; the design and development of the integrated platform will commence with PG co-investment with more advanced implementations in the following years. The implementation time frame for the core infrastructure is 8 months, with a fully operational core platform in 12 months. Spatial and aspatial water data will be represented in compliance with open standards encodings (WaterML 2.0). Open standards (OGC compliant) services will be developed to expose data from water quality sensors in an interoperable manner.

Platform architecture: Concurrently, an end-to-end platform will be designed that complies with open standards and incorporates and supplement existing non-compliant water data provisioning components.

Core platform: The integrated platform will host these services and the process chains that monitor and identify anomalous events registered by water quality sensors (based on the technologies implemented for the Advanced Fire Information System). The Wide Area Alerting System (WAAS) will be deployed as part of this platform to disseminate alert notifications to users for evaluation.

Years 2 and 3

Implementation in years 2 and 3 entail the following

Refinement and expansion: The monitoring and evaluation process chain will be extended to 20 or more sensors as they are deployed in other areas.

Platform migration:  The system will be migrated to an open standards and open source architecture. Where required, systems will run in parallel until with controlled phase-over of the existing components.

Integration and simulation environment: Other water data sources and models will be integrated into the platform: Open source applications (such as UrbanSim) will be incorporated in a modelling and analysis environment that enables the creation of workflows for simulation and analysis of human settlement and water consumption dynamics

Robust sensor networks: Communications hardware, protocols and services will be implemented to enable the deployment of sensors in locations with unreliable or no power sources or poor digital communications infrastructure.

## 2.2 Schedule of tasks

The following table lists the task implementation time line, together with existing technologies to be implemented, deliverables and outputs. Individual tasks are described separately in greater detail.

| Months | Task number: Activity/Description |  | Technology (TRL): Deliverable |
| --- | --- | --- | --- |
| Year 1 |  |  |  |
| 01 – 06 | E1.1 Incorporate Wide Area Alerting System in existing CAS proposed system | WAAS (7): System able to send SMS messages to subscribed users |  |
| 04 – 06 | E1.2 Specify first level system architecture | Architecture specification report |  |
| 07 – 09 | E1.3 Monitoring system and integrated platform core infrastructure | EO4Vistrails (46): Open source geospatial data base, feeder modules, sensor services and interfaces implemented |  |
| 09 – 12 | E1.4 Operational integrated platform for monitoring and alerting | Validated web interface dashboard with alerting services |  |
| Year 2 |  |  |  |
| 13 – 18 | E2.1 Data series viewing functionality and subscription services; 20 sensor/probe inputs | TSV (5 6): Time series viewer implemented; system expanded to accommodate 20 sensors |  |
| 13 – 24 | E2.2 Foraging cognitive radio communication infrastructure | Wireless broadband device and ability to acquire alternative energy sources |  |
| 19 – 30 | E2.3 Implement fully integrated platform | Functional analytical environment implemented and deployed |  |
| 13 – 30 | E2.4 Modelling and analysis workflow environment | EO4V (6): Simulation and evaluation component integration completed |  |
| Year 3 |  |  |  |
| 24 – 32 | E3.1 integrated simulation models and data sources; Extension to further applications | EO4V (4 7): EO4Vistrails with analytical software implemented |  |
| 31 – 36 | E3.2 Advanced water quality and quantity modelling and evaluation applications | System extended to other applications (e.g. Blue drop) |  |

Table 1: Task implementation schedule

Much of the Year 1 activities above align with and contribute to Tasks and Deliverables specified in the Governance component of the overall proposal; in particular, Deliverables D2 (Implement integrated platform for simulations, options and decisions) and D3 (Consolidate and select intervention options, Task T3.1).

# 3.  Resources

## 3.1  Budget

The budgeted costs (Table 1) are for the human resources only; Running costs are detailed separately for each Task. PG funding will be co-invested in the development of the Integrated Platform.

| Activity/Task | Year 1 (ZAR) | Year 2 (ZAR) | Year 3 (ZAR) |
| --- | --- | --- | --- |
| [3.2] E1.1: Integrate dissemination (alerting notification) subsystem bases on WAAS* | 70 200 |  |  |
| [3.3] E1.2: Design end-to-end integrated platform | 90 675 |  |  |
| [3.10] E1.3 Implement near real time monitoring and simulation environment core infrastructure | 290 700 |  |  |
| [3.11] E1.4 Implement and migrate system to integrated platform | 369 900 |  |  |
| E2.1 Expand system to 20 geo-located sensors |  | 311 700 |  |
| E2.2 Foraging cognitive radio communication infrastructure |  | 1 068 267 | 534 133 |
| E2.3 Implement fully integrated platform |  | 546 900 | 372 900 |
| E2.4 Implement workflow modelling environment |  | 420 675 | 582 225 |
| E3.1 Fully integrated simulation environment |  |  | 926 100 |
| E3.2 Implement advanced applications |  |  | 821 100 |
| E3.3 Power saving for remote sensors |  | 635 000 |  |
| Total | 820 475 | 2 981 867 | 3 234 233 |

Table 2: Yearly budget (*These figures exclude amounts budgeted for these tasks in the Governance section)

Figures in Table 1 include the amount of R500 000 budgeted in Section 3 of the Governance component of the proposal. An amount of R160 000 PG funding will be co-invested in the first year, and further PG funds will be budgeted in subsequent years.  The following relevant projects provide complimentary funding.

| Project name | Budget (ZAR) |
| --- | --- |
| SWEOS (Safe Waters Earth Observation System) | 330 000 |
| Acid Mine Drainage (AMD) project | 1 432 000 |
| FP7 EO2HEAVEN (Earth Observation and the Mitigation of Health Risks) | 4 040 855 |
| EO2HEAVEN DST co-investment | 1 219 250 |

The SWEOS and AMD projects include the development of the same technologies as proposed here. EO2HEAVEN entails the development of models and technologies in support of the mitigation of water-borne health risks.

# Appendix D1

Existing technologies useful for the WSF

### A.1  Open Standards Compliant Sensor Web Services

Open standards (Open Geospatial Consortium) compliant services for sensor data ensure interoperability and are key to developing sensor observation and monitoring services in a cost-effective and sustainable manner. Several such services are deployed operationally in systems such as the Advanced Fire Information System (AFIS) and the Safe Waters Earth Observation System (SWEOS SRP), and more are developed for, for example, the Acid Mine Drainage (AMD SRP).

### A.2  Wide Area Alerting System

The Wide Area Alerting System (WAAS) is a TRL level 7 ICT platform that generates and disseminates data and information derived from data originating from heterogeneous sensors, models and/or monitoring processes, over multiple digital communications channels. Again, AFIS, is one example where this technology have been applied very successfully. The system facilitates

  - Ease of Administration; manage user subscriptions individually or group wise;

  - Flexibility; handles data about heterogeneous phenomena from different sensors;

  - Allow complex alert conditions to be configured – e.g. combine several phenomena but filter them by attributes, spatial location and time;

  - Extensible – easy to re-use system in different scenarios;

  - Scalable – handles observation/notification configurations in the order of hundreds of thousands, for thousands of users

  - Support for multiple notification channels, principally SMS, Internet and E-mail, and also via Instant Messaging, even radio.

### A.3  Earth Observation water quality monitoring and mapping

An sensor observation and monitoring system has been developed as part of the Safe Water Earth Observation System (SWEOS) that ingests MERIS and MODIS sensor data at 300 – 500m resolution. The system provides maps of eutrophication and cyanobacterial indices, water clarity and other for water quality products for approximately 250 major dams in South Africa. The following figure shows examples for some local dams. This technology is at TRL 7.

### A.4  EO4Vistrails

EO4VisTrails is an open-source scientific workflow and provenance management system based on Vistrails. VisTrails was designed to manage repeatable, rapidly-evolving different, but related, workflows created interactively. A key feature of VisTrails is its comprehensive provenance infrastructure that maintains a detailed history information about the processes, data and derived data products (history tree) produced during their executions. Figure 2 shows an example of the workflow history tree, a workflow (far top right) and the visual outputs produced (bottom).

The EO4Vistrails environment provides a platform to leverage sensor data resources together with analytical tools for simulations, data exploration and visualization. Scientific workflows are used to develop and robustly execute applications that are exploratory and dynamic in nature. Examples of such applications are near-real-time and long-running observation and monitoring processes. Spatio temporal processing often utilises large datasets requiring extensive CPU and memory resources in their processing. Other features currently implemented in EO4Vostrails include open standards compliant services and interfaces for accessing spatio temporal data resources and models as well as statistical analysis and visualisation tools to process, transform and render information.

Figure: Example of Vistrails application

### A.4  Minimum maintenance, autonomous and robust wireless networks for monitoring water conditions

This contribution includes a set of components permitting to establish a long-life power-efficient self-configuring wireless sensor network. The key features are:

- Minimum maintenance, long life and power efficiency

- Robust and able to re-route information, e.g. in case of a fault

- Autonomous; having the capability to operate on its own in a remote/inaccessible area

- Throughput, security; directed beam offers lower interference and lower probability of intercept

### A.5  Ultra-power-efficient array antenna to improve operation/life time of low power sensor nodes

An antenna able to have a narrow focussed beam pointing towards the desired receiver may help to save power. Estimates show that, for low power nodes, it is possible to improve the life/operation time by factor of ~5X, compared to single omni-directional antenna.

Envisioned applications: mass market or devices requiring long autonomous operation on batteries

Current status: theory, a prototype, measured low power consumption

Development required: 6-8 months (increase antenna gain and reduce antenna’s size)

### A.6  Algorithm development for localization / self-position-determination (without GPS, also minimizing the power consumption)

Many applications require the knowledge of its node’s geo-spatial position within the network. Some applications require lower cost devices, some others (e.g. underground mining) simply cannot receive GPS signal. This contribution offers algorithms capable of reliable determination of the position (localization) using wireless metrics free of GPS.

Envisioned applications: wireless sensor networks, underground mining

Current status: algorithms tested in wireless network simulator and showing superior performance (also resulted in PhD)

Development required: 6-18 months, depending on the requirements (inputs, mobility etc.)

### A.7  Wireless mesh networking device and routing algorithms for mesh networking

In many applications, it is necessary to be able to set up a network providing reliable services and capable of self-configuration and self-healing. The mesh networks with their peer-to-peer routing based connectivity do exactly that.

Envisioned applications: wireless sensor networks, underground mining

Current status: being manufactured and installed in South Africa to connect rural schools (over 200 installations), supports 2.4 GHz and 5.8 GHz frequency bands

Development required: adaptation to the specific requirements may be required

### 2.8  Foraging cognitive radio architecture (FOCORA) for broadband information relay over long distance in remote areas.

The architecture is developed into commodity wireless routers and it is a software that combines the functionality of wireless green and TV white space networking capabilities. The main features are that: the wireless network can transport broadband services (a converged voice, data, and video) information over long distance connectivity using spectrum band ~80MHz-1GHz of unused TV spectrum in most South African rural areas and optimised transmission power levels in energy-constrained application. It is anticipated that the FOCORA will relay green water information situated remotely to the water treatment plants as well as to water quality decision making organs in real time. In this framework architecture, wireless sensors, underwater sensors, underground sensors are deployed in water catchment areas and the FOCORA routers form back-haul links that connect the gathered data to the treatment plants and decision organs.

Envisioned applications: wireless back-haul for broadband applications

Current status: optimal transmission power control algorithm has been severally tested via simulations. Prototype development in wireless Mesh Lab is ongoing. Cognitive radio test-bed via USRP equipment has been demonstrated.

Development required: 12 to 18 months of FOCORA firmware development and real-life application.

Figure 1: Applications of self-configured FOCORA networking for broadband services relay

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Expand system to 20 sensors |  |  |  |  |  |  |  | Task Ref. Number: E2.1 |  |  |  |  |
| Description: Near real-time monitoring system is expanded to monitor at least 20 more water quality sensors |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 369900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 120 |  | 82800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 120 |  | 77400 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 40 |  | 35400 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 180 |  | 116100 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 311700 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 04/05/2012 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Foraging cognitive radio (FOCORA) communication infrastructure |  |  |  |  |  |  |  | Task Ref. Number: E2.2 |  |  |  |  |
| Description: It is a sustainable broadband based wireless backhaul communication infrastructure for Water quality data transport between water catchment areas, treatment stations, decision making points and usage points. It is characterized by ability to forage energy freely from the environment and opportunistically perform spectrum management of TV white spaces |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Thomas Olwal, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | Yr2 Mnth 01 |  | Payment details: |  | The WSF Project contribution is envisaged to take 12 months effective Approval of funds. |  |  |  |  |  |  |
|  |  | Yr3 Mnth 18 |  |  |  |  |  |  |  |  |  |  |
|  |  | 1602400 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: +wireless broadband communication device. +Ability to acquire alternative energy sources and transmit with optimal energy +Ability to scan TV white spaces and use spectrum judiciously +Software defined radios ability |  |  |  |  | Critical predecessor tasks: +optimal transmission energy been tested. +Cognitive radio TV white space trails are ongoing. +Spectrum monitoring platform has been implemented. |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost |  | Running |  | Notes for running costs |  |  | Capital |
| Fisseha Mekuria |  | 1170 | 360 |  | 421 200 |  | 45 000 |  | Field travels |  |  | 466 200 |
| Thomas Olwal |  | 765 | 720 |  | 550 800 |  | 55 000 |  | Field travels |  |  | 605 800 |
| Moshe Masonta |  | 570 | 720 |  | 410 400 |  | 55 000 |  | Field travels |  |  | 465 400 |
| Experimental equipment |  | 12000 | 5 |  | 00 |  | 60 000 |  | USRP+ Antennas |  |  | 60 000 |
| Sensors |  | 1000 | 5 |  | 00 |  | 5 000 |  | Multi-purpose sensors |  |  | 5 000 |
| Totals: |  |  |  |  | 1382400 |  | 220000 |  |  |  |  | 1602400 |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  |  | Critical successor tasks |  |  |
| Assumptions, Risk Factors & Contingencies: Assumption: multipurpose sensors exist off-the-shelves in local markets and no need to order overseas for highly specialised sensor types. Risks: Technical complexity, there is likelihood that equipment assembly might be complex causing a possible delay of the experimental deliverables. Contingencies: The system will utilise SDR approach to minimise Hardware complexities. |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Implement fully integrated platform |  |  |  |  |  |  |  | Task Ref. Number: E2.3 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 919800 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 300 |  | 207000 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 200 |  | 129000 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 200 |  | 177000 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 480 |  | 309600 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 80 |  | 97200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 919800 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Validated monitoring system and core platform, including data models and first level system components |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Core components of existing system migrated to open platform |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Workflow modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E2.4 |  |  |  |  |
| Description: EO4VisTrails implemented for simulation and modelling environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 Apr 2013 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 30 Sep 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  | 1002900 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 420 |  | 289800 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 180 |  | 116100 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 160 |  | 141600 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 480 |  | 309600 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 120 |  | 145800 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 1002900 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Operational version of modelling and simulation environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Fully integrated simulation and modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E3.1 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment, data sources and extension to further applications |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2014 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2015 |  |  |  |  |  |  |  |  |  |  |
|  |  | 926100 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: Dissemination (WAAS) validated and operational |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 360 |  | 248400 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 240 |  | 154800 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 120 |  | 106200 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 420 |  | 270900 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 120 |  | 145800 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 926100 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Fully integrated platform including data sources and further applications (eg UrbanSim) |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-01 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Fully integrated simulation and modelling environment |  |  |  |  |  |  |  | Task Ref. Number: E3.2 |  |  |  |  |
| Description: Fully integrated platform implemented to accommodate simulation and modelling environment, data sources and extension to further applications |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Terence van Zyl, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | 1 July 2014 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | 31 Mar 2015 |  |  |  |  |  |  |  |  |  |  |
|  |  | 821100 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: Specified user & partner needs Open source APIs, databases and tools and API to sensors |  |  |  |  | Critical predecessor tasks: |  |  |  |  |  |  |  |
| Resources |  | Unit cost | Units |  | HR Cost | Running |  |  |  | Notes for running costs |  | Capital |
| G McFerren |  | 690 | 360 |  | 248400 |  |  |  |  |  |  |  |
| M Mtetsfwa |  | 645 | 240 |  | 154800 |  |  |  |  |  |  |  |
| T van Zyl |  | 885 | 100 |  | 88500 |  |  |  |  |  |  |  |
| D Hohls |  | 645 | 360 |  | 232200 |  |  |  |  |  |  |  |
| A Vahed |  | 1215 | 80 |  | 97200 |  |  |  |  |  |  |  |
| Totals: |  |  |  |  | 821100 |  |  |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
|  | Main output: Advanced applications including water quantity and other water quality aspects |  |  |  |  |  |  |  |  |  |  |  |  |
| Assumptions, Risk Factors & Contingencies: Assumptions: (a) Sensor interface parameters and data are provided (b) users and partners describe specific needs. User requirements will be iteratively refined based on user feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

| TASK DETAIL SHEET |  |  |  |  |  |  |  | Date: 2012-04-25 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task heading: Power saving for remote sensors |  |  |  |  |  |  |  | Task Ref. Number: E3.3 |  |  |  |  |
| Description: Adaptation of the technology to the wireless sensor [network] nodes, permitting to increase the device longevity by up to 4-5 times. |  |  |  |  |  |  |  |  |  |  |  |  |
| Responsible Resource: Albert Lysko, Meraka Institute |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date: Finish date: Total Budget: |  | Yr2, Mnth 01 |  | Payment details: |  |  |  |  |  |  |  |  |
|  |  | Yr2, Mnth 12 |  |  |  |  |  |  |  |  |  |  |
| Input and specifications: - Host device (wireless sensor mote) - Environmental and casing requirements - Access to software on the device and network of devices |  |  |  |  | Critical predecessor tasks: - The host device (wireless sensor mote) must be able to function standalone - Network topology/config. well have been defined |  |  |  |  |  |  |  |
| Resources |  | Unit cost R/hour | Units |  | HR Cost |  | Running |  |  | Notes for running costs |  | Capital |
| Albert Lysko |  | 885 | 560 |  | 459,600 |  | 50,000 |  |  | manufacturing |  |  |
| Sensor device’s owner unit |  | 1000 | 140 |  | 140,000 |  | 12,000 |  |  | Fitting into existing device |  |  |
| Totals: |  |  |  |  | 635,600 |  | 62,000 |  |  |  |  |  |
| Ref | Notes on Outputs, Specifications & Controls |  |  |  |  |  |  |  | Critical successor tasks |  |  |  |
| Assumptions, Risk Factors & Contingencies: It is assumed: 1) the sensor device exists and already works with a traditional antenna, 2) the software running on the wireless node is open for access, 3) there is no need to design a custom enclosure (i.e. it is possible to fit the antenna into the existing device or to find a suitable commercially available enclosure). Contingencies to (3): (i) design time for the enclosure (~R100K?) and (ii) more running needed (~R50K per iteration X 2-3 iterations). |  |  |  |  |  |  |  |  |  |  |  |  |
| Various notes (including capital needs): |  |  |  |  |  |  |  |  |  |  |  |  |

APPENDIX E: MEASURABLES, BUDGET, GANTT AND CASH-FLOW

The project measurables for the WSF are shown as Quarterly stage-gate deliverables for the WSF, PG funded and Other co-funded projects in Table 1 along with the associated value for each.

Table 1: Stage Gate analysis for the WSF

| IA1 PLANNING & GOVERNANCE (COORDINATED BY NRE) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task | Quarter 1 | Value | Quarter 2 | Value | Quarter 3 | Value | Quarter 4 | Value |
| WSF funding | Project management - detailed project plan. Stakeholder consultation | 825 | T1.1: Policy context, institutional arrangements and decision processes defined for WWTWs - nationally and for case areas in particular T1.2: Relationships between urban development and wastewater volumes and quality quantified - nationally and for case areas in particular T1.3: Water infrastructure, capacity and consumption data acquired and incorporate into relational database | 2150 | T1.4: Catchment (downstream users and environment) objectives and management options defined (NFEPA, and Human health) T2.2: UrbanSim, Geo-Spatial Analysis Platform and StepSA updated for case areas | 2236 | T2.1: Formalise and implement Living Lab process (ongoing) T2.3: Technologies (ACWUA DSS, ECO2 model, WSIL Scenarios framework) and data incorporated in an integrated risk and options matrix T3.1: UrbanSim, Geo-Spatial Analysis Platform and StepSA iterations and projections T3.2: Prioritize options for WWTWs in the case areas | 1289 |
| NRE: Aquabase, wetland index and water sustainability | Stakeholder consultation Data collection | 355 | Data and literature synthesis | 532 | Conceptual model development | 532 | Develop models and ecological production functions | 532 |
| BE: Living lab application | Data acquisition and set up | 182 | Desk Top Review of Urban Form Literature, Policies and Plans, Analysis of Simulation Results | 273 | Prepare policy brief on key findings in recpect of alternative development scenarios | 273 | Development Policy Brief and Conference Papers. | 273 |
| BIO: Water sustainability | Literature review | 273 | Assessment of detection methods | 409 | Development of detection methods in the context of WSF | 409 | Testing of detection methods | 409 |
| NRE: Coaltech sustainability and wetlands | Stakeholder engagement and project details | 655 | Establish cause-effect relationships | 982 | Identify and compare intervention options | 982 | Implementation of selected options (continue into 2013/14) | 982 |
| BE: IPDM and GITMC | Data acquisition and set up | 182 | Data acquisition. Model Customisation and validation. | 273 | Expand geographic scope, deepen public transport component. | 273 | Scenario Testing and preparation of simulation results | 273 |

| IA2 INFRASTRUCTURE INTERVENTION (COORDINATED BY BE) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task | Quarter 1 | Value | Quarter 2 | Value | Quarter 3 | Value | Quarter 4 | Value |
| WSF Funding | Site prepared, detail planning completed, equipment procurement initiated | 440 | Detailed planning complete, design and construction initiated | 1370 | Community programme initiated, Design and construction complete, equipment installed | 3090 | Community programme initiated, baseline study complete | 700 |
| BE: Baseline study for impact assessment |  |  | Baseline study complete | 900 |  |  |  |  |
| BE: Development of conceptual design of enhanced aerobic solution | Lit survey done | 200 |  |  | Conceptual design complete | 900 |  |  |
| BE: DST project on AD: |  |  |  |  |  |  |  |  |
| Degritting of existing AD | None | 0 | AD degritted | 320 | Complete |  |  |  |
| Purchase of equipment for upgrade | None | 0 | Equipment purchased | 7507 |  |  |  |  |
| Operation of plant and evaluation | None | 0 | None | 0 | Operation and evaluation ongoing | 600 |  |  |
| ERWAT maintenance and community programme | None | 0 | Community programme initiated | 400 | Community programme ongoing | 600 |  |  |

| IA3 REAL TIME MONITORING AND RESPONSE (COORDINATED BY CAS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task | Quarter 1 | Value | Quarter 2 | Value | Quarter 3 | Value | Quarter 4 | Value |
| WSF Funding | Preparation and equipment manufactured, site inspections | 1769 | Installations and water footprints complete | 3527 | Version 1 of next generation unit complete | 3362 | Full data reporting, next generation manufacturing spec | 3417 |
| MSM: Project Management & field sampling (PG MSM) | Groundwork and lit survey | 150 | Field data collection complete | 300 | Organic probe prototype complete | 300 | Full data reporting, and specs for organic measurement | 150 |
| MER: Project Management (PG MERAKA) | Project management | 0 | Project management | 80 | Project management | 80 |  | 0 |
| CAS: Systems, algorithms and rules | Development | 1273 | Development | 1909 | Development | 1909 | Development | 1909 |

The cashflow associated with the expenditure for funds from the WSF, the PG portion and the Other co-funding for the first year is summarised in Table 2 below. The detailed breakdown of tasks and associated budget are provided in Appendices A, B, C and D.

The detailed cashflow from the WSF fund for the first year of the integrated project is shown in Table 3 below.

Table 2: Cashflow for the WSF and associated co-funding sources

| Description | 2013/14 |  |  |  |  |  |  |  |  |  |  |  |  |  | TOTALS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q1 |  | Q2 |  |  |  |  | Q3 |  |  | Q4 |  |  |  |  |  |  |
|  | May | Jun | Jul | Aug |  | Sep |  | Oct | Nov | Dec |  | Jan | Feb | Mar | WSF | PG | OTHER |
| WSF: 2012/13 CASHFLOW (Rx1000) | 2 110 | 2 149 | 2 239 | 3 214 |  | 3 044 |  | 3 189 | 4 135 | 2 814 |  | 2 344 | 3 133 | 1 629 | 30000 |  |  |
| Cashflow sub-totals associated with Quarterly stage-gate deliverables | 4259 |  | 8497 |  |  |  |  | 10138 |  |  |  | 7106 |  |  | 30000 |  |  |
| PG: 2012/13 CASHFLOW (Rx1000) | 455 | 1 005 | 1 025 |  | 1 035 |  | 735 | 735 | 635 | 525 |  | 505 | 505 | 455 |  | 7610 |  |
| OTHER: 2012/13 CASHFLOW (Rx1000) | 1 055 | 1 055 | 1 055 |  | 1 375 |  | 1 055 | 1 055 | 8 762 | 1 255 |  | 1 455 | 1 455 | 1 455 |  |  | 21027 |

Table 3: Project Gantt Chart and cashflow breakdown per task (Year 1). (Amounts in R x 1000)

|  | Task/Activity | 2013/14 |  |  |  |  |  |  |  |  |  |  |  | TOTALS | TOTALS | TOTALS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Description | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |  | WSF | PG | OTHER |
| 1 | IA 1 PLANNING & GOVERNANCE (COORDINATED BY NRE) |  |  |  |  |  |  |  |  |  |  |  |  | 6 500 | 4 450 | 4 600 |
| 1.1 | Systems model: Cause-effect relationships | 350 | 350 | 350 | 350 | 350 | 350 | 336 |  |  |  |  |  | 2 436 |  |  |
| 1.2 | Establish integrated simulation platform setup and calibration |  |  | 200 | 300 | 400 | 400 | 400 | 200 | 400 | 386 |  |  | 2 686 |  |  |
| 1.3 | Consolidate and select intervention options |  |  |  |  |  | 100 | 200 | 100 | 200 | 115 |  |  | 715 |  |  |
| 1.4 | Project Management & reporting | 75 | 50 | 75 | 50 | 75 | 50 | 75 | 25 | 50 | 63 | 75 |  | 663 |  |  |
| 1.5 | NRE: Aquabase, wetland index and water sustainability | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 |  |  | 1 950 |  |
| 1.6 | BE: Living lab application | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 |  |  | 1 000 |  |
| 1.7 | BIO: Water sustainability | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 | 136 |  |  | 1 500 |  |
| 1.8 | NRE: Coaltech sustainability and wetlands | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 327 |  |  |  | 3 600 |
| 1.9 | BE: IPDM and urban dynamics laboratory | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 |  |  |  | 1 000 |

| 2 | IA2 INFRASTRUCTURE INTERVENTION (COORDINATED BY BE) |  |  |  |  |  |  |  |  |  |  |  |  | 6 300 | 2 000 | 9 427 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | Preparation of site at Olifantsfontein | 90 |  |  |  |  |  |  |  |  |  |  |  | 90 |  |  |
| 2.2 | Detailed planning | 100 | 100 | 100 |  |  |  |  |  |  |  |  |  | 300 |  |  |
| 2.3 | Preparation for and execution of community programme |  |  |  |  | 100 | 100 | 200 | 200 | 200 | 200 |  |  | 1 000 |  |  |
| 2.4 | Procurement of equipment |  | 50 | 30 | 25 | 25 | 50 |  |  |  |  |  |  | 180 |  |  |
| 2.5 | Installation of new equipment (mixing, heat exchange, piping, CHP generator, etc) |  |  |  | 100 | 100 | 50 | 50 | 100 |  |  |  |  | 400 |  |  |
| 2.6 | Design and construction of the second tank and gas storage |  |  |  |  | 690 | 600 | 600 | 690 |  |  |  |  | 2 580 |  |  |
| 2.7 | Installation of gas polishers / scrubbers to remove unwanted content from the biogas |  |  |  |  |  | 200 | 100 | 50 |  |  |  |  | 350 |  |  |
| 2.8 | Monitor and evaluate results (Baseline) |  | 100 | 100 | 100 |  |  |  | 100 | 100 | 100 | 100 |  | 700 |  |  |
| 2.9 | BE: Baseline study for impact assessment |  | 300 | 300 | 300 |  |  |  |  |  |  |  |  |  | 900 |  |
| 2.10 | BE: Development of conceptual design of enhanced aerobic solution |  | 200 | 200 | 200 | 200 | 200 | 100 |  |  |  |  |  |  | 1 100 |  |
| 2.11 | BE: DST project on AD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.11.1 | Degritting of existing AD |  |  |  | 320 |  |  |  |  |  |  |  |  |  |  | 320 |
| 2.11.2 | Purchase of equipment for upgrade |  |  |  |  |  |  | 7 507 |  |  |  |  |  |  |  | 7 507 |
| 2.11.3 | Operation of plant and evaluation |  |  |  |  |  |  |  |  | 200 | 200 | 200 | Ongoing |  |  | 600 |
| 2.12 | ERWAT maintenance and community programme |  |  |  |  |  |  | 200 | 200 | 200 | 200 | 200 |  |  |  | 1 000 |
| 2.13 | Project Management & reporting | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 150 |  | 700 |  |  |

| 3 | IA3 REAL TIME MONITORING AND RESPONSE (CAS) |  |  |  |  |  |  |  |  |  |  |  |  | 12 075 | 1 160 | 7 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Pilot Sites Units Yr 1 | 125 | 250 | 200 | 200 | 100 | 100 | 100 | 100 | 60 | 60 | 60 |  | 1 355 |  |  |
| 3.2 | Integrate dissemination (alerting notification) subsystem bases on WAAS (MERAKA) | 20 | 10 | 10 | 10 | 10 | 10 |  |  |  |  |  |  | 70 |  |  |
| 3.3 | Design end-to-end integrated platform (MERAKA) |  |  |  | 30 | 30 | 30 |  |  |  |  |  |  | 90 |  |  |
| 3.4 | Configuration of Pilot Units Yr 1 |  | 25 |  | 25 |  | 25 |  | 25 |  |  |  |  | 100 |  |  |
| 3.5 | Governance - Site Inspections | 100 | 100 | 100 | 100 | 90 |  |  |  |  |  |  |  | 490 |  |  |
| 3.6 | Governance - Laboratory Testing |  | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 42 |  | 442 |  |  |
| 3.7 | Governance - WWTW Assessments |  | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 | 354 |  | 3 540 |  |  |
| 3.8 | Modelling & Algorithms |  | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  |  |  | 600 |  |  |
| 3.9 | Hardware & Software |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 800 |  |  |
| 3.10 | Implement near real time monitoring and simulation environment core infrastructure (MERAKA) |  |  |  |  |  |  | 100 | 100 | 90 |  |  |  | 290 |  |  |
| 3.11 | Implement integrated platform (MERAKA) |  |  |  |  |  |  |  |  | 70 | 150 | 150 |  | 370 |  |  |
| 3.12 | Next Generation | 150 | 250 | 250 | 250 | 250 | 300 | 300 | 400 | 450 | 400 | 228 |  | 3 228 |  |  |
| 3.13 | Project Management (WSF) | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 25 | 25 | 100 | 150 |  | 700 |  |  |
| 3.14 | MSM: Project Management & field sampling (PG MSM) | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 50 |  |  | 1 000 |  |
| 3.15 | MER: Project Management (PG MERAKA) |  |  | 20 | 30 | 30 | 30 | 30 | 20 |  |  |  |  |  | 160 |  |
| 3.16 | CAS: Systems, algorithms and rules | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 |  |  |  | 7 000 |

| 4 | WSF PROGRAMME COORDINATION BY NRE |  |  |  |  |  |  |  |  |  |  |  |  | 5125 | 0 | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Planning, Quality Control and Reporting | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 240 |  | 2240 | 0 | 0 |
| 4.2 | Risk management (Contingency pool) | 700 |  |  | 700 |  |  | 700 |  |  | 785 |  |  | 2885 | 0 | 0 |
|  | FUNDING TOTALS |  |  |  |  |  |  |  |  |  |  |  |  | 30 000 | 7 610 | 21 027 |

APPENDIX F: LOGFRAME WITH DELIVERABLES FOR STAGE-GATE ASSESSMENT (Year 1)

| Key Questions | Work Packages (Year 1) | Deliverables (Year 1) |
| --- | --- | --- |
| Q1.Can equitable access and sustainable and inclusive development be facilitated by following an approach that is strategic, integrated, and promotes cooperative governance and planning for water sustainability. | WP1: Establish relationship between governance, human settlement, WWTWs and downstream users WP2: : Implement integrated platform for simulations, options and decisions WP3: Consolidate and select intervention options . | D1: Report on the established relationship between governance, human settlement, WWTWs and downstream users D2: An integrated platform for the pilot areas D3: Report outlining the prioritized intervention areas, |
| Q2: Can the improvement of the functionality of WWTW reduce the risk to people’s health and to water resources? | WP4: Increasing the capacity of municipal WWTW WP5: Providing electricity from a WWTW waste stream WP6: Provision of deactivated sludge as a resource for community based fertilizer production enterprise. | D4: Upgraded Anaerobic Digester D5: The Pilot plant is commissioned D6: Operator training programme established and in progress D7: A report specifying the composition of the gas D8: Certified deactivated sludge produced from the pilot plant |
| Q3: Can a system (near) real-time WWTW performance information facilitate effective and timely responses to potential WWTW failure | WP7: Manufacturing and installation of the required sensing station system WP8: Development and upgrading of the required software and Hardware WP9: Improving the water quality algorithms WP10: Setting up an integrated platform for monitoring and alerting | D9: Upgraded and up-scaled sensing stations installed, commissioned and maintained at pilot sites D10: Wide Area Alerting Sub-system as component of the real-time monitoring and response system implemented D11: Architecture for the integrated water information platform designed based on open standards and open source software. D12: Report on detailed WWTW assessments D13: Refined models & site specific rules D14: A report on the performance of the integrated platform for monitoring and alerting. |

For application in this context

R730k contingency is also available as part of the contingency pool

National Freshwater Ecosystem Priority Areas

Urban Growth Simulation Platform

Geo-Spatial Analysis Platform

Spatial and Temporal Evidence for Planning in South Africa

Assessment of Considerations for Water Use Allocations

Ecology (to) Economy Model

Water Sector Institutional Landscape Scenarios

Unit PG

http://code.google.com/p/eo4vistrails/

http://www.vistrails.org/index.php/Main_Page#VisTrails_Overview